## CapEx 23-24
Scheme-wise details of Capital Expenditure incurred in FY: 2023-24 of 4th control period
(figures in Crores)
Sl No. | Project Code / Scheme ID (SAP Code) | Project Title (SAP Project title) | Scope of work (Names of all the Sub-stations and Lines included in the scheme) | Project Purpose (SI/SE/SR/GE) | Administrative Approval TOO Ref. | SRPC approval (if any) | TGERC Investment Approval Ref. | Total approved Cost (in Cr) | Source of funds |  |  |  | Project Start Date (DD-MM-YY) | Project Completion Date (DD-MM-YY) | DOC | Opening CWIP as on 31.03.2023 | Actual Expenditure from 01.04.2023 to 31.03.2024 | Cumulative expenditure upto 31.03.2024 | % Capatalisation | Remarks / Balance works , if any.
[9 empty] | TGTransco Funds | Loan source | Loan Amount | Grants, if any | [8 empty] | CWIP | CApital Expenditure 2023-24
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
Annual Petition for 2024-25 for Transmission Business filed with TGERC
I. Ongoing Schemes as on 01.04.2023
Sub-total-I | [15 empty] | 69.951 | 150.7431 | 219.8556
1 | A-15-05 | AUGof PTR@EHT SS for extending 9Hrs |  | SE | TOO |  |  | 32.01 | TSTRANSCO |  |  |  | 01.04.2016 | 31.03.2024 |  | 0.02 | -0.13123 | -0.11123 | -0.3475% |  | 204738.33 | -188880.07
2 | A-15-22 | STRENGTHENING OF 10 NOS. OVERLOAD LINES | Stengthening of existing conductor with HTLS |  | T. O. O. (CE/Transmission) MS.No.158 dated 23.11.2016 |  |  | 215.07 |  | PFC |  |  | 18.04.2016 | 14.12.2016 |  | 2.133 | -0.031562 | 2.1014 | 0.9771% |  | 21331362.3 | -114585.24
3 | A-16-01 | 3rd 31.5MVA PTR at Adilabad SS |  | SE |  |  |  | 1.02 | TSTRANSCO |  |  |  | 01.04.2016 | 31.03.2024 |  | 0.018 | 0 | 0.018 | 1.765% |  | 178269 | 0
4 | A-16-04 | Aug-adtnl 80MVAPTR-132kVSS Madapur-Metro |  | SE |  |  |  | 4.76 | [7 empty] | 0.009 | -0.15416 | -0.14516 | -3.049% |  | 90034 | -1451526
5 | A-17-01 | 24 Hrs. Agl. supply works in WGL ZONE |  | SE |  |  |  | 7.22 | TSTRANSCO |  |  |  | 01.04.2017 | 31.03.2024 |  | 0.221 | -0.0035264 | 0.21747 | 3.012% |  | 2205253.05 | 40788.4
6 | A-17-02 | Aug Sys Stren & 24 Hrs Agl METRO & RURAL |  | SE |  |  |  | 51.29 | TSTRANSCO |  |  |  | 01.04.2017 | 31.03.2024 |  | 0.754 | -0.12371 | 0.63029 | 1.229% |  | 7543501.54
7 | A-18-01 | Aug of PTR capacity at 220KV Ch'gutta |  | SE |  |  |  | 15.3 | TSTRANSCO |  |  |  | 01.04.2018 | 31.03.2025 |  | 0.011 | -0.011209 | -0.0002091 | -0.001367% |  | 112091
8 | A-18-05 | PSDF STRENGTHENING-7NO'S 220KV EHT LINES | Stengthening of existing conductor with HTLS |  | T. O. O. (CE/Transmission) MS. No. 09 Dated: 13.04.2018 |  |  | 100.55 |  |  |  | PSDF grant-75% | 18.09.2018 | 20.05.2019 |  | 1.354 | -0.13663 | 1.2174 | 1.211% |  | 13540079.08
9 | A-19-01 | Aug of 4th 160 MVA at 220KV Gachibowli |  | SE | T.O.O.396, Dt:03.07.2019 |  |  | 6.21 | TSTRANSCO |  |  |  | 01.04.2019 | 31.03.2024 |  | 0.112 | -0.025993 | 0.086008 | 1.385% |  | 1118777.97
10 | A-19-02 | Augmentation of 132 KV Chintal SS |  | SE | T.O.O.724, Dt:22.02.2020 |  |  | 0.69 | TSTRANSCO |  |  |  | 01.04.2019 | 31.03.2024 |  | 0.064 | 0.11337 | 0.17737 | 25.71% |  | 642304.68 | 1190516.18
11 | A-19-03 | Augmentation of 80 MVA at 132 KV IDPL SS |  | SE | T.O.O.731, Dt:07.03.2020 |  |  | 0.72 | TSTRANSCO |  |  |  | 01.04.2019 | 31.03.2024 |  | 0.065 | -0.034329 | 0.030671 | 4.26% |  | 648057.18
12 | A-19-04 | Augmentation of PTRs at 220 KV Hayathnag |  | SE | T.O.O.737, Dt:18.03.2020 |  |  | 14.4 | TSTRANSCO |  |  |  | 01.04.2019 | 31.03.2024 |  | 0.03 | 0.18771 | 0.21771 | 1.512% |  | 300758.4
13 | A-19-05 | Augmentation of PTRs at gesukonda & Tiru |  | SE | T.O.O.738, Dt:18.03.2020 |  |  | 0.76 | TSTRANSCO |  |  |  | 01.04.2019 | 31.03.2022 |  | 0.188 | -0.013199 | 0.1748 | 23% |  | 1880882.12
14 | A-20-01 | Augmentation at 220KV Manthani SS & 132K |  | SE | T.O.O.780, Dt:10.06.2020 |  |  | 8.97 | TSTRANSCO |  |  |  | 01.04.2020 | 31.03.2024 |  | 1.409 | 4.2116 | 5.6206 | 62.66% |  | 14088975.26 | 41316599.62
15 | A-20-02 | Aug of 3rd 220/132KV PTR at 400KV Narsap |  | SE | T.O.O.792, Dt:26.06.2020 |  |  | 3.63 | TSTRANSCO |  |  |  | 01.04.2020 | 31.03.2024 |  | 1.866 | 0.45317 | 2.3192 | 63.89% |  | 18664146.23 | 2720217.92
16 | A-20-03 | Aug of PTR at Warangal & Karimnagar Circ |  | SE | T.O.O.856, Dt:03.10.2020 |  |  | 8.66 | TSTRANSCO |  |  |  | 01.04.2020 | 31.03.2024 |  | 0.795 | 1.2798 | 2.0748 | 23.96% |  | 7952406.25 | 16869243.1
17 | A-20-04 | Augmentation of PTR at 132KV Donthanpall |  | SE | T.O.O.870, Dt:03.11.2020 |  |  | 0.33 | TSTRANSCO |  |  |  | 01.04.2020 | 31.03.2024 |  | 0.088 | -0.013312 | 0.074688 | 22.63% |  | 884721.52
18 | A-20-05 | Augmentation of PTR at 132KV Khaithalapu |  | SE | T.O.O.883, Dt:18.11.2020 |  |  | 8.25 | TSTRANSCO |  |  |  | 01.04.2020 | 31.03.2024 |  | 0.038 | -0.00048 | 0.03752 | 0.4548% |  | 375538.54
19 | A-20-06 | Aug of 3rd PTR at 132KV MDPally SS |  | SE | 03.01.2020 |  |  | 3.92 | TSTRANSCO |  |  |  | 03.01.2020 | 31.03.2024 |  | 0.134 | -0.063957 | 0.070043 | 1.787% |  | 1344724.65 | 27503.38
20 | A-20-07 | Aug of 4rd PTR at 132KV Pashmailaram SS |  | SE | T.O.O.1026, Dt:30.03.2021 |  |  | 1.56 | TSTRANSCO |  |  |  | 30.03.2021 | 31.03.2024 |  | 0.159 | 0.017295 | 0.17629 | 11.3% |  | 1593439.72 | 1523969.94
21 | A-21-01 | Aug of 160 MVA PTR at 400KV Suryapet SS |  | SE | T.O.O.1034, Dt:12.04.2021 |  |  | 8.35 | TSTRANSCO |  |  |  | 01.04.2021 | 31.03.2025 |  | 0.148 | 0.20341 | 0.35141 | 4.208% |  | 1483332.22 | 1001306.76
22 | A-21-02 | Aug of 132/33 KV PTRs at Mamidipally & 4 |  | SE | T.O.O.1053, Dt:07.05.2021 |  |  | 11.47 | TSTRANSCO |  |  |  | 01.04.2021 | 31.03.2025 |  | 0.329 | 4.3737 | 4.7027 | 41% |  | 3294993.34 | 46375826.72
23 | A-21-04 | Aug. of PTR capacity at 220KV Huzurabad |  | SE | T.O.O.1167, Dt:18.08.2021 |  |  | 6.03 | TSTRANSCO |  |  |  | 18.08.2021 | 31.03.2025 |  | 0.183 | 9.3188 | 9.5018 | 157.6% |  | 1834323.22 | 90900040.5
24 | A-21-05 | Augmentations of 220KV PTRs at 5Nos Subs |  | SE | T.O.O1209, Dt:04.10.2021 |  |  | 6.03 | TSTRANSCO |  |  |  | 04.10.2021 | 31.03.2025 |  | 3.062 | 28.4348 | 31.4968 | 522.3% |  | 30618461.72 | 189385719.16
25 | A-21-06 | Augmentations of 132KV PTRs at 24Nos Sub |  | SE | T.O.O1211, Dt:07.10.2021 |  |  | 48.75 | TSTRANSCO |  |  |  | 07.10.2021 | 31.03.2025 |  | 2.202 | 39.4542 | 41.6562 | 85.45% |  | 22017443.68 | 360308521.27
26 | A-22-02 | Augmentation of PTR at 132KV Balanagar S |  | SE | T.O.O.1486, Dt:11.10.2022 |  |  | 6.27 | TSTRANSCO |  |  |  | 11.10.2022 | 31.03.2025 |  | 0.046 | 5.1495 | 5.1955 | 82.86% |  | 455028.79 | 51032469
27 | D-16-06 | Erection 33KV Bays TSNPDCL | Erection 33KV Bays TSNPDCL | SE | T.O.O 46, Dt:31.03.2016 | --- | --- | 16.31 | --- | --- | --- | --- | 31.03.2016 | 31.03.2024 |  | 0.017 | 0 | 0.017 | 0.1042% | Deposit contribution Works - All works Completed | 173110
28 | D-18-01 | replacement of 1No. CVT at M/s. OCC Ltd. | replacement of 1No. CVT at M/s. OCC Ltd. | SR | Lr. No 02 Dt 01.04.2018 | --- | --- | 0.05 | --- | --- | --- | --- | 01.04.2018 | 31.03.2025 |  | 0.013 | -0.012543 | 0.0004566 | 0.9132% | Deposit contribution Works | 125434
29 | D-18-03 | Implementation of DAS for RTSS | Implementation of DAS for RTSS | SR | Lr.No 175 Dt 25.01.2018 | --- | --- | 3.8 | --- | --- | --- | --- | 25.01.2018 | 31.03.2025 |  | 0.05 | 0.0095978 | 0.059598 | 1.568% | Deposit contribution Works | 497850.38 | 593828.64
30 | D-18-04 | Erection of ABT Metering arrangement 220 | Erection of ABT Metering arrangement 220 | [10 empty] | 31.03.2025 |  | 0 | 0.05
31 | D-18-06 | Replacemnt of 132KV CT's & PT's for 132K | Replacemnt of 132KV CT's & PT's for 132K | SR | Lr.No 1247 Dt 12.03.2018 | --- | --- | 0.43 | --- | --- | --- | --- | 12.03.2018 | 31.03.2025 |  | 0.036 | -0.036186 | -0.00018597 | -0.04325% | Deposit contribution Works | 361859.67
32 | D-18-11 | Replacement of old CTs & PTs at 132KV OC | Replacement of old CTs & PTs at 132KV OC | SR | Lr.No 4228 Dt 28.09.2018 | --- | --- | 0.57 | --- | --- | --- | --- | 28.09.2018 | 31.03.2025 |  | 0.065 | 0 | 0.065 | 11.4% | Deposit contribution Works | 654517.68
33 | D-18-20 | Providing of ABT Meters for all Traction | Providing of ABT Meters for all Traction | SR | Lr.No 138 Dt 21.02.2019 | --- | --- | 9.65 | --- | --- | --- | --- | 21.02.2019 | 31.03.2025 |  | 2.168 | 0.022229 | 2.1902 | 22.7% | Deposit contribution Works | 21675043.78 | 2213429.81
34 | D-19-06 | 132KV Durshed-Karimnagar | DCW | SR |  |  |  | 2.98 |  |  |  |  | 01.04.2023 | 31.03.2025 |  | 0.003 | 0 |  |  | Deposit contribution Works
35 | D-19-07 | ABT Metering at 132 KV Manuguru & Kothag | ABT Metering at 132 KV Manuguru & Kothag | SR | Lr.No.333 Dt 18.06.2019 | --- | --- | 1.06 | --- | --- | --- | --- | 18.06.2019 | 31.03.2025 |  | 0.081 | 0.07213 | 0.15313 | 14.45% | Deposit contribution Works | 810492.27 | 1127803.84
36 | D-19-08 | ABT Metering at 132KV OCM & Mandamarry S | ABT Metering at 132KV OCM & Mandamarry S | SR | Lr.No.677 Dt 05.10.2019 | --- | --- | 9.29 | --- | --- | --- | --- | 05.10.2019 | 31.03.2025 |  | 0.239 | 0.21025 | 0.44925 | 4.836% | Deposit contribution Works | 2393758.03 | 2162809.7
37 | D-19-14 | 33 KV Bay extension at 220KV SS Manguru | 33 KV Bay extension at 220KV SS Manguru | SE | Lr.No.14 Dt 04.03.2020 | --- | --- | 0.2 | --- | --- | --- | --- | 04.03.2020 | 31.03.2025 |  | 0.025 | 0.0020047 | 0.027005 | 13.5% | Deposit contribution Works | 249073.75 | 26703.87
38 | D-20-16 | Erection of 4Nos 33KV Bays for M/s Amazo | Erection of 4Nos 33KV Bays for M/s Amazo | SE | Lr.No.33 Dt 17.04.2020 | --- | --- | 1.59 | --- | --- | --- | --- | 17.04.2020 | 31.03.2025 |  | 0.236 | -0.093999 | 0.142 | 8.931% | Deposit contribution Works | 2355958.02
39 | D-20-17 | Modification of Control Room at 132 KV S | Modification of Control Room at 132 KV S | [10 empty] | 31.03.2025 |  | 0 | 0.13
40 | D-20-20 | 33KV Bay at 220KV FABCITY SS for chirpa | 33KV Bay at 220KV FABCITY SS for chirpa | SE | Lr.No.70 Dt 08.05.2020 | --- | --- | 0.43 | --- | --- | --- | --- | 08.05.2020 | 31.03.2025 |  | 0.063 | -0.0034515 | 0.059548 | 13.85% | Deposit contribution Works | 631025.54
41 | D-20-21 | 33KV bay for SCCL,Bittupally at 132KV Ma | 33KV bay for SCCL,Bittupally at 132KV Ma | SE | Lr. No 1585 Dt 08.07.2020 | --- | --- | 0.27 | --- | --- | --- | --- | 08.07.2020 | 31.03.2025 |  | 0.024 | -0.00025143 | 0.023749 | 8.796% | Deposit contribution Works | 244931.14
42 | D-20-22 | CT Replacement for Kesoram at Malyalapal | CT Replacement for Kesoram at Malyalapal | SR | Lr.No. 161 Dt 29.05.2020 | --- | --- | 0.12 | --- | --- | --- | --- | 29.05.2020 | 31.03.2025 |  | 0.05 | 0 | 0.05 | 41.67% | Deposit contribution Works | 498406.45
43 | D-20-26 | 33KV Bay at 220 Fabcity for Sakura premi | 33KV Bay at 220 Fabcity for Sakura premi | SE | Lr.No. 71 Dt 08.05.2020 | --- | --- | 0.44 | --- | --- | --- | --- | 08.05.2020 | 31.03.2025 |  | 0.063 | -0.0034515 | 0.059548 | 13.53% | Deposit contribution Works | 631025.54
44 | D-20-27 | 33KV Bays for Amazon at Mahabubnagar Cir | 33KV Bays for Amazon at Mahabubnagar Cir | SE | Lr.No 185 Dt 08.07.2020 | --- | --- | 0.66 | --- | --- | --- | --- | 08.07.2020 | 31.03.2025 |  | 0.203 | -0.006903 | 0.1961 | 29.71% | Deposit contribution Works | 2029482.95
45 | D-20-36 | 220KV Shivrampally SS-4Nos 33KV bays for | 220KV Shivrampally SS-4Nos 33KV bays for | SE | Lr.No.641 Dt 08.02.2021 | --- | --- | 1.17 | --- | --- | --- | --- | 08.02.2021 | 31.03.2025 |  | 0.189 | -0.050235 | 0.13877 | 11.86% | Deposit contribution Works | 1892221.3
46 | D-20-43 | 33 KV Bay for TSNPDCL at 132KV Dasnagar | 33 KV Bay for TSNPDCL at 132KV Dasnagar | SE | Lr.No 647 Dt 08.02.2021 | --- | --- | 0.17 | --- | --- | --- | --- | 08.02.2021 | 31.03.2025 |  | 0.062 | -0.002863 | 0.059137 | 34.79% | Deposit contribution Works | 623041.33
47 | D-21-16 | 4Nos 33KV Bays in substation in OMC Wara | 4Nos 33KV Bays in substation in OMC Wara | SE | Lr.No.1478 Dt 25.02.2022 | --- | --- | 0.84 | --- | --- | --- | --- | 25.02.2022 | 31.03.2025 |  | 0.269 | -0.051632 | 0.21737 | 25.88% | Deposit contribution Works | 2691583.64 | 34622.42
48 | D-21-20 | 33KV Bay for Raghuram at 132KV Suglampal | 33KV Bay for Raghuram at 132KV Suglampal | SE | Lr.No.1375 Dt 30.10.2021 | --- | --- | 0.23 | --- | --- | --- | --- | 30.10.2021 | 31.03.2025 |  | 0.029 | 0.053939 | 0.082939 | 36.06% | Deposit contribution Works | 289616.84
49 | D-21-22 | 132KV Nandipet- Nizamabad | DCW | SR | [8 empty] | 23.07.2021 | 12.01.2022 |  | 0.013 | 0.15245 |  |  | Deposit contribution Works
50 | D-21-26 | 33KV Bay for singareni at 132KV Penuball | 33KV Bay for singareni at 132KV Penuball | SE | Lr.No.599 Dt 07.09.2021 | --- | --- | 0.13 | --- | --- | --- | --- | 07.09.2021 | 31.03.2025 |  | 0.034 | 0 | 0.034 | 26.15% | Deposit contribution Works | 336816.84
51 | D-21-46 | 33KV Bay at 132KV B.Gangaram for diverio | 33KV Bay at 132KV B.Gangaram for diverio | SE | Lr.No.482 Dt 26.07.2021 | --- | --- | 0.16 | --- | --- | --- | --- | 26.07.2021 | 31.03.2025 |  | 0.003 | 0.03058 | 0.03358 | 20.99% | Deposit contribution Works | 34515 | 308873.68
52 | D-22-07 | Release of additional CMD of 850KVA to U | Release of additional CMD of 850KVA to U | [10 empty] | 31.03.2025 |  | 0 | 0.18
53 | D-22-12 | Utilization of Various Tower Parts and C | Utilization of Various Tower Parts and C | [10 empty] | 31.03.2025 |  | 0 | 0.31
54 | D-22-15 | Aug of PTR Capacity at 220 KV HIAL SS | Aug of PTR Capacity at 220 KV HIAL SS | SE | Lr.No.275 Dt 08.06.2022 | --- | --- | 14.93 | --- | --- | --- | --- | 08.06.2022 | 31.03.2025 |  | 0.084 | 0.50329 | 0.58729 | 3.934% | Deposit contribution Works | 835056.26 | 1145365.35
55 | N-16-OMCP | O&M CAPITAL MAT. PROC. for FY: 2016-17 | [5 empty] | 6.58 | [7 empty] | 0.031 | 0 | 0.031 | 0.4711% |  | 314241.02
56 | N-16-OMCP-OPENCAPSTOCK | Migrate OMC Open Capital Inventory | [5 empty] | 32.54 | [7 empty] | 0.929 | 0 | 0.929 | 2.855% |  | 9290424.89
57 | N-17-OMCP | O&M CAPITAL MAT. PROC. for FY: 2017-18 | [5 empty] | 16.57 | [7 empty] | 0.555 | 0 | 0.555 | 3.349% |  | 5552627.09
58 | N-19-02 | Non Planned Capital works (O&M) 2019-20 | [5 empty] | 3.52 | [7 empty] | 0.05 | 0.022224 | 0.072224 | 2.052% |  | 499120.6 | 222240.4
59 | N-19-OMCP | Cap.Material Drawl in O&M for FY:2019-20 | [5 empty] | 0.77 | [7 empty] | 0.469 | -0.46943 | -0.00042949 | -0.05578% |  | 4694294.88 | -4694294.88
60 | N-20-02 | Non Planned Capital works (O&M) 2020-21 | Non Pln works in O &M | SR | - | - | - | 6.3 | TGTRNSCO | - | - | - | 01.04.2020 | 31.03.2025 | - | 1.11 | 0 | 1.11 | 17.62% |  | 11101491.49 | 2389913
61 | N-21-02 | Non Planned Capital works (O&M) 2021-22 | Non Pln works in O &M | SR | - | - | - | 10.91 | TGTRNSCO | - | - | - | 01.04.2021 | 31.03.2025 | - | 2.839 | 1.2083 | 4.0473 | 37.1% |  | 28385178.67 | 14213426.08
62 | N-22-02 | Non Planned Capital works (O&M) 2022-23 | Non Pln works in O &M | SR | - | - | - | 26.48 | TGTRNSCO | - | - | - | 01.04.2022 | 31.03.2025 | - | 6.117 | 8.2172 | 14.3342 | 54.13% |  | 61165781.44 | 82171820.66
63 | O-16-01 | Rolling stock for FY 2016-2017 | Procurement of Mteril | SR | T. O. O:4 ,Dt:11.01.2017 | - | - | 39.53 |  | REC | 3162.4 | - | 11.01.2017 | 31.03.2025 | - | 0.061 | 19.6423 | 19.7033 | 49.84% |  | 614574.71 | 78578560
64 | O-18-01 | Procure of Major SS equip under rolling | Procurement of Mteril | SR | T. O. O:70 ,Dt:3.4.2019 | - | - | 26.43 |  | REC |  | - | 3.4.2018 | 31.03.2024 | - | 0.815 | -0.081998 | 0.733 | 2.773% |  | 8151553.01
65 | R-15-01 | RMI for the year 2015 | Renovtion modernition nd Improvement | SR | T. O. O:182 ,Dt:16.9.2015 | - | - | 53.08 |  | PFC | 47.772 | - | 16.09.2015 | 31.03.2025 | - | 2.162 | 0.19165 | 2.3537 | 4.434% |  | 21618207.11 | 1665701.61
66 | R-16-02 | PSDF | PSDF | SR | T.O.O. 19, Dt::08.02.2016. | - | - | 59.97 |  |  |  | PSDF grant-90% | 08.02.2016 | 31.03.2021 |  | 0.025 | 0 | 0.025 | 0.04169% |  | 253210.33
67 | R-17-01 | RMI for FY:2017-18 & 2018-19 | Renovtion modernition nd Improvement | SR | T. O. O:146 ,Dt:7.10.2017 | - | - | 100.22 | - | REC | 90.198 | - | 7.10.2017 | 31.03.2027 |  | 2.796 | 2.0268 | 4.8228 | 4.812% |  | 27958441.14 | 23741181.8
68 | R-17-02 | 132 KV BEL'PALLY - S' KHAGAZ NAGAR TOWER | RMI | SR |  |  |  | 4.79 |  |  |  |  | 23.04.2018 | 31.03.2024 |  | 4.583 | -0.38631 | 4.1967 | 87.61% |  | 45826419.65 | -1283772.75
69 | R-20-01 | Renovation & Modernization Scheme - 2020 | Renovtion modernition nd Improvement | SR | T. O. O:843 ,Dt:16.9.2020 | - | - | 75.6 | - | REC | 68.04 | - | 16.09.2020 | 31.03.2027 | - | 12.342 | 1.5194 | 13.8614 | 18.34% |  | 123416691.2 | 35301518.31
70 | R-21-01 | RMI scheme for FY 2021-22 | Renovtion modernition nd Improvement | SR | T. O. O:1336,Dt:14.3.2022 | - | - | 59.7 | TGTRNSCO | - | - | - | 14.03.2022 | 31.03.2027 | - | 3.704 | 6.9209 | 10.6249 | 17.8% |  | 37039332.29 | 69924732.69
71 | S-22-01 | Const. of 33KV bays at 132/33KV Substati | [10 empty] | 16.09.2015 | 31.03.2025 |  | 0.841 | 1.1373 | 1.9783 | #DIV/0! |  | 8409556.23 | 11719680.57
72 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION | Procurement of Mteril | SR | - | - | - | 64.38 | TGTRNSCO |  |  |  | 01.04.2021 | 31.03.2025 |  | 8.848 | -0.092952 | 8.755 | 13.6% |  | 88478089.64 | 25289859.96
73 | Z-99-01 | Rolling Stocks Procurement N Consumption | Procurement of Mteril | SR | - | - | - | 77.3 | TGTRNSCO |  |  |  | 1.04.2022 | - |  | 2.217 | 16.9686 | 19.1856 | 24.82% |  | 22171447.11 | 100356213.28
II. New schemes taken up during 2023-24
Sub-total-II | [15 empty] | 0 | 33.901 | 33.901
1 | A-22-03 | Aug. of PTR at Kaithalapur & Bhongir | [5 empty] | 3.11 | [7 empty] | 0 | 2.796 | 2.796 | 89.9% |  |  | 27036993.52
2 | A-22-04 | Aug of 132/33KV PTRs at 11Nos. EHT SS | [5 empty] | 18.301 | [7 empty] | 0 | 12.4433 | 12.4433 | 67.99% |  |  | 123807139.28
3 | A-23-02 | Aug. of 132/33 KV PTR Capacities at 4 No | [5 empty] | 18.4 | [7 empty] | 0 | 0.10099 | 0.10099 | 0.5488% |  |  | 1009852
4 | A-23-09 | Aug of 132/33KV PTR Cap at 9Nos.EHT Subs | [5 empty] | 28.09 | [7 empty] | 0 | 10.5238 | 10.5238 | 37.46% |  |  | 105238070.05
5 | D-22-03 | Replacement of 132KV metering CT&PTs at | [5 empty] | 0.257 | [7 empty] | 0 | 0.17246 | 0.17246 | 67.11% |  |  | 501087.53
6 | D-22-17 | Replmnt CTs & PTs NFCI&II feeders @220KV | [5 empty] | 1.44 | [7 empty] | 0 | 0.86357 | 0.86357 | 59.97% |  |  | 7654315.5
7 | D-22-20 | 220 KV SS Pulyathanda - Testing & Oil Fi | [5 empty] | 0.127 | [7 empty] | 0 | 0.015947 | 0.015947 | 12.56% |  |  | 159465.2
8 | D-23-12 | 132KV Nizamabad SS - 33KV RTC Feeder Bay | [5 empty] | 0.229 | [7 empty] | 0 | 0.10976 | 0.10976 | 47.93% |  |  | 1097639.33
9 | R-22-01 | RMI 2022-23 | [5 empty] | 63.29 | [7 empty] | 0 | 6.7705 | 6.7705 | 10.7% |  |  | 31772235.63
10 | R-23-01 | RMI(2023-24) Replace of Old & Obsolete E | [5 empty] | 67.9 | [7 empty] | 0 | 0.10473 | 0.10473 | 0.1542% |  |  | 312958.98
III. Non-plan schemes taken up during 2023-24
Sub-total-III | [15 empty] | 0 | 0.32657 | 0.32657
1 | N-23-02 | Non Planned Capital works (O&M) 2022-23 | [5 empty] | 3.74 | [7 empty] | 0 | 0.32657 | 0.32657 | 8.732% |  |  | 3265683.28
Grans Total I + II + III | [15 empty] | 69.951 | 184.9707 | 254.0832
Note : Project Purpose : System Improvement (SI), System Expansion (SE), System Replacements (SR)/ RMI, Generation Evacuation (GE)
The statement to be printed on A3 size sheets please

## CapEx 24-25
Scheme-wise details of Capital Expenditure incurred in FY: 2024-25 of 4th control period
[17 empty] | H1 | (figures in Crores)
Sl No. | Project Code / Scheme ID (SAP Code) | Project Title (SAP Project title) | Scope of work (Names of all the Sub-stations and Lines included in the scheme) | Project Purpose (SI/SE/SR/GE) | Administrative Approval TOO Ref. | SRPC approval (if any) | TGERC Investment Approval Ref. | Total approved Cost (in Cr) | Source of funds |  |  |  | Project Start Date (DD-MM-YY) | Project Completion Date (DD-MM-YY) | DOC | Opening CWIP as on 31.03.2024 | proposed Expenditure from 01.04.2024 to 31.03.2025 | Cumulative expenditure upto 31.03.2024 | % Capatalisation | Remarks / Balance works , if any. |  | H1
[9 empty] | TGTransco Funds | Loan source | Loan Amount | Grants, if any | [8 empty] | CWIP | CApital Expenditure 2024-25
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
Annual Petition for 2024-25 for Transmission Business filed with TGERC
I. Ongoing Schemes as on 01.04.2024
Sub-total-I | [15 empty] | 127.2989 | 65.86 | 188.3738
1 | A-15-05 | AUGof PTR@EHT SS for extending 9Hrs |  | SE | TOO | --- | --- | 32.01 | TSTRANSCO | --- | --- | --- | 01.04.2016 | 31.03.2025 |  | 0.020474 | -0.02 | 0.00047383 | 0.00148% |  | 204738.33 | -204738 |  | A-15-05
2 | A-15-06 | AUGof PTR@EHT SS for extending 9Hrs |  | SE | TOO | --- | --- | 9.36 | TSTRANSCO | --- | --- | --- | 01.04.2016 | 31.03.2025 |  | 0 |  |  |  |  | 0 | 382039.59 |  | A-15-06
3 | A-15-22 | STRENGTHENING OF 10 NOS. OVERLOAD LINES | Stengthening of existing conductor with HTLS | SE | T. O. O. (CE/Transmission) MS.No.158 dated 23.11.2016 | --- | --- | 215.07 |  | PFC |  |  | 18.04.2016 | 14.12.2016 |  | 2.113 | -2.083 | 0.030033 | 0.01396% |  | 21130328.25 | -20826162.39 |  | A-15-22
4 | A-16-01 | 3rd 31.5MVA PTR at Adilabad SS | 3rd 31.5MVA PTR at Adilabad SS | SE |  | --- | --- | 1.02 | TSTRANSCO | --- | --- | --- | 01.04.2016 | 31.03.2025 |  | 0.017827 | -0.018 | -0.0001731 | -0.01697% |  | 118458814.71 | -178269 |  | A-16-01
4 | A-17-01 | [12 empty] | 31.03.2025 |  | 0.21 | [7 empty] | #N/A
5 | A-17-02 | Aug Sys Stren & 24 Hrs Agl METRO & RURAL | Aug Sys Stren & 24 Hrs Agl METRO & RURAL | SE |  | --- | --- | 51.29 | TSTRANSCO | --- | --- | --- | 01.04.2017 | 31.03.2025 |  | 0.63079 | -0.118 | 0.51279 | 0.9998% |  | 6307857.13 | -1175525.68 |  | A-17-02
6 | A-18-01 | Aug of PTR capacity at 220KV Ch'gutta | Aug of PTR capacity at 220KV Ch'gutta | SE |  | --- | --- | 15.3 | TSTRANSCO | --- | --- | --- | 01.04.2018 | 31.03.2025 |  | 0 | 8.9 | 8.9 | 58.17% |  | 0 | 88997960 |  | A-18-01
6 | A-18-05 | [12 empty] | 31.03.2025 |  | 1.22 | [7 empty] | #N/A
7 | A-19-01 | Aug of 4th 160 MVA at 220KV Gachibowli | Aug of 4th 160 MVA at 220KV Gachibowli | SE | T.O.O.396, Dt:03.07.2019 | --- | --- | 6.21 | TSTRANSCO | --- | --- | --- | 01.04.2019 | 31.03.2025 |  | 0.086154 | -0.016 | 0.070154 | 1.13% |  | 861537.97 | -160690 |  | A-19-01
8 | A-19-02 | Augmentation of 132 KV Chintal SS | Augmentation of 132 KV Chintal SS | SE | T.O.O.724, Dt:22.02.2020 | --- | --- | 0.69 | TSTRANSCO | --- | --- | --- | 01.04.2019 | 31.03.2025 |  | 0.058549 | 0.023 | 0.081549 | 11.82% |  | 585488.42 | 226387.73 |  | A-19-02
9 | A-19-03 | Augmentation of 80 MVA at 132 KV IDPL SS | Augmentation of 80 MVA at 132 KV IDPL SS | SE | T.O.O.731, Dt:07.03.2020 | --- | --- | 0.72 | TSTRANSCO | --- | --- | --- | 01.04.2019 | 31.03.2025 |  | 0.030477 | 0 | 0.030477 | 4.233% |  | 304766.86 | -1917.5 |  | A-19-03
9 | A-19-04 | [12 empty] | 31.03.2025 |  | 0.22 | [7 empty] | #N/A
10 | A-19-05 | Augmentation of PTRs at gesukonda & Tiru | Augmentation of PTRs at gesukonda & Tiru | SE | T.O.O.738, Dt:18.03.2020 | --- | --- | 0.76 | TSTRANSCO | --- | --- | --- | 01.04.2019 | 31.03.2025 |  | 0.17489 | 0.053 | 0.22789 | 29.99% |  | 1880882.12 | 530609.51 |  | A-19-05
11 | A-20-01 | Augmentation at 220KV Manthani SS & 132K | Augmentation at 220KV Manthani SS & 132K | SE | T.O.O.780, Dt:10.06.2020 | --- | --- | 8.97 | TSTRANSCO | --- | --- | --- | 01.04.2020 | 31.03.2025 |  | 0.40334 | 0.462 | 0.86534 | 9.647% |  | 14088975.26 | 4623475.38 |  | A-20-01
12 | A-20-02 | Aug of 3rd 220/132KV PTR at 400KV Narsap | Aug of 3rd 220/132KV PTR at 400KV Narsap | SE | T.O.O.792, Dt:26.06.2020 | --- | --- | 3.63 | TSTRANSCO | --- | --- | --- | 01.04.2020 | 31.03.2025 |  | 2.3196 | 0.224 | 2.5436 | 70.07% |  | 18664146.23 | 2240794.61 |  | A-20-02
13 | A-20-03 | Aug of PTR at Warangal & Karimnagar Circ | Aug of PTR at Warangal & Karimnagar Circ | SE | T.O.O.856, Dt:03.10.2020 | --- | --- | 8.66 | TSTRANSCO | --- | --- | --- | 01.04.2020 | 31.03.2025 |  | 0.56393 | 0.67 | 1.2339 | 14.25% |  | 7952406.25 | 6701522.43 |  | A-20-03
14 | A-20-04 | Augmentation of PTR at 132KV Donthanpall | Augmentation of PTR at 132KV Donthanpall | SE | T.O.O.870, Dt:03.11.2020 | --- | --- | 0.33 | TSTRANSCO | --- | --- | --- | 01.04.2020 | 31.03.2025 |  | 0.07516 | -0.024 | 0.05116 | 15.5% |  | 884721.52 | -242416.84 |  | A-20-04
14 | A-20-05 | [12 empty] | 31.03.2025 |  | 0.04 | [7 empty] | #N/A
15 | A-20-06 | Aug of 3rd PTR at 132KV MDPally SS | Aug of 3rd PTR at 132KV MDPally SS | SE | 03.01.2020 | --- | --- | 3.92 | TSTRANSCO | --- | --- | --- | 03.01.2020 | 31.03.2025 |  | 0.067765 | -0.044 | 0.023765 | 0.6062% |  | 1344724.65 | -435231.44 |  | A-20-06
16 | A-20-07 | Aug of 4rd PTR at 132KV Pashmailaram SS | Aug of 4rd PTR at 132KV Pashmailaram SS | SE | T.O.O.1026, Dt:30.03.2021 | --- | --- | 1.56 | TSTRANSCO | --- | --- | --- | 30.03.2021 | 31.03.2025 |  | 0.024242 | 0.057 | 0.081242 | 5.208% |  | 1593439.72 | 569940 |  | A-20-07
17 | A-21-01 | Aug of 160 MVA PTR at 400KV Suryapet SS | Aug of 160 MVA PTR at 400KV Suryapet SS | SE | T.O.O.1034, Dt:12.04.2021 | --- | --- | 8.35 | TSTRANSCO | --- | --- | --- | 01.04.2021 | 31.03.2025 |  | 0.26858 | -0.004 | 0.26458 | 3.169% |  | 1483332.22 | -37760.89 |  | A-21-01
18 | A-21-02 | Aug of 132/33 KV PTRs at Mamidipally & 4 | Aug of 132/33 KV PTRs at Mamidipally & 4 | SE | T.O.O.1053, Dt:07.05.2021 | --- | --- | 11.47 | TSTRANSCO | --- | --- | --- | 01.04.2021 | 31.03.2025 |  | 0.64038 | 4.368 | 5.0084 | 43.67% |  | 329499334 | 43679353.68 |  | A-21-02
19 | A-21-04 | Aug. of PTR capacity at 220KV Huzurabad | Aug. of PTR capacity at 220KV Huzurabad | SE | T.O.O.1167, Dt:18.08.2021 | --- | --- | 6.03 | TSTRANSCO | --- | --- | --- | 18.08.2021 | 31.03.2025 |  | 9.3091 | -0.004 | 9.3051 | 154.3% |  | 1834323.22 | -37760.47 |  | A-21-04
20 | A-21-05 | Augmentations of 220KV PTRs at 5Nos Subs | Augmentations of 220KV PTRs at 5Nos Subs | SE | T.O.O1209, Dt:04.10.2021 | --- | --- | 6.03 | TSTRANSCO | --- | --- | --- | 04.10.2021 | 31.03.2025 |  | 20.9971 | 9.132 | 30.1291 | 499.7% |  | 30618461.72 | 91315620.2 |  | A-21-05
21 | A-21-06 | Augmentations of 132KV PTRs at 24Nos Sub | Augmentations of 132KV PTRs at 24Nos Sub | SE | T.O.O1211, Dt:07.10.2021 | --- | --- | 48.75 | TSTRANSCO | --- | --- | --- | 07.10.2021 | 31.03.2025 |  | 4.989 | 3.599 | 8.588 | 17.62% |  | 22017443.68 | 35985158.08 |  | A-21-06
22 | A-22-01 | Aug of PTR cap at 132KV Medchal SS & Deration of PTR cap at Chilkalguda | Aug of PTR cap at 132KV Medchal SS & Deration of PTR cap at Chilkalguda | SE | T.O.O1411, Dt.06.06.2022 | --- | --- | 0.26 | TSTRANSCO | --- | --- | --- | 07.10.2021 | 31.03.2025 |  | 0 | 0.027 | 0.027 | 10.38% |  |  | 269925 |  | A-22-01
23 | A-22-02 | Augmentation of PTR at 132KV Balanagar S | Augmentation of PTR at 132KV Balanagar S | SE | T.O.O.1486, Dt:11.10.2022 | --- | --- | 6.27 | TSTRANSCO | --- | --- | --- | 11.10.2022 | 31.03.2025 |  | 0.046288 | 0.027 | 0.073288 | 1.169% |  | 455028.79 | 269925 |  | A-22-02
24 | A-22-03 | Aug. of PTR at Kaithalapur & Bhongir | Aug. of PTR at Kaithalapur & Bhongir | SE | T.O.O.1537, Dt:21.12..2022 | --- | --- | 0.49 | TSTRANSCO | --- | --- | --- | 21.12.2022 | 31.03.2025 |  | 0.092576 | 0.008 | 0.10058 | 20.53% |  |  | 76970.22 |  | A-22-03
25 | A-23-01 | Augmentations of PTR cap at 400KV Suryapet SS | Augmentations of PTR cap at 400KV Suryapet SS | SE | T.O.O.1721, Dt:11.07.2023 | --- | --- | 18.41 | HUDCO | --- | --- | --- | 11.07.2023 | 31.03.2025 |  | 0 | 9.001 | 9.001 | 48.89% |  |  | 90008204.43 |  | A-23-01
26 | A-23-02 | Aug. of 132/33KV PTR Cap at 4 Nos. EHT SS | Aug. of 132/33KV PTR Cap at 4 Nos. EHT SS | SE | T.O.O.1802 Dt:27.09..2023 | --- | --- | 18.4 | TSTRANSCO | --- | --- | --- | 27.09.2023 | 31.03.2025 |  | 0 | 0.003 | 0.003 | 0.0163% |  |  | 26305.74 |  | A-23-02
27 | A-23-09 | Aug. of 132/33KV PTR Cap at 9 Nos. EHT SS | Aug. of 132/33KV PTR Cap at 9 Nos. EHT SS | SE | T.O.O.1879, Dt:10.01.2024 | --- | --- | 25.09 | TSTRANSCO | --- | --- | --- | 10.01.2024 | 31.03.2026 |  | 5.1076 | 9.501 | 14.6086 | 58.22% |  |  | 95009619.55 |  | A-23-09
28 | D-16-06 | Erection 33KV Bays TSNPDCL | Erection 33KV Bays TSNPDCL | SE | T.O.O 46, Dt:31.03.2016 | --- | --- | 16.31 | --- | --- | --- | --- | 31.03.2016 | 31.03.2024 |  | 0.017311 | 0 | 0.017311 | 0.1061% | Deposit contribution Works - All works Completed | 173110 |  |  | D-16-06
29 | D-18-04 | Erection of ABT Metering arrangement 220 | Erection of ABT Metering arrangement 220 | SR |  | --- | --- | 0.6 | --- | --- | --- | --- |  |  |  | 0.053714 | 0.5 | 0.55371 | 92.29% |  | 537136 |  | 0.6 | #N/A
30 | D-18-11 | Replacement of old CTs & PTs at 132KV OC | Replacement of old CTs & PTs at 132KV OC | SR | Lr.No 4228 Dt 28.09.2018 | --- | --- | 0.57 | --- | --- | --- | --- | 28.09.2018 | 31.03.2025 |  | 0.065452 | 0.4 | 0.46545 | 81.66% | Deposit contribution Works | 654517.68 |  |  | #N/A
31 | D-18-20 | Providing of ABT Meters for all Traction | Providing of ABT Meters for all Traction | SR | Lr.No 138 Dt 21.02.2019 | --- | --- | 9.65 | --- | --- | --- | --- | 21.02.2019 | 31.03.2025 |  | 2.0105 | 1 | 3.0105 | 31.2% | Deposit contribution Works | 20105374.71 |  |  | #N/A
32 | D-19-07 | ABT Metering at 132 KV Manuguru & Kothag | ABT Metering at 132 KV Manuguru & Kothag | SR | Lr.No.333 Dt 18.06.2019 | --- | --- | 1.06 | --- | --- | --- | --- | 18.06.2019 | 31.03.2025 |  | 0.041295 | 0.8 | 0.8413 | 79.37% | Deposit contribution Works | 412950.27 |  |  | #N/A
33 | D-19-08 | ABT Metering at 132KV OCM & Mandamarry S | ABT Metering at 132KV OCM & Mandamarry S | SR | Lr.No.677 Dt 05.10.2019 | --- | --- | 9.29 | --- | --- | --- | --- | 05.10.2019 | 31.03.2025 |  | 0.22773 | 0.4 | 0.62773 | 6.757% | Deposit contribution Works | 2277291.33 |  |  | #N/A
34 | D-19-14 | 33 KV Bay extension at 220KV SS Manguru | 33 KV Bay extension at 220KV SS Manguru | SE | Lr.No.14 Dt 04.03.2020 | --- | --- | 0.2 | --- | --- | --- | --- | 04.03.2020 | 31.03.2025 |  | 0.024242 | 0.1 | 0.12424 | 62.12% | Deposit contribution Works | 242416.84 |  |  | #N/A
35 | D-20-16 | Erection of 4Nos 33KV Bays for M/s Amazo | Erection of 4Nos 33KV Bays for M/s Amazo | SE | Lr.No.33 Dt 17.04.2020 | --- | --- | 1.59 | --- | --- | --- | --- | 17.04.2020 | 31.03.2025 |  | 0.1416 | 0.8 | 0.9416 | 59.22% | Deposit contribution Works | 1415963.23 |  |  | #N/A
35 | D-20-17 | [12 empty] | 31.03.2025 |  | 0.13 | [7 empty] | #N/A
36 | D-20-20 | 33KV Bay at 220KV FABCITY SS for chirpa | 33KV Bay at 220KV FABCITY SS for chirpa | SE | Lr.No.70 Dt 08.05.2020 | --- | --- | 0.43 | --- | --- | --- | --- | 08.05.2020 | 31.03.2025 |  | 0.059651 | 0.3 | 0.35965 | 83.64% | Deposit contribution Works | 596510.54 |  |  | #N/A
37 | D-20-21 | 33KV bay for SCCL,Bittupally at 132KV Ma | 33KV bay for SCCL,Bittupally at 132KV Ma | SE | Lr. No 1585 Dt 08.07.2020 | --- | --- | 0.27 | --- | --- | --- | --- | 08.07.2020 | 31.03.2025 |  | 0.024242 | 0.2 | 0.22424 | 83.05% | Deposit contribution Works | 242416.84 |  |  | #N/A
38 | D-20-22 | CT Replacement for Kesoram at Malyalapal | CT Replacement for Kesoram at Malyalapal | SR | Lr.No. 161 Dt 29.05.2020 | --- | --- | 0.12 | --- | --- | --- | --- | 29.05.2020 | 31.03.2025 |  | 0.049841 | 0.06 | 0.10984 | 91.53% | Deposit contribution Works | 498406.45 |  |  | #N/A
39 | D-20-26 | 33KV Bay at 220 Fabcity for Sakura premi | 33KV Bay at 220 Fabcity for Sakura premi | SE | Lr.No. 71 Dt 08.05.2020 | --- | --- | 0.44 | --- | --- | --- | --- | 08.05.2020 | 31.03.2025 |  | 0.059651 | 0.3 | 0.35965 | 81.74% | Deposit contribution Works | 596510.54 |  |  | #N/A
40 | D-20-27 | 33KV Bays for Amazon at Mahabubnagar Cir | 33KV Bays for Amazon at Mahabubnagar Cir | SE | Lr.No 185 Dt 08.07.2020 | --- | --- | 0.66 | --- | --- | --- | --- | 08.07.2020 | 31.03.2025 |  | 0.19605 | 0.2 | 0.39605 | 60.01% | Deposit contribution Works | 1960452.95 |  |  | #N/A
41 | D-20-36 | 220KV Shivrampally SS-4Nos 33KV bays for | 220KV Shivrampally SS-4Nos 33KV bays for | SE | Lr.No.641 Dt 08.02.2021 | --- | --- | 1.17 | --- | --- | --- | --- | 08.02.2021 | 31.03.2025 |  | 0.13899 | 0.8 | 0.93899 | 80.26% | Deposit contribution Works | 1389873.38 |  |  | #N/A
42 | D-20-43 | 33 KV Bay for TSNPDCL at 132KV Dasnagar | 33 KV Bay for TSNPDCL at 132KV Dasnagar | SE | Lr.No 647 Dt 08.02.2021 | --- | --- | 0.17 | --- | --- | --- | --- | 08.02.2021 | 31.03.2025 |  | 0.059441 | 0.1 | 0.15944 | 93.79% | Deposit contribution Works | 594410.84 |  |  | D-20-43
43 | D-21-16 | 4Nos 33KV Bays in substation in OMC Wara | 4Nos 33KV Bays in substation in OMC Wara | SE | Lr.No.1478 Dt 25.02.2022 | --- | --- | 0.84 | --- | --- | --- | --- | 25.02.2022 | 31.03.2025 |  | 0.21406 | 0.5 | 0.71406 | 85.01% | Deposit contribution Works | 2140640.36 |  |  | D-21-16
44 | D-21-20 | 33KV Bay for Raghuram at 132KV Suglampal | 33KV Bay for Raghuram at 132KV Suglampal | SE | Lr.No.1375 Dt 30.10.2021 | --- | --- | 0.23 | --- | --- | --- | --- | 30.10.2021 | 31.03.2025 |  | 0.082901 | 0.1 | 0.1829 | 79.52% | Deposit contribution Works | 829009 |  |  | #N/A
45 | D-21-26 | 33KV Bay for singareni at 132KV Penuball | 33KV Bay for singareni at 132KV Penuball | SE | Lr.No.599 Dt 07.09.2021 | --- | --- | 0.13 | --- | --- | --- | --- | 07.09.2021 | 31.03.2025 |  | 0.033682 | 0.08 | 0.11368 | 87.45% | Deposit contribution Works | 336816.84 |  |  | #N/A
46 | D-21-46 | 33KV Bay at 132KV B.Gangaram for diverio | 33KV Bay at 132KV B.Gangaram for diverio | SE | Lr.No.482 Dt 26.07.2021 | --- | --- | 0.16 | --- | --- | --- | --- | 26.07.2021 | 31.03.2025 |  | 0.0031441 | 0.1 | 0.10314 | 64.47% | Deposit contribution Works | 31440.86 |  |  | #N/A
47 | D-22-03 | Replacement of 132KV metering CT&PTs at | Replacement of 132KV metering CT&PTs at | SR | --- | --- | --- | 0.25 | --- | --- | --- | --- | 01.04.2022 | 31.03.2025 |  | 0.12235 | 0.1 | 0.22235 | 88.94% | Deposit contribution Works | 1223511.32 |  |  | #N/A
47 | D-22-07 | [12 empty] | 31.03.2025 |  | 0.18 | [7 empty] | #N/A
47 | D-22-12 | [12 empty] | 31.03.2025 |  | 0.31 | [7 empty] | #N/A
48 | D-22-15 | Aug of PTR Capacity at 220 KV HIAL SS | Aug of PTR Capacity at 220 KV HIAL SS | SE | Lr.No.275 Dt 08.06.2022 | --- | --- | 14.93 | --- | --- | --- | --- | 08.06.2022 | 31.03.2025 |  | 0.46944 | 7 | 7.4694 | 50.03% | Deposit contribution Works | 4694364.26 |  |  | D-22-15
49 | D-22-17 | Replmnt CTs & PTs NFCI&II feeders @220KV | Replmnt CTs & PTs NFCI&II feeders @220KV | SR | --- | --- | --- | 1.44 | --- | --- | --- | --- | 01.04.2022 | 31.03.2025 |  | 0.86357 | 0.4 | 1.2636 | 87.75% |  | 8635709.7 |  |  | D-22-17
50 | D-23-05 | 132KV Karimnagar Waterworks - 33KV RTC F | 132KV Karimnagar Waterworks - 33KV RTC F | SE/ | --- | --- | --- | 0.33 |  |  |  |  | 01.04.2022 | 31.03.2025 |  | 0 | 0.3 | 0.3 | 90.91% |  |  |  |  | D-23-05
51 | D-23-12 | 132KV Nizamabad SS - 33KV RTC Feeder Bay | 132KV Nizamabad SS - 33KV RTC Feeder Bay | SE | --- | --- | --- | 0.22 | --- | --- | --- | --- | 01.04.2023 | 31.03.2025 |  | 0.10976 | 0.1 | 0.20976 | 95.35% |  | 1097639.33 |  |  | #N/A
52 | D-23-26 | 33 KV Bays for customers in EHT Substations | 33 KV Bays for customers in EHT Substations | SE | --- | --- | --- | 1.64 | --- | --- | --- | --- | 01.04.2023 | 31.03.2026 |  | 0 | 1 | 1 | 60.98% | Deposit contribution Works |  |  |  | D-23-26
53 | D-24-01 | 33 KV Bays for customers in EHT Substations | 33 KV Bays for customers in EHT Substations | SE | --- | --- | --- | 2.82 | --- | --- | --- | --- | 01.04.2023 | 31.03.2026 |  | 0 | 2 | 2 | 70.92% | Deposit contribution Works |  |  |  | D-24-01
54 | N-16-OMCP | O&M CAPITAL MAT. PROC. for FY: 2016-17 | [5 empty] | 6.58 | [7 empty] | 0.031424 | 0 | 0.031424 | 0.4776% |  | 314241.02 |  |  | #N/A
55 | N-16-OMCP-OPENCAPSTOCK | Migrate OMC Open Capital Inventory | [5 empty] | 32.54 | [7 empty] | 0.92904 | 0 | 0.92904 | 2.855% |  | 9290424.89 |  |  | #N/A
56 | N-17-OMCP | O&M CAPITAL MAT. PROC. for FY: 2017-18 | [5 empty] | 16.57 | [7 empty] | 0.55526 | 0 | 0.55526 | 3.351% |  | 5552627.09 |  |  | #N/A
57 | N-19-02 | Non Planned Capital works (O&M) 2019-20 | [5 empty] | 3.52 | [7 empty] | 0 |  | 0 | 0% |  | 499120.6 | 222240.4 |  | #N/A
58 | N-19-OMCP | Cap.Material Drawl in O&M for FY:2019-20 | [5 empty] | 0.77 | [7 empty] | 0 |  | 0 | 0% |  | 4694294.88 | -4694294.88 |  | #N/A
59 | N-20-02 | Non Planned Capital works (O&M) 2020-21 | Non Pln works in O &M | SR | - | - | - | 6.3 | TGTRNSCO | - | - | - | 01.04.2020 | 31.03.2025 | - | 0.28342 |  | 0.28342 | 4.499% |  | 11101491.49 | 2389913 |  | #N/A
60 | N-21-02 | Non Planned Capital works (O&M) 2021-22 | Non Pln works in O &M | SR | - | - | - | 10.91 | TGTRNSCO | - | - | - | 01.04.2021 | 31.03.2025 | - | 2.5199 |  | 2.5199 | 23.1% |  | 28385178.67 | 14213426.08 |  | #N/A
61 | N-22-02 | Non Planned Capital works (O&M) 2022-23 | Non Pln works in O &M | SR | - | - | - | 26.48 | TGTRNSCO | - | - | - | 01.04.2022 | 31.03.2025 | - | 13.0002 |  | 13.0002 | 49.09% |  | 61165781.44 | 82171820.66 |  | #N/A
62 | N-23-02 | Non Planned Capital works (O&M) 2022-23 | [5 empty] | 3.74 | [7 empty] | 0.055491 |  | 0.055491 | 1.484% |  |  |  |  | #N/A
63 | O-16-01 | Rolling stock for FY 2016-2017 | Procurement of Mteril | SR | T. O. O:4 ,Dt:11.01.2017 | - | - | 39.53 |  | REC | 3162.4 | - | 11.01.2017 | 31.03.2025 | - | 11.8459 | 4.59 | 16.4359 | 41.58% |  | 614574.71 | 78578560 |  | O-16-01
64 | O-18-01 | Procure of Major SS equip under rolling | Procurement of Mteril | SR | T. O. O:70 ,Dt:3.4.2019 | - | - | 26.43 |  | REC |  | - | 3.4.2018 | 31.03.2025 | - | 0.73316 | -0.025 | 0.70816 | 2.679% |  | 8151553.01 |  |  | O-18-01
65 | R-15-01 | RMI for the year 2015 | Renovtion modernition nd Improvement | SR | T. O. O:182 ,Dt:16.9.2015 | - | - | 53.08 |  | PFC | 47.772 | - | 16.09.2015 | 31.03.2025 | - | 2.0437 | 0.026 | 2.0697 | 3.899% |  | 21618207.11 | 1665701.61 |  | R-15-01
66 | R-16-02 | PSDF | PSDF | SR | T.O.O. 19, Dt::08.02.2016. | - | - | 59.97 |  |  |  | PSDF grant-90% | 08.02.2016 | 31.03.2021 |  | 0.025321 | 0 | 0.025321 | 0.04222% |  | 253210.33 |  |  | #N/A
67 | R-17-01 | RMI for FY:2017-18 & 2018-19 | Renovtion modernition nd Improvement | SR | T. O. O:146 ,Dt:7.10.2017 | - | - | 100.22 | - | REC | 90.198 | - | 7.10.2017 | 31.03.2027 |  | 2.8275 |  | 2.8275 | 2.821% |  | 27958441.14 | 23741181.8 |  | R-17-01
68 | R-17-02 | 132 KV BEL'PALLY - S' KHAGAZ NAGAR TOWER | RMI | SR |  |  |  | 4.79 |  |  |  |  | 23.04.2018 | 31.03.2024 |  | 0.034333 | -0.128 | -0.093667 | -1.955% |  | 45826419.65 | -1283772.75 |  | #N/A
69 | R-20-01 | Renovation & Modernization Scheme - 2020 | Renovtion modernition nd Improvement | SR | T. O. O:843 ,Dt:16.9.2020 | - | - | 75.6 | - | REC | 68.04 | - | 16.09.2020 | 31.03.2027 | - | 8.3332 | 0 | 8.3332 | 11.02% |  | 123416691.2 | 35301518.31 |  | R-20-01
70 | R-21-01 | RMI scheme for FY 2021-22 | Renovtion modernition nd Improvement | SR | T. O. O:1336,Dt:14.3.2022 | - | - | 59.7 | TGTRNSCO | - | - | - | 14.03.2022 | 31.03.2027 | - | 7.5167 |  | 7.5167 | 12.59% |  | 37039332.29 | 69924732.69 |  | R-21-01
71 | S-22-01 | Const. of 33KV bays at 132/33KV Substati | Const. of 33KV bays at 132/33KV Substati | SE | [8 empty] | 16.09.2015 | 31.03.2025 |  | 0.14265 | 0.143 | 0.28565 | #DIV/0! |  | 1426500.34 | 1426500.34 |  | S-22-01
72 | S-23-01 | Const. of 33KV bays at 132/33KV Substati | Const. of 33KV bays at 132/33KV Substati | SE | [8 empty] | 16.09.2015 | 31.03.2025 |  | 0 | 0 | 0 | #DIV/0! |  | 0 |  |  | S-23-01
73 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION | Procurement of Mteril | SR | - | - | - | 64.38 | TGTRNSCO |  |  |  | 01.04.2021 | 31.03.2025 |  | 4.7126 | -0.11 | 4.6026 | 7.149% |  | 88478089.64 | 25289859.96 |  | Z-21-01
74 | Z-99-01 | Rolling Stocks Procurement N Consumption | Procurement of Mteril | SR | - | - | - | 77.3 | TGTRNSCO |  |  |  | 1.04.2022 | - |  | 10.6105 |  | 10.6105 | 13.73% |  | 22171447.11 | 100356213.28 |  | Z-99-01
75 | R-22-01 | RMI 2022-23 | Renovtion modernition nd Improvement |  |  |  |  | 63.29 | [7 empty] | 5.6096 |  | 3.177 | 5.02% |  |  |  |  | R-22-01
76 | R-23-01 | RMI(2023-24) Replace of Old & Obsolete E | [5 empty] | 67.9 | [7 empty] | 0.073431 |  | 0.031 | 0.04566% |  |  |  |  | R-23-01
II. New schemes taken up during 2024-25
Sub-total-II | [15 empty] | 0.16391 | 25.726 | 25.8899
1 | A-22-03 | Aug. of PTR at Kaithalapur & Bhongir | [5 empty] | 3.11 | [7 empty] | 0 | 2.704 | 2.704 | 86.95% |  |  | 27036993.52
2 | A-22-04 | Aug of 132/33KV PTRs at 11Nos. EHT SS | [5 empty] | 18.301 | [7 empty] | 0.16391 | 12.381 | 12.5449 | 68.55% |  |  | 123807139.28
3 | A-23-02 | Aug. of 132/33 KV PTR Capacities at 4 No | [5 empty] | 18.4 | [7 empty] | 0 | 0.101 | 0.101 | 0.5489% |  |  | 1009852
4 | A-23-09 | Aug of 132/33KV PTR Cap at 9Nos.EHT Subs | [5 empty] | 28.09 | [7 empty] | 0 | 10.524 | 10.524 | 37.47% |  |  | 105238070.05
5 | D-22-20 | 220 KV SS Pulyathanda - Testing & Oil Fi | [5 empty] | 0.127 | [7 empty] | 0 | 0.016 | 0.016 | 12.6% |  |  | 159465.2
6 |  | RMI 24-25 |  |  | T.O.O to issued | [7 empty] | Works to be taken up after issuing T.O.O | [6 empty] | T.O.O to be issued to Rs.47.00Cr.
III. Non-plan schemes taken up during 2024-25
Sub-total-III | [15 empty] | 0 | 0 | 0
1 | N-24-02 | Non Planned Capital works (O&M) 2024-25 | [5 empty] | 7.72 | [7 empty] | 0 |  | 0 | 0% |  |  | 3265683.28
Grans Total I + II + III | [15 empty] | 127.4628 | 91.586 | 214.2638
Note : Project Purpose : System Improvement (SI), System Expansion (SE), System Replacements (SR)/ RMI, Generation Evacuation (GE)
The statement to be printed on A3 size sheets please

## Captlztn 23-24
TRANSMISSION CORPORATION OF TELANGANA LIMITED
Annual Petition for 2024-25 for Transmission Business filed with TGERC
Scheme wise details of Actual Capitalisation for FY 2023-24
[9 empty] | Work Period | [5 empty] | Source of Funds | [7 empty] | Additions to Network
Sl No. | Voltage Level | Project Code (SAP Code) / Scheme IDs | Project Title (SAP Project title) | Scope of work (Names of all the Sub-stations and Lines included in the Scheme) | Project Purpose (SI/SE/SR/GE) | Administrative approval no. with date | SRPC approval no with date (if any) | Investment Approval No. with Date | Start Date |  | Completion Date (Charging date) |  | Date of Capitalization | Approved Cost as per Investment Approval | Transco Funds | Loan Source | Loan Amount | Grants, if any | Capitalisation Upto Previous Year (n-1) (as per Audited Financial Statements) | Capital Expenditure during the current year (2023-24) | Capitalisation claimed for the Current year (2023-24) | Whether Part Capitalization or Full Capitalisation | Sub-stations (Nos) | Lines (CKM) | PTR (MVA) | Bays (Nos) | Physical Completion Certificate Nos. | Financial Completion Certificate Nos. | Remarks / Reasons for Cost & Time overruns (if any)
[9 empty] | Schedule | Actual | Schedule | Actual
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
I. Ongoing Schemes as on 01.04.2023
Sub-total-I | [19 empty] | 154.8051 | 128.1307 |  | 0 | 0 | 352 | 6
1 | A-16-04 | Aug-adtnl 80MVAPTR-132kVSS Madapur-Metro | Aug-adtnl 80MVAPTR-132kVSS Madapur-Metro | 132kVSS Madapur | SE |  | - | - | 01.04.2016 | 01.04.2016 |  | 31.03.2024 |  | 4.76 | TSTRANSCO |  |  |  |  | -0.14515 | -0.14515 |  | --- | --- | --- | --- | - | 202000328
2 | A-17-01 | 24 Hrs. Agl. supply works in WGL ZONE | 24 Hrs. Agl. supply works in WGL ZONE | WGL Zone | SE |  | - | - | 01.04.2017 | 01.04.2017 |  | 18.12.2017 21.04.2018 |  | 7.22 | TSTRANSCO |  |  |  |  | 0.0040788 | 0.0040788 |  | --- | --- | --- | --- | 2019000493, 2019000493 | 202001070 202001431
3 | A-19-02 | Augmentation of 132 KV Chintal SS | Augmentation of 132 KV Chintal SS | 132KV Chintal SS | SE |  | - | - | 01.04.2023 | 01.04.2023 |  | 08.09.2023 06.10.2023 |  | 0.69 | TSTRANSCO |  |  |  |  | 0.11905 | 0.11905 |  | --- | --- | --- | --- | 2023001279, 2024000349 | 2024000697 2024000740
4 | A-20-01 | Augmentation at 220KV Manthani SS & 132K | Augmentation at 220KV Manthani SS & 132K | 220KV Manthani SS & 132Karimnagar | SE |  | - | - | 01.06.2020 | 01.06.2020 |  | 28.12.2023 12.05.2023 |  | 8.97 | TSTRANSCO |  |  |  |  | 4.1317 | 5.2172 |  | --- | --- | --- | --- | 2023001230. 2023001239 | 2024000289 2024000653 2024000254
5 | A-20-03 | Aug of PTR at Warangal & Karimnagar Circ | Aug of PTR at Warangal & Karimnagar Circ |  | SE |  | - | - | 03.01.2020 | 03.01.2020 |  | 25-01-2024 19-02-2024 29-11-2023 29-11-2023 25-01-2024 |  | 8.26 | TSTRANSCO |  |  |  |  | 1.6869 | 1.5111 |  | --- | --- | --- | --- | 2023001225, 2024000392, 2023001223 2024000099 2024000382 | 2024000283 2024000285 2024000286 2024000288 2024000270
6 | A-20-06 | Aug of 3rd PTR at 132KV MDPally SS | Aug of 3rd PTR at 132KV MDPally SS | 132KV MDPally SS | SE |  | - | - | 03.01.2020 | 03.01.2020 |  | 2022-08-09 |  | 3.92 | TSTRANSCO |  |  |  |  | 0.0027503 | 0.0027503 |  | --- | --- | --- | --- | 2022000495 | 2023000064
7 | A-20-07 | Aug of 4rd PTR at 132KV Pashmailaram SS | Aug of 4rd PTR at 132KV Pashmailaram SS | 132KV Pashmailaram SS | SE |  | - | - | 30.03.2021 | 30.03.2021 |  | 26-12-2021 30-12-2021 20-06-2023 |  | 1.56 | TSTRANSCO |  |  |  |  | 0.1524 | 0.1524 |  | --- | --- | --- | --- | 2022000273 2024000157 2023001355 | 202200195 2024000190 2024000246
8 | A-21-01 | Aug of 160 MVA PTR at 400KV Suryapet SS | Aug of 160 MVA PTR at 400KV Suryapet SS | 400KV Suryapet SS | SE |  | - | - | 12.04.2021 | 12.04.2021 |  | 13.01.2023 |  | 8.35 | TSTRANSCO |  |  |  |  | 0.10013 | 0.083158 |  | --- | --- | --- | --- | 2022000501 | 2023000924
9 | A-21-02 | Aug of 132/33 KV PTRs at Mamidipally & 4 | Aug of 132/33 KV PTRs at Mamidipally & 4 | Mamidipally & 4 | SE |  | - | - | 07.05.2021 | 07.05.2021 |  | 18-05-2024 22-07-2023 22-07-2023 27-04-2022 20-06-2023 |  | 11.47 | TSTRANSCO |  |  |  |  | 4.6376 | 4.0628 |  | --- | --- | --- | --- | 2024000432 2023001212 2023001213 2023001204 2024000270 | 2024000298 2024000299 2024000573 2024000324
10 | A-21-04 | Aug. of PTR capacity at 220KV Huzurabad | Aug. of PTR capacity at 220KV Huzurabad | 220KV Huzurabad | SE |  | - | - | 18.08.2021 | 18.08.2021 |  | 01-11-2021 03-08-2023 |  | 6.03 | TSTRANSCO |  |  |  |  | 9.09 | 0.19306 |  | --- | --- | --- | --- | 2023000537 2024000393 | 2024000290 202200364
11 | A-21-05 | Augmentations of 220KV PTRs at 5Nos Subs | Augmentations of 220KV PTRs at 5Nos Subs |  | SE |  | - | - | 04.10.2021 | 04.10.2021 |  | 02-01-2024 07-09-2022 22-08-2022 |  | 6.03 | TSTRANSCO |  |  |  |  | 18.9386 | 10.4995 |  | --- | --- | --- | --- | 2023001227 2023000997 2023000570 | 2023000473 2024000175 2023000315 2024000255
12 | A-21-06 | Augmentations of 132KV PTRs at 24Nos Sub | Augmentations of 132KV PTRs at 24Nos Sub |  | SE |  | - | - | 07.10.2021 | 07.10.2021 |  | 13-03-2023 28-09-2022 24-12-2022 26-09-2023 16-12-2023 22-12-2022 11-05-2023 16-08-2023 20-01-2024 11-11-2022 28-09-2022 23-10-2022 13-03-2023 17-06-2023 20-06-2023 24-05-2023 16-12-2023 09-06-2023 09-06-2023 05-01-2024 20-01-2023 10-11-2023 24-05-2023 26-08-2023 26-09-2023 24-02-2024 19-09-2023 05-01-2024 |  | 48.75 | TSTRANSCO |  |  |  |  | 36.0309 | 36.667 |  | --- | --- | --- | --- | 2023000582 2023000609 2023000583 2023001488 2023001487 2023000333 2023001324 2023001419 2023001491 2023000664 2023000740 2023000228 2023001407 2023001408 2023001338 2024000144 2023001486 2023001303 2023001248 2024000067 2023001507 2024000133 2024000133 2024000150 2024000124 2024000125 2024000229 2024000087 2024000180 | 2024000516 2024000527 2023000173 2023001149 2024000486 2024000485 2024000243 2024000375 2024000198 2024000214 2024000376 2024000055 2024000475 2024000462 2024000377 2024000152 2024000153 2024000669 2024000049 2024000078 2024000091 2023000604 2024000323 2024000209 2023001151 2023001150 2023001159
13 | A-22-01 | Augmentation of PTR at 132 KV Medchal SS | Augmentation of PTR at 132 KV Medchal SS | 132 KV Medchal SS | SE |  | - | - | 01.04.2021 | 01.04.2021 |  | 08.01.2023 08.01.2023 |  | 0.26 | TSTRANSCO |  |  |  |  | 0 | -1.27e-07 |  |  |  | 30 |  | 3300T052 3300T052 | 2023000735 2023000734
14 | A-22-02 | Augmentation of PTR at 132KV Balanagar S | Augmentation of PTR at 132KV Balanagar S | 132KV Balanagar S | SE |  | - | - | 11.10.2022 | 11.10.2022 |  | 06-12-2022 09-08-2023 |  | 6.27 | TSTRANSCO |  |  |  |  | 5.1032 | 5.1487 |  |  |  | 30 |  | 2023001203 2024000310 | 2024000584 2024000724
15 | A-22-03 | Aug. of PTR at Kaithalapur & Bhongir | Aug. of PTR at Kaithalapur & Bhongir | Kaithalapur & Bhongir | SE |  | - | - | 11.10.2022 | 11.10.2022 |  | 01-03-2023 19-06-2023 |  | 3.11 | TSTRANSCO |  |  |  |  | 2.7037 | 2.7037 |  |  |  | 48.5 |  | 2023000241 2023001411 | 2023001074 2024000482
16 | A-22-04 | Aug of 132/33KV PTRs at 11Nos. EHT SS | Aug of 132/33KV PTRs at 11Nos. EHT SS |  | SE |  | - | - | 01.04.2024 | 01.04.2024 |  | 30-07-2024 26-05-2023 03-07-2023 12-09-2023 23-06-2023 02-09-2023 12-09-2023 05-07-2023 02-09-2023 04-08-2023 01-06-2023 12-09-2023 08-08-2023 12-09-2023 02-09-2023 06-10-2023 04-08-2023 |  | 13.67 | TSTRANSCO |  |  |  |  | 12.3807 | 12.2794 |  |  |  | 123.5 |  | 2024000430 2023001502 2024000430 2023001502 2023001250 2023001436 2024000243 2023001463 2023001435 2023001323 2023001464 2023001299 2023001410 2023001433 2024000131 2024000268 2023001466 2024000132 2024000121 | 2024000477 2024000071 2024000595 2024000042 2024000609 2024000610 2024000120 2024000614 2024000122 2024000483 2024000619 2024000047 2024000620 2024000621 2024000046 2024000142
17 | A-23-02 | Aug. of 132/33 KV PTR Capacities at 4 No |  |  | SE |  | - | - | 01.04.2024 | 01.04.2024 |  | 13-01-2024 |  | 18.4 | TSTRANSCO |  |  |  |  | 0.10099 | 0.10099 | [5 empty] | 2024000005 | 2024000253
18 | A-23-09 | Aug of 132/33KV PTR Cap at 9Nos.EHT Subs | Aug of 132/33KV PTR Cap at 9Nos.EHT Subs |  | SE |  | - | - | 01.04.2024 | 01.04.2024 |  | 06-11-2023 10.07.2024 |  | 25.09 | TSTRANSCO |  |  |  |  | 10.5236 | 5.4162 |  |  |  | 60 |  | 2024000427 2024000443
19 | D-18-03 | Implementation of DAS for RTSS | Implementation of DAS for RTSS | --- | SR | Lr No 175 Dt 25.01.2018 | --- | --- | [11 empty] | 0.059383 | 0.059383 |  | --- | --- | --- | --- | 2019000335
20 | D-18-20 | Providing of ABT Meters for all Traction | Providing of ABT Meters for all Traction | 15 Nos. Railway Substations | SR |  | --- | --- | [11 empty] | 0.22134 | 0.1792 |  | --- | --- | --- | --- | 2023000024 2023000019
21 | D-19-07 | ABT Metering at 132 KV Manuguru & Kothag | ABT Metering at 132 KV Manuguru & Kothag | Manuguru & Kothagudem | SR | LrNo 333 Dt 18.06.2019 | --- | --- | [11 empty] | 0.11278 | 0.11278 |  | --- | --- | --- | --- | 2023001062 2023001017
22 | D-19-08 | ABT Metering at 132KV OCM & Mandamarry S | ABT Metering at 132KV OCM & Mandamarry S | Open Cast Mining & Mandamarry | SR | LrNo 677 Dt 05.10.2019 | --- | --- | [11 empty] | 0.21628 | 0.21628 |  | --- | --- | --- | --- | 2022000430 2023000531
23 | D-19-14 | 33 KV Bay extension at 220KV SS Manguru | 33 KV Bay extension at 220KV SS Manguru | Manuguru | SE | DCR No 14 Dt 04.03.2020 | --- | --- | [11 empty] | 0.0026703 | 0.0026704 |  | --- | --- | --- | 1 | 2023001060
24 | D-21-16 | 4Nos 33KV Bays in substation in OMC Wara | 4Nos 33KV Bays in substation in OMC Wara | Pulakurthy, Narmetta, Dharmasagar, Narmetta | SE | Lr No 1478 Dt 25.02.2021 | --- | --- | [11 empty] | 0.0034622 | 0.0034622 |  | --- | --- | --- | 4 | 2022000364 2023000703 2023000435 2023000330
25 | D-21-46 | 33KV Bay at 132KV B.Gangaram for diverio | 33KV Bay at 132KV B.Gangaram for diverio | B. Gangaram | SE | Lr.No. 482 Dt 26.07.2021 | --- | --- | [11 empty] | 0.030887 | 0.030887 |  | --- | --- | --- | 1 | 2023001008
26 | D-22-03 | Replacement of 132KV metering CT&PTs at | Replacement of 132KV metering CT&PTs at | Yeddumailaram | SR | Lr.No . 961 Dt 20.05.2022 | --- | --- | [11 empty] | 0.050109 | 0.050109 |  | --- | --- | --- | --- | 2023000723
27 | D-22-10 | Laying of 2Nos. (S+6) type towers to cro | Laying of 2Nos. (S+6) type towers to cro | TGNPDCL |  |  |  |  | 21.07.2022 | 21.07.2022 |  | 05.09.2022 | [7 empty] | 0.45245 | 0.45245
28 | D-22-15 | Aug of PTR Capacity at 220 KV HIAL SS | Aug of PTR Capacity at 220 KV HIAL SS | Hyderabad International Airport Limited (HIAL) SS | SE | Lr.No . 275 Dt 08.06.2022 | --- | --- | [11 empty] | 0.11454 | 0.11736 |  | --- | --- | 60 | --- | 2024000253 2024000257
29 | D-22-20 | 220 KV SS Pulyathanda - Testing & Oil Fi | 220 KV SS Pulyathanda - Testing & Oil Fi | Pulyathanda | - | LR Dt 2 Dt 02.01.2022 | --- | --- | [11 empty] | 0.015946 | 0.015947 |  | --- | --- | --- | --- | 2023001409
30 | N-19-02 | Non Planned Capital works (O&M) 2019-20 | Non Pln works in O & M | Through out TGTRNSCO | SR |  | --- | --- | [11 empty] | 0.022224 | 0.072136 |  | - | - | - | - | - | -
31 | N-20-02 | Non Planned Capital works (O&M) 2020-21 | Non Pln works in O &M | Through out TGTRNSCO | SR | --- | --- | --- | [11 empty] | 0.23899 | 0.82672
32 | N-21-02 | Non Planned Capital works (O&M) 2021-22 | Non Pln works in O &M | Through out TGTRNSCO | SR | --- | --- | --- | [11 empty] | 1.4213 | 1.5269
33 | N-22-02 | Non Planned Capital works (O&M) 2022-23 | Non Pln works in O &M | Through out TGTRNSCO | SR | --- | --- | --- | [11 empty] | 8.2172 | 1.3335
34 | N-23-02 | Non Planned Capital works (O&M) 2022-23 | Non Pln works in O &M | Through out TGTRNSCO | SR | --- | --- | --- | [11 empty] | 0.32657 | 0.27108 |  | - | - | - | -
35 | O-16-01 | Rolling stock for FY 2016-2017 | Procurement of Mteril | Through out TGTRNSCO | SR | T. O. O:4 ,Dt:11.01.2017 | --- | --- | [11 empty] | 7.8579 | 7.8579 |  | - | - | - | -
36 | R-15-01 | RMI for the year 2015 | Renovtion modernition nd Improvement | Through out TGTRNSCO | SR | T. O. O:182 ,Dt:16.9.2015 | --- | --- | [11 empty] | 0.16657 | 0.30974 |  | - | - | - | -
37 | R-17-01 | RMI for FY:2017-18 & 2018-19 | Renovtion modernition nd Improvement | Through out TGTRNSCO | SR | T. O. O:146 ,Dt:7.10.2017 | --- | --- | [11 empty] | 2.3741 | 1.9939 |  | - | - | - | -
38 | R-17-02 | 132 KV BEL'PALLY - S' KHAGAZ NAGAR TOWER | Renovtion modernition nd Improvement | Through out TGTRNSCO | SR |  | --- | --- | 23.04.2018 | 23.04.2018 |  | 31.03.2024 | [7 empty] | -0.12838 | 4.4065 |  | - | - | - | -
39 | R-20-01 | Renovation & Modernization Scheme - 2020 | Renovtion modernition nd Improvement | Through out TGTRNSCO | SR | T. O. O:843 ,Dt:16.9.2020 | --- | --- | [11 empty] | 3.5302 | 5.5314 |  | - | - | - | -
40 | R-21-01 | RMI scheme for FY 2021-22 | Renovtion modernition nd Improvement | Through out TGTRNSCO | SR | T. O. O:1336,Dt:14.3.2022 | --- | --- | [11 empty] | 6.9925 | 3.1082 |  | - | - | - | -
41 | R-22-01 | RMI 2022-23 | Renovtion modernition nd Improvement | Through out TGTRNSCO | SR | T.O.O:1549,Dt.10.01.2023 | --- | --- | [11 empty] | 3.1772 | 1.1608 |  | - | - | - | -
42 | R-23-01 | RMI(2023-24) Replace of Old & Obsolete E | Renovtion modernition nd Improvement | Through out TGTRNSCO | SR | T.O.O:1810,Dt.07.10.2023 | --- | --- | [11 empty] | 0.031296 | 0.031296 |  | - | - | - | -
43 | S-22-01 | Const. of 33KV bays at 132/33KV Substati | [17 empty] | 1.172 | 1.8356 |  | - | - | - | -
44 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION | Procurement of Mteril | Through out TGTRNSCO | SR |  | - | - | [11 empty] | 2.529 | 4.0503 |  | - | - | - | -
45 | Z-99-01 | Rolling Stocks Procurement N Consumption | Procurement of Mteril | Through out TGTRNSCO | SR |  | - | - | [11 empty] | 10.0356 | 8.5582 |  | - | - | - | -
II. New schemes taken up during 2023-24
Sub-total-II | [19 empty] | 0.031296 | 0.031296
1 | R-23-01 | RMI(2023-24) Replace of Old & Obsolete E | Renovtion modernition nd Improvement | Through out TGTRNSCO | SR | T.O.O:1810,Dt.07.10.2023 | --- | --- | [11 empty] | 0.031296 | 0.031296 |  | - | - | - | -
III. Non-plan schemes taken up during 2023-24
Sub-total-III | [19 empty] | 0.32657 | 0.27108
1 | N-23-02 | Non Planned Capital works (O&M) 2022-23 | Non Pln works in O &M | Through out TGTRNSCO | SR | --- | --- | --- | [11 empty] | 0.32657 | 0.27108 |  | - | - | - | -
Grans Total I + II + III | [19 empty] | 155.163 | 128.4331
Note : Project Purpose : System Improvement (SI), System Expansion (SE), System Replacements (SR)/ RMI, Generation Evacuation (GE)
The statement to be printed on A3 size sheets please

## CapEx 25-26
TRANSMISSION CORPORATION OF TELANGANA LIMITED
Annual Petition for 2024-25 for Transmission Business filed with TGERC
Scheme wise details of Capital Expenditure proposed for Financial Year 2025-26
Sl No. | Project Code / Scheme ID (SAP Code) | Project Title (SAP Project title) | Scope of work (Names of all the Sub-stations and Lines included in the scheme maybe given) | Justification | Project Purpose (SI/SE/SR/GE) | Administrative Approval TOO Ref. | SRPC approval (if any) | TGERC Investment Approval Ref. | Total TGERC approved Cost (in Cr) | Source of funds |  |  |  | Proposed Project Start Date DD-MM-YY | Proposed Project Completion Date DD-MM-YY | CWIP O.B. | FY:2024-25 |  |  | Projected expenditure for 2025-26 | Spill over Yearly Capital Expenditure projected for works taken up in or before 2025-26 (in Cr) |  |  | Total Cumulative Expenditure (in Cr) | Present Status of work
[10 empty] | TGTransco funds | Loan source | Loan Amount | Grants, if any |  |  |  | 1st Half (Apr-Sept) (Actuals) | 2nd Half (Oct-Mar) (Projected) | Total 24-25 (Projected) |  | 2026-27 | 2027-28 | 2028-29
1 | 2 | 3 | 4 |  | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 |  |  |  | 17 | 18 | 19 | 20 | 21 | 22
I. Ongoing Schemes as on 01.04.2025
1 | O-16-01 | Rolling stock for FY 2016-2017 | Procurement of Mteril |  | SR | T. O. O:4 ,Dt:11.01.2017 | - | - | 39.53 |  | REC | 31.624 | - | 11.01.2017 | 31.03.2025 | 11.8459 | 4.5998 | 5 | 9.5998 | [5 empty] | Works under progress
2 | O-18-01 | Procure of Major SS equip under rolling | Procurement of Mteril |  | SR | T. O. O:70 ,Dt:3.4.2019 | - | - | 26.43 |  | REC |  | - | 3.4.2018 | 31.03.2025 | 0.73316 | -0.025659 |  | -0.025659 | [5 empty] | Works completed - Scheme Closed
3 | R-15-01 | RMI for the year 2015 | Renovtion modernition nd Improvement |  | SR | T. O. O:182 ,Dt:16.9.2015 | - | - | 53.08 |  | PFC | 47.772 | - | 16.09.2015 | 31.03.2025 | 2.0437 | 0.026581 |  | 0.026581 | [5 empty] | Works about to complete
4 | Z-21-01 | ROLLING STOCKS PROC AND CONSUMPTION | Procurement of Mteril |  | SR | - | - | - | 64.38 | TGTRNSCO |  |  |  | 01.04.2021 | 31.03.2025 | 4.7126 | -0.11753 |  | -0.11753 | [5 empty] | Works under progress
5 | Z-99-01 | Rolling Stocks Procurement N Consumption | Procurement of Mteril |  | SR | - | - | - | 77.3 | TGTRNSCO |  |  |  | 1.04.2022 | 31.03.2025 | 10.6105 | 3.9434 |  | 3.9434 | [5 empty] | Works under progress
6 | R-17-01 | RMI for FY:2017-18 & 2018-19 | Through out TGTRNSCO |  | SR | T. O. O:146 ,Dt:7.10.2017 | - | - | 100.22 | - | REC |  |  | 7.10.2017 | 31.03.2027 | 2.8275 | 0.40474 | 5 | 5.4047 | 20 | 27 | 0 | 0 | 52.4047 | Works under progress
7 | R-20-01 | Renovation & Modernization Scheme - 2020 | Renovtion modernition nd Improvement |  | SR | T. O. O:843 ,Dt:16.9.2020 | - | - | 75.6 | - | REC |  |  | 16.09.2020 | 31.03.2027 | 8.3332 | 0.48233 | 8 | 8.4823 | 20 | 17.6 | 0 | 0 | 46.0823 | Works under progress
8 | R-21-01 | RMI scheme for FY 2021-22 | Renovtion modernition nd Improvement |  | SR | T. O. O:1336,Dt:14.3.2022 | - | - |  | TGTRNSCO | - |  |  | 14.03.2022 | 31.03.2027 | 7.5167 | 3.3391 | 8 | 11.3391 | 20 | 16.7 | 0 | 0 | 48.0391 | Works under progress
9 | R-22-01 | RMI 2022-23 | Renovtion modernition nd Improvement |  | SR | T.O.O:1549,Dt.10.01.2023 | - | - | 63.29 |  | HUDCO |  |  | 10.01.2023 | 31.03.2028 | 5.6096 | 5.1736 | 5 | 10.1736 | 20 | 20 | 8.29 | 0 | 58.4636 | Works under progress
10 | R-23-01 | RMI(2023-24) Replace of Old & Obsolete E | Renovtion modernition nd Improvement |  | SR | T.O.O:1810,Dt.07.10.2023 | - | - | 67.9 |  | HUDCO |  |  | 07.10.2023 | 31.03.2028 | 0.073431 | 1.3281 | 15 | 16.3281 | 20 | 20 | 12.2 | 0 | 68.5281 | Works under progress
11 | N-24-02 | Non pln works in O & M | Non pln works |  | 5: SR; 7: -; 8: -; TGTransco funds 10: TGTRNSCO; Grants, if any 14: 01.04.2024; Grants, if any 15: 31.03.2025; Grants, if any 16: 0 | 0 | 7.72 | 7.72 | 0 | 0 | 0 | 0 | 7.72 | Works under progress
12 |  | RMI(2024-25) Replace of Old & Obsolete E | Renovtion modernition nd Improvement |  | 5: SR; 6: To be issued; 7: -; 8: -; Grants, if any 14: T.O.O to be issued; Grants, if any 15: 31.03.2028; Grants, if any 16: 0 | 0 | 5 | 5 | 20 | 15 | 7 | 0 | 47 | Works to be taken up fter issuing T.O.O
13 | A-15-05 | AUGof PTR@EHT SS for extending 9Hrs | AUGof PTR@EHT SS for extending 9Hrs |  | SE | TOO No 82 DT 01.05.2015 | --- | --- | 32.01 | TSTRANSCO | --- | --- | --- | 01.04.2016 | 31.03.2025 | 0.020474 | -0.020474 |  | -0.020474 | [5 empty] | Works completed - Scheme Closed
14 | A-15-06 | AUGof PTR@EHT SS for extending 9Hrs | AUGof PTR@EHT SS for extending 9Hrs |  | SE | TOO No 83 DT 01.05.2015 | --- | --- | 9.36 | TSTRANSCO | --- | --- | --- | 01.04.2016 | 31.03.2025 | 0 | 0.038204 |  | 0.038204 | [5 empty] | Works completed - Scheme Closed
15 | A-15-22 | STRENGTHENING OF 10 NOS. OVERLOAD LINES | Stengthening of existing conductor with HTLS | Stengthening of existing conductor with HTLS | SE | T. O. O. (CE/Transmission) MS.No.158 dated 23.11.2016 | --- | --- | 215.07 |  | PFC |  |  | 18.04.2016 | 14.12.2016 | 2.113 | -2.0826 |  | -2.0826 | [5 empty] | Works completed - Scheme Closed
16 | A-16-01 | 3rd 31.5MVA PTR at Adilabad SS | 3rd 31.5MVA PTR at Adilabad SS | Augmentation | SE | T. O. O. (CE/Transmission) MS.No.37 dated 01.03.2016 | --- | --- | 1.02 | TSTRANSCO | --- | --- | --- | 01.04.2016 | 31.03.2025 | 0.017827 | -0.017827 |  | -0.017827 | [5 empty] | Works completed - Scheme Closed
17 | A-17-02 | Aug Sys Stren & 24 Hrs Agl METRO & RURAL | Aug Sys Stren & 24 Hrs Agl METRO & RURAL | To meet the Industrial, Agriculture loads etc | SE | T. O. O. (CE/Transmission) MS.No.87 dated 20.06.2017 | --- | --- | 51.29 | TSTRANSCO | --- | --- | --- | 01.04.2017 | 31.03.2025 | 0.63079 | -0.11755 |  | -0.11755 | [5 empty] | Works completed - Scheme Closed
18 | A-18-01 | Aug of PTR capacity at 220KV Ch'gutta | Aug of PTR capacity at 220KV Ch'gutta | Augmentation | SE | T. O. O. (CE/Transmission) MS.No.78 dated 13.04.2018 | --- | --- | 15.3 | TSTRANSCO | --- | --- | --- | 01.04.2018 | 31.03.2025 | 0 | 8.8998 |  | 8.8998 | [5 empty] | Works completed
19 | A-19-01 | Aug of 4th 160 MVA at 220KV Gachibowli | Aug of 4th 160 MVA at 220KV Gachibowli | Augmentation | SE | T.O.O.396, Dt:03.07.2019 | --- | --- | 6.21 | TSTRANSCO | --- | --- | --- | 01.04.2019 | 31.03.2025 | 0.086154 | -0.016069 |  | -0.016069 | [5 empty] | Works completed
20 | A-19-02 | Augmentation of 132 KV Chintal SS | Augmentation of 132 KV Chintal SS |  | SE | T.O.O.724, Dt:22.02.2020 | --- | --- | 0.69 | TSTRANSCO | --- | --- | --- | 01.04.2019 | 31.03.2025 | 0.058549 | 0.022639 |  | 0.022639 | [5 empty] | Works completed
21 | A-19-03 | Augmentation of 80 MVA at 132 KV IDPL SS | Augmentation of 80 MVA at 132 KV IDPL SS |  | SE | T.O.O.731, Dt:07.03.2020 | --- | --- | 0.72 | TSTRANSCO | --- | --- | --- | 01.04.2019 | 31.03.2025 | 0.030477 | -0.00019175 |  | -0.00019175 | [5 empty] | Works completed
22 | A-19-05 | Augmentation of PTRs at gesukonda & Tiru | Augmentation of PTRs at gesukonda & Tiru | To meet the growing loads | SE | T.O.O.738, Dt:18.03.2020 | --- | --- | 0.76 | TSTRANSCO | --- | --- | --- | 01.04.2019 | 31.03.2025 | 0.17489 | 0.053061 |  | 0.053061 | [5 empty] | Works completed
23 | A-20-01 | Augmentation at 220KV Manthani SS & 132K | Augmentation at 220KV Manthani SS & 132K | To meet the growing loads | SE | T.O.O.780, Dt:10.06.2020 | --- | --- | 8.97 | TSTRANSCO | --- | --- | --- | 01.04.2020 | 31.03.2025 | 0.40334 | 0.46235 |  | 0.46235 | [5 empty] | Works completed
24 | A-20-02 | Aug of 3rd 220/132KV PTR at 400KV Narsap | Aug of 3rd 220/132KV PTR at 400KV Narsap | To meet the growing loads | SE | T.O.O.792, Dt:26.06.2020 | --- | --- | 3.63 | TSTRANSCO | --- | --- | --- | 01.04.2020 | 31.03.2025 | 2.3196 | 0.22408 |  | 0.22408 | [5 empty] | Works completed
25 | A-20-03 | Aug of PTR at Warangal & Karimnagar Circ | Aug of PTR at Warangal & Karimnagar Circ | To meet the growing loads | SE | T.O.O.856, Dt:03.10.2020 | --- | --- | 8.66 | TSTRANSCO | --- | --- | --- | 01.04.2020 | 31.03.2025 | 0.56393 | 0.67015 |  | 0.67015 | [5 empty] | Works under progress
26 | A-20-04 | Augmentation of PTR at 132KV Donthanpall | Augmentation of PTR at 132KV Donthanpall | To meet the growing loads | SE | T.O.O.870, Dt:03.11.2020 | --- | --- | 0.33 | TSTRANSCO | --- | --- | --- | 01.04.2020 | 31.03.2025 | 0.07516 | -0.024242 |  | -0.024242 | [5 empty] | Works completed
27 | A-20-06 | Aug of 3rd PTR at 132KV MDPally SS | Aug of 3rd PTR at 132KV MDPally SS | To meet the growing loads | SE | 03.01.2020 | --- | --- | 3.92 | TSTRANSCO | --- | --- | --- | 03.01.2020 | 31.03.2025 | 0.067765 | -0.043523 |  | -0.043523 | [5 empty] | Works completed
28 | A-20-07 | Aug of 4rd PTR at 132KV Pashmailaram SS | Aug of 4rd PTR at 132KV Pashmailaram SS | To meet the growing loads | SE | T.O.O.1026, Dt:30.03.2021 | --- | --- | 1.56 | TSTRANSCO | --- | --- | --- | 30.03.2021 | 31.03.2025 | 0.024242 | 0.056994 |  | 0.056994 | [5 empty] | Works completed
29 | A-21-01 | Aug of 160 MVA PTR at 400KV Suryapet SS | Aug of 160 MVA PTR at 400KV Suryapet SS | To meet the growing loads | SE | T.O.O.1034, Dt:12.04.2021 | --- | --- | 8.35 | TSTRANSCO | --- | --- | --- | 01.04.2021 | 31.03.2025 | 0.26858 | -0.003776 |  | -0.003776 | [5 empty] | Works completed
30 | A-21-02 | Aug of 132/33 KV PTRs at Mamidipally & 4 | Aug of 132/33 KV PTRs at Mamidipally & 4 | To meet the growing loads | SE | T.O.O.1053, Dt:07.05.2021 | --- | --- | 11.47 | TSTRANSCO | --- | --- | --- | 01.04.2021 | 31.03.2025 | 0.64038 | 4.3679 |  | 4.3679 | [5 empty] | Works under progress
31 | A-21-04 | Aug. of PTR capacity at 220KV Huzurabad | Aug. of PTR capacity at 220KV Huzurabad | To meet the growing loads | SE | T.O.O.1167, Dt:18.08.2021 | --- | --- | 6.03 | TSTRANSCO | --- | --- | --- | 18.08.2021 | 31.03.2025 | 9.3091 | -0.0037761 |  | -0.0037761 | [5 empty] | Works completed
32 | A-21-05 | Augmentations of 220KV PTRs at 5Nos Subs | Augmentations of 220KV PTRs at 5Nos Subs | To meet the growing loads | SE | T.O.O1209, Dt:04.10.2021 | --- | --- | 6.03 | TSTRANSCO | --- | --- | --- | 04.10.2021 | 31.03.2025 | 20.9971 | 9.1316 |  | 9.1316 | [5 empty] | Works under progress
33 | A-21-06 | Augmentations of 132KV PTRs at 24Nos Sub | Augmentations of 132KV PTRs at 24Nos Sub | To meet the growing loads | SE | T.O.O1211, Dt:07.10.2021 | --- | --- | 48.75 | TSTRANSCO | --- | --- | --- | 07.10.2021 | 31.03.2025 | 4.989 | 3.5985 |  | 3.5985 | [5 empty] | Works under progress
34 | A-22-01 | Aug of PTR cap at 132KV Medchal SS & Deration of PTR cap at Chilkalguda | Aug of PTR cap at 132KV Medchal SS & Deration of PTR cap at Chilkalguda | To meet the growing loads | SE | T.O.O1411, Dt.06.06.2022 | --- | --- | 0.26 | TSTRANSCO | --- | --- | --- | 07.10.2021 | 31.03.2025 | 0 | 0.026992 | 0 | 0.026992 | [5 empty] | Works under progress
35 | A-22-02 | Augmentation of PTR at 132KV Balanagar S | Augmentation of PTR at 132KV Balanagar S | To meet the growing loads | SE | T.O.O.1486, Dt:11.10.2022 | --- | --- | 6.27 | TSTRANSCO | --- | --- | --- | 11.10.2022 | 31.03.2025 | 0.046288 | 0.026992 | 0 | 0.026992 | [5 empty] | Works under progress
36 | A-22-03 | Aug. of PTR at Kaithalapur & Bhongir | Aug. of PTR at Kaithalapur & Bhongir | To meet the growing loads | SE | T.O.O.1537, Dt:21.12..2022 | --- | --- | 0.49 | TSTRANSCO | --- | --- | --- | 21.12.2022 | 31.03.2025 | 0.092576 | 0.007697 | 0 | 0.007697 | [5 empty] | Works under progress
37 | A-23-01 | Augmentations of PTR cap at 400KV Suryapet SS | Augmentations of PTR cap at 400KV Suryapet SS | To meet the growing loads | SE | T.O.O.1721, Dt:11.07.2023 | --- | --- | 18.41 | HUDCO | --- | --- | --- | 11.07.2023 | 31.03.2025 | 0 | 9.0008 | 0 | 9.0008 | [5 empty] | Works under progress
38 | A-23-02 | Aug. of 132/33KV PTR Cap at 4 Nos. EHT SS | Aug. of 132/33KV PTR Cap at 4 Nos. EHT SS | To meet the growing loads | SE | T.O.O.1802 Dt:27.09..2023 | --- | --- | 18.4 | TSTRANSCO | --- | --- | --- | 27.09.2023 | 31.03.2025 | 0 | 0.0026306 | 0 | 0.0026306 | [5 empty] | Works under progress
39 | A-23-09 | Aug. of 132/33KV PTR Cap at 9 Nos. EHT SS | Aug. of 132/33KV PTR Cap at 9 Nos. EHT SS | To meet the growing loads | SE | T.O.O.1879, Dt:10.01.2024 | --- | --- | 25.09 | TSTRANSCO | --- | --- | --- | 10.01.2024 | 31.03.2026 | 5.1076 | 9.501 | 0 | 9.501 | [5 empty] | Works under progress
40 | D-16-06 | Erection 33KV Bays TSNPDCL | Erection 33KV Bays TSNPDCL |  | SE | T.O.O 46, Dt:31.03.2016 | --- | --- | 16.31 | DC works | --- | --- | --- | 31.03.2016 | 31.03.2024 | 0.017311 | -0.017311 |  | -0.017311 | [5 empty] | Works completed
41 | D-20-43 | 33 KV Bay for TSNPDCL at 132KV Dasnagar | 33 KV Bay for TSNPDCL at 132KV Dasnagar |  | SE | Lr.No 647 Dt 08.02.2021 | --- | --- | 0.17 | DC works | --- | --- | --- | 08.02.2021 | 31.03.2026 | 0.059441 | -0.025137 | 0 | -0.025137 | [5 empty] | Works completed
42 | D-21-16 | 4Nos 33KV Bays in substation in OMC Wara | 4Nos 33KV Bays in substation in OMC Wara |  | SE | Lr.No.1478 Dt 25.02.2022 | --- | --- | 0.84 | DC works | --- | --- | --- | 25.02.2022 | 31.03.2026 | 0.21406 | -0.11066 | 0 | -0.11066 | [5 empty] | Works completed
43 | D-22-15 | Aug of PTR Capacity at 220 KV HIAL SS | Aug of PTR Capacity at 220 KV HIAL SS |  | SE | Lr.No.275 Dt 08.06.2022 | --- | --- | 14.93 | DC works | --- | --- | --- | 08.06.2022 | 31.03.2026 | 0.46944 | 11.859 | 5 | 16.859 | [5 empty] | Works under progress
44 | D-22-16 | Replmnt old 132KV C&R panel with new C&R | Replmnt old 132KV C&R panel with new C&R |  | SR | Lr.No.278 Dt 08.06.2022 | --- | --- | 0.079 | DC works | --- | --- | --- | 08.06.2022 | 31.03.2026 | 0 | 0.03962 | 0 | 0.03962 | [5 empty] | Works under progress
45 | D-22-17 | Replmnt CTs & PTs NFCI&II feeders @220KV | Replmnt CTs & PTs NFCI&II feeders @220KV |  | SR | Lr.No.347 Dt 23.08.2022 | --- | --- | 1.44 | DC works | --- | --- | --- | 23.08.2022 | 31.03.2026 | 0.86357 | 0.48217 | 0 | 0.48217 | [5 empty] | Works under progress
46 | D-23-05 | 132KV Karimnagar Waterworks - 33KV RTC F | 132KV Karimnagar Waterworks - 33KV RTC F |  | SE/ | Lr.No.1287 Dt 13.12.2023 | --- | --- | 0.33 | DC works | --- | --- | --- | 13.12.2023 | 31.03.2026 | 0 | 0.086755 | 0.1 | 0.18676 | [5 empty] | Works under progress
47 | D-23-26 | 33KV Bays for Consumers in GHMC Area - D | 33KV Bays for Consumers in GHMC Area - D |  | SE | 3417, Dt:18.08.2023. | --- | --- | 1.64 | DC works | --- | --- | --- | 18.08.2026 | 31.03.2026 | 0 | 0.058649 | 2 | 2.0586 | [5 empty] | Works under progress
48 | D-24-01 | 33 KV Bays for customers in EHT Substations | 33 KV Bays for customers in EHT Substations |  | SE | Lr.No.47/2023, Dt.13.04.2023 | --- | --- | 2.82 | DC works | --- | --- | --- | 01.04.2023 | 31.03.2026 | 0 | 0.27305 | 1 | 1.273 | 1 |  |  |  |  | Works under progress
49 | S-22-01 | Const. of 33KV bays at 132/33KV Substati | Const. of 33KV bays at 132/33KV Substati |  | SE | Lr.No.810 Dt 05.03.2022 | --- | --- | 2.11 | TGTRANSCO | --- | --- | --- | 05.03.2022 | 31.03.2026 | 0.14265 | 0.099461 | 0.5 | 0.59946 | 0.5 |  |  |  |  | Works under progress
50 | S-23-01 | Const. of 33 KV Bays at 132/33 Substatio | Const. of 33 KV Bays at 132/33 Substatio |  | SE | Lr.No.47/2023, Dt.13.04.2023 | --- | --- | 2.29 | TGTRANSCO | --- | --- | --- | 13.04.2023 | 31.03.2026 | 0 | 0.49565 | 0.2 | 0.69565 | 1 |  |  |  |  | Works under progress
51 | S-24-01 | Const. of 33 KV Bays at 132/33 Substatio | Const. of 33 KV Bays at 132/33 Substatio |  | SE | Lr.No.40/2023, Dt.10.04.2024 | --- | --- | 0.22 | TGTRANSCO | --- | --- | --- | 10.04.2024 | 31.03.2026 | 0 | 0 | 0.1 | 0.1 | 0.1 |  |  |  |  | Works under progress
52 | A-17-01 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31.03.2025 | 0.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
53 | A-18-05 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31.03.2025 | 1.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
54 | A-19-04 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31.03.2025 | 0.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
55 | A-20-05 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31.03.2025 | 0.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
56 | D-18-04 | Erection of ABT Metering arrangement 220 | Erection of ABT Metering arrangement 220 |  | SR | 0 | --- | --- | 0.6 | --- | --- | --- | --- | 0 | 31.03.2025 | 0.053714 | 0.11471 | 0.5 | 0.61471 | 0.92286 | 0 | 0 | 0 | 0 | 0
57 | D-18-11 | Replacement of old CTs & PTs at 132KV OC | Replacement of old CTs & PTs at 132KV OC |  | SR | Lr.No 4228 Dt 28.09.2018 | --- | --- | 0.57 | --- | --- | --- | --- | 28.09.2018 | 31.03.2025 | 0.065452 | 0 | 0.4 | 0.4 | 0.81658 | Deposit contribution Works | 0 | 0 | 0 | 0
58 | D-18-20 | Providing of ABT Meters for all Traction | Providing of ABT Meters for all Traction |  | SR | Lr.No 138 Dt 21.02.2019 | --- | --- | 9.65 | --- | --- | --- | --- | 21.02.2019 | 31.03.2025 | 2.0105 | 0 | 1 | 1 | 0.31197 | Deposit contribution Works | 0 | 0 | 0 | 0
59 | D-19-07 | ABT Metering at 132 KV Manuguru & Kothag | ABT Metering at 132 KV Manuguru & Kothag |  | SR | Lr.No.333 Dt 18.06.2019 | --- | --- | 1.06 | --- | --- | --- | --- | 18.06.2019 | 31.03.2025 | 0.041295 | 0 | 0.8 | 0.8 | 0.79367 | Deposit contribution Works | 0 | 0 | 0 | 0
60 | D-19-08 | ABT Metering at 132KV OCM & Mandamarry S | ABT Metering at 132KV OCM & Mandamarry S |  | SR | Lr.No.677 Dt 05.10.2019 | --- | --- | 9.29 | --- | --- | --- | --- | 05.10.2019 | 31.03.2025 | 0.22773 | -0.34143 | 0.4 | 0.058568 | 0.06757 | Deposit contribution Works | 0 | 0 | 0 | 0
61 | D-19-14 | 33 KV Bay extension at 220KV SS Manguru | 33 KV Bay extension at 220KV SS Manguru |  | SE | Lr.No.14 Dt 04.03.2020 | --- | --- | 0.2 | --- | --- | --- | --- | 04.03.2020 | 31.03.2025 | 0.024242 | 0 | 0.1 | 0.1 | 0.62121 | Deposit contribution Works | 0 | 0 | 0 | 0
62 | D-20-16 | Erection of 4Nos 33KV Bays for M/s Amazo | Erection of 4Nos 33KV Bays for M/s Amazo |  | SE | Lr.No.33 Dt 17.04.2020 | --- | --- | 1.59 | --- | --- | --- | --- | 17.04.2020 | 31.03.2025 | 0.1416 | -0.054404 | 0.8 | 0.7456 | 0.5922 | Deposit contribution Works | 0 | 0 | 0 | 0
63 | D-20-17 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31.03.2025 | 0.13 | 0.24058 | 0 | 0.24058 | 0 | 0 | 0 | 0 | 0 | 0
64 | D-20-20 | 33KV Bay at 220KV FABCITY SS for chirpa | 33KV Bay at 220KV FABCITY SS for chirpa |  | SE | Lr.No.70 Dt 08.05.2020 | --- | --- | 0.43 | --- | --- | --- | --- | 08.05.2020 | 31.03.2025 | 0.059651 | -0.024452 | 0.3 | 0.27555 | 0.8364 | Deposit contribution Works | 0 | 0 | 0 | 0
65 | D-20-21 | 33KV bay for SCCL,Bittupally at 132KV Ma | 33KV bay for SCCL,Bittupally at 132KV Ma |  | SE | Lr. No 1585 Dt 08.07.2020 | --- | --- | 0.27 | --- | --- | --- | --- | 08.07.2020 | 31.03.2025 | 0.024242 | 0 | 0.2 | 0.2 | 0.83052 | Deposit contribution Works | 0 | 0 | 0 | 0
66 | D-20-22 | CT Replacement for Kesoram at Malyalapal | CT Replacement for Kesoram at Malyalapal |  | SR | Lr.No. 161 Dt 29.05.2020 | --- | --- | 0.12 | --- | --- | --- | --- | 29.05.2020 | 31.03.2025 | 0.049841 | 0 | 0.06 | 0.06 | 0.91534 | Deposit contribution Works | 0 | 0 | 0 | 0
67 | D-20-26 | 33KV Bay at 220 Fabcity for Sakura premi | 33KV Bay at 220 Fabcity for Sakura premi |  | SE | Lr.No. 71 Dt 08.05.2020 | --- | --- | 0.44 | --- | --- | --- | --- | 08.05.2020 | 31.03.2025 | 0.059651 | -0.024452 | 0.3 | 0.27555 | 0.81739 | Deposit contribution Works | 0 | 0 | 0 | 0
68 | D-20-27 | 33KV Bays for Amazon at Mahabubnagar Cir | 33KV Bays for Amazon at Mahabubnagar Cir |  | SE | Lr.No 185 Dt 08.07.2020 | --- | --- | 0.66 | --- | --- | --- | --- | 08.07.2020 | 31.03.2025 | 0.19605 | -0.11481 | 0.2 | 0.085191 | 0.60007 | Deposit contribution Works | 0 | 0 | 0 | 0
69 | D-20-36 | 220KV Shivrampally SS-4Nos 33KV bays for | 220KV Shivrampally SS-4Nos 33KV bays for |  | SE | Lr.No.641 Dt 08.02.2021 | --- | --- | 1.17 | --- | --- | --- | --- | 08.02.2021 | 31.03.2025 | 0.13899 | 0.11315 | 0.8 | 0.91315 | 0.80255 | Deposit contribution Works | 0 | 0 | 0 | 0
70 | D-21-20 | 33KV Bay for Raghuram at 132KV Suglampal | 33KV Bay for Raghuram at 132KV Suglampal |  | SE | Lr.No.1375 Dt 30.10.2021 | --- | --- | 0.23 | --- | --- | --- | --- | 30.10.2021 | 31.03.2025 | 0.082901 | 0 | 0.1 | 0.1 | 0.79522 | Deposit contribution Works | 0 | 0 | 0 | 0
71 | D-21-26 | 33KV Bay for singareni at 132KV Penuball | 33KV Bay for singareni at 132KV Penuball |  | SE | Lr.No.599 Dt 07.09.2021 | --- | --- | 0.13 | --- | --- | --- | --- | 07.09.2021 | 31.03.2025 | 0.033682 | -0.033682 | 0.08 | 0.046318 | 0.87447 | Deposit contribution Works | 0 | 0 | 0 | 0
72 | D-21-46 | 33KV Bay at 132KV B.Gangaram for diverio | 33KV Bay at 132KV B.Gangaram for diverio |  | SE | Lr.No.482 Dt 26.07.2021 | --- | --- | 0.16 | --- | --- | --- | --- | 26.07.2021 | 31.03.2025 | 0.0031441 | -0.0031441 | 0.1 | 0.096856 | 0.64465 | Deposit contribution Works | 0 | 0 | 0 | 0
73 | D-22-03 | Replacement of 132KV metering CT&PTs at | Replacement of 132KV metering CT&PTs at |  | SR | --- | --- | --- | 0.25 | --- | --- | --- | --- | 01.04.2022 | 31.03.2025 | 0.12235 | -0.02031 | 0.1 | 0.07969 | 0.8894 | Deposit contribution Works | 0 | 0 | 0 | 0
74 | D-22-07 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31.03.2025 | 0.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
75 | D-22-12 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31.03.2025 | 0.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
76 | D-23-12 | 132KV Nizamabad SS - 33KV RTC Feeder Bay | 132KV Nizamabad SS - 33KV RTC Feeder Bay |  | SE | --- | --- | --- | 0.22 | --- | --- | --- | --- | 01.04.2023 | 31.03.2025 | 0.10976 | 0 | 0.1 | 0.1 | 0.95347 | 0 | 0 | 0 | 0 | 0
77 | N-16-OMCP | O&M CAPITAL MAT. PROC. for FY: 2016-17 | 0 |  | 0 | 0 | 0 | 0 | 6.58 | 0 | 0 | 0 | 0 | 0 | 31.03.2025 | 0.031424 | 0 | 0 | 0 | 0.0047757 | 0 | 0 | 0 | 0 | 0
78 | N-16-OMCP-OPENCAPSTOCK | Migrate OMC Open Capital Inventory | 0 |  | 0 | 0 | 0 | 0 | 32.54 | 0 | 0 | 0 | 0 | 0 | 31.03.2025 | 0.92904 | -0.031983 | 0 | -0.031983 | 0.028551 | 0 | 0 | 0 | 0 | 0
79 | N-17-OMCP | O&M CAPITAL MAT. PROC. for FY: 2017-18 | 0 |  | 0 | 0 | 0 | 0 | 16.57 | 0 | 0 | 0 | 0 | 0 | 31.03.2025 | 0.55526 | 0 | 0 | 0 | 0.03351 | 0 | 0 | 0 | 0 | 0
80 | N-19-02 | Non Planned Capital works (O&M) 2019-20 | 0 |  | 0 | 0 | 0 | 0 | 3.52 | 0 | 0 | 0 | 0 | 0 | 31.03.2025 | 0 | 0.0031283 | 0 | 0.0031283 | 0 | 0 | 0 | 0 | 0 | 0
81 | N-19-OMCP | Cap.Material Drawl in O&M for FY:2019-20 | 0 |  | 0 | 0 | 0 | 0 | 0.77 | 0 | 0 | 0 | 0 | 0 | 31.03.2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
82 | N-20-02 | Non Planned Capital works (O&M) 2020-21 | Non Pln works in O &M |  | SR | - | - | - | 6.3 | TGTRNSCO | - | - | - | 01.04.2020 | 31.03.2025 | 0.28342 | 0.022341 | 0 | 0.022341 | 0.044988 | 0 | 0 | 0 | 0 | 0
83 | N-21-02 | Non Planned Capital works (O&M) 2021-22 | Non Pln works in O &M |  | SR | - | - | - | 10.91 | TGTRNSCO | - | - | - | 01.04.2021 | 31.03.2025 | 2.5199 | 0.39107 | 0 | 0.39107 | 0.23097 | 0 | 0 | 0 | 0 | 0
84 | N-22-02 | Non Planned Capital works (O&M) 2022-23 | Non Pln works in O &M |  | SR | - | - | - | 26.48 | TGTRNSCO | - | - | - | 01.04.2022 | 31.03.2025 | 13.0002 | 2.9928 | 0 | 2.9928 | 0.49094 | 0 | 0 | 0 | 0 | 0
85 | N-23-02 | Non Planned Capital works (O&M) 2022-23 | 0 |  | 0 | 0 | 0 | 0 | 3.74 | 0 | 0 | 0 | 0 | 0 | 31.03.2025 | 0.055491 | 0.13398 | 0 | 0.13398 | 0.014837 | 0 | 0 | 0 | 0 | 0
86 | R-16-02 | PSDF | PSDF |  | SR | T.O.O. 19, Dt::08.02.2016. | - | - | 59.97 | 0 | 0 | 0 | PSDF grant-90% | 08.02.2016 | 31.03.2021 | 0.025321 | 0 | 0 | 0 | 0.00042223 | 0 | 0 | 0 | 0 | 0
87 | R-17-02 | 132 KV BEL'PALLY - S' KHAGAZ NAGAR TOWER | RMI |  | SR | 0 | 0 | 0 | 4.79 | 0 | 0 | 0 | 0 | 23.04.2018 | 31.03.2024 | 0.034333 | 0 | -0.128 | -0.128 | -0.019555 | 0 | 0 | 0 | 0 | 0
Sub-total-I |  |  |  |  | Grants, if any 16: 127.2989 | 79.5201 | 73.832 | 153.3521 | 136.515
II. New schemes taken up during 2025-26
1 |  | Augmentation of PTRs at 220KV GIS Osmania, Shivaramaplly |  | Network Improvement in GHMC area to meet growing load and N-1 compliance. | 5: SE; 9: 48; Grants, if any 15: 31.03.2026 |  |  | 0 | 48
2 | A-22-04 | Aug of 132/33KV PTRs at 11Nos. EHT SS |  |  | 9: 18.301; Grants, if any 15: 31.03.2025; Grants, if any 16: 0.16391 | 2.29 | 10.091 | 12.381
2 |  | Augmentation of PTRs at 220KV Erragadda, Chanchalguda, Moulali, Shamshabad & Fabcity |  | Network Improvement in GHMC area to meet growing load and N-1 compliance. | 5: SE; 9: 44; Grants, if any 15: 31.03.2026 |  |  | 0 | 44
3 |  | Augmentation of PTRs at 220/132KV Nagole, Parigi, Kosig & Siddipet |  | To meet the growing loads | 5: SE; 9: 49; Grants, if any 15: 31.03.2026 |  |  | 0 | 49
4 |  | Augmentation of PTRs at Parigi and 400KV Raidurg SS |  | Network Improvement in GHMC area to meet growing load and N-1 compliance. | 5: SE; 9: 49.2; Grants, if any 15: 31.03.2026 |  |  | 0 | 49.2
5 |  | Augmentation of PTRs at 220KV Shapurnagar, Chandanvelly, Miyapur & Tandur |  | Network Improvement in GHMC area to meet growing load and N-1 compliance. | 5: SE; 9: 44; Grants, if any 15: 31.03.2026 |  |  | 0 | 44
6 |  | Augmentation of PTRs at 220KV Miryalaguda, KM Pally, Narketpally, Kosigi & Siddipet |  | To meet the Industrial, Agriculture loads etc | 5: SE; 9: 47; Grants, if any 15: 31.03.2026 |  |  | 0 | 47
7 |  | Augmentation of PTRs at 220KV Peddagopathi, Siricilla, Renjal & Bheemgal |  | To meet the Industrial, Agriculture loads etc | 5: SE; 9: 47; Grants, if any 15: 31.03.2026 |  |  | 0 | 47
8 |  | Augmentation of PTRs at 220KV Dichpally, Nirmal, Indravelly |  | To meet the Industrial, Agriculture loads etc | 5: SE; 9: 27; Grants, if any 15: 31.03.2026 |  |  | 0 | 27
9 |  | Augmentation of PTRs at 15Nos.132KV SS (132KV Bhikanoor, Pammy, Zaheerabad, Yeldurthy, 220/33KV Singotam, Peddadagada(Chinnamaroor), Munagala, 220/132/33KV Miryalaguda, Yerrabelly, Kanagal, Vikarabad, 220/132/33KV Mahabubnagar, Makthal, Midjil, Sadasivapet) |  | To meet the growing loads | 5: SE; 9: 50; Grants, if any 15: 31.03.2026 |  |  | 0 | 50
10 |  | Augmentation of PTRs at 17Nos.132KV SS (Donthanpally, Kodangal, Dharmasagar, Thungathurthy, Ramapuram, Achampet, Thirumalaipally, Nagarkurnool, Kalwakurthy, Maddur, Peddagada, Khillaghanpur, Balanagar, Amarachintha, Alampur and Borapatla) |  | To meet the Industrial, Agriculture loads etc | 5: SE; 9: 46; Grants, if any 15: 31.03.2026 |  |  | 0 | 46
11 |  | Augmentation of 132KV PTRs at 5Nos.132KV SS(220/132/33KV Fabcity, 132/33KV RC Puram, 220/132/33 KV Gachibowli & 220/132/33KV Shamshabad) |  | Network Improvement in GHMC area to meet growing load and N-1 compliance. | 5: SE; 9: 42; Grants, if any 15: 31.03.2026 |  |  | 0 | 50
12 |  | Augmentation of PTRs at 16Nos.132KV SS (Habsipur, Kandi, Siddipet, Ganeshpally, Duddeda, 220/132/33KV Meenajipet, Bollaram, Patancheru, Bachhannapet, Guduru, Waddekothapally, Peddanagaram, Narmetta, Dornakal, 220/132/33KV Janagaon, Kusumanchi) |  | Network Improvement in Non GHMC area to meet growing load and N-1 compliance. | 5: SE; 9: 46; Grants, if any 15: 31.03.2026 |  |  | 0 | 46
13 |  | Augmentation of PTRs at 16Nos.132KV SS (Habsipur, Kandi, Siddipet, Ganeshpally, Duddeda, 220/132/33KV Meenajipet, Bollaram, Patancheru, Bachhannapet, Guduru, Waddekothapally, Peddanagaram, Narmetta, Dornakal, 220/132/33KV Janagaon, Kusumanchi) |  | To meet the Industrial, Agriculture loads etc | 5: SE; 9: 46; Grants, if any 15: 31.03.2026 |  |  | 0 | 46
14 |  | Augmentation of PTRs at 18Nos.132KV SS (Donthanpally, Kodangal, Dharmasagar, Thungathurthy, Ramapuram, Achampet, Thirumalaipally, Nagarkurnool, Kalwakurthy, Maddur, Peddagada, Khillaghanpur, Balanagar, Amarachintha, Alampur, Chinnashankarampet and Borapatla) |  | To meet the Industrial, Agriculture loads etc | 5: SE; 9: 50; Grants, if any 15: 31.03.2026 |  |  | 0 | 50
15 |  | Augmentation of 132KV PTRs at 6Nos.132KV SS (132KV Jubilee Hills, Chintal, Medchal, E-city, Gunrock, Malkaram, Ibrahimpatnam) |  | Network Improvement in GHMC area to meet growing load and N-1 compliance. | 5: SE; 9: 49; Grants, if any 15: 31.03.2026 |  |  | 0 | 47
16 |  | Augmentation of PTRs at 8Nos.132KV SS |  |  | 5: SE; 9: 47; Grants, if any 15: 31.03.2026 |  |  | 0 | 47
17 |  | Augmentation of PTRs at 8Nos.132KV SS |  |  | 5: SE; 9: 47; Grants, if any 15: 31.03.2026 |  |  | 0 | 47
18 |  | Augmentation of PTRs at 8Nos.132KV SS |  |  | 5: SE; 9: 47; Grants, if any 15: 31.03.2026 |  |  | 0 | 47
19 | A-23-07 | Augmentation of PTRs at 7Nos.132KV SS |  |  | 5: SE; 9: 50; Grants, if any 15: 31.03.2025; Grants, if any 16: 0 | 0.45 |  | 0.45 | 50
20 |  | Augmentation of PTRs at 10Nos.132KV SS |  |  | 5: SE; 9: 47; Grants, if any 15: 31.03.2026 |  |  | 0 | 47
21 |  | Augmentation of PTRs at 7Nos.132KV SS |  |  | 5: SE; 9: 48; Grants, if any 15: 31.03.2026 |  |  | 0 | 48
22 |  | Augmentation of PTRs at 12Nos.132KV SS |  |  | 5: SE; 9: 50; Grants, if any 15: 31.03.2026 |  |  | 0 | 50
23 |  | Augmentation of PTRs at 17Nos.132KV SS |  |  | 5: SE; 9: 47; Grants, if any 15: 31.03.2026 |  |  | 0 | 47
24 |  | Augmentation of PTRs at 5Nos.132KV SS |  |  | 5: SE; 9: 43; Grants, if any 15: 31.03.2026 |  |  | 0 | 43
25 |  | Augmentation of PTRs at 12Nos.132KV SS |  |  | 5: SE; 9: 47; Grants, if any 15: 31.03.2026 |  |  | 0 | 47
26 |  | Augmentation of PTRs at 09Nos.132KV SS |  |  | 5: SE; 9: 32; Grants, if any 15: 31.03.2026 |  |  | 0 | 32
27 | D-23-16 | 220KV Meenajipet SS-33Kv Bay for Coca co |  |  | Grants, if any 15: 31.03.2025; Grants, if any 16: 0 | 0.18 |  | 0.18
28 |  | Renovtion modernition nd Improvement |  |  | 5: SR; 9: 74.86; Grants, if any 15: 31.03.2026 |  |  | 0 | 74.86 |  |  |  | 74.86
Sub-total-II | [16 empty] | 2.92 | 10.091 | 13.011 | 1270.06
III. Non-plan schemes taken up during 2025-26
1 |  | Non Pln works for 25-26 |  |  | 5: SR; 9: 33; Grants, if any 15: 31.03.2026 |  |  |  | 33 |  |  |  | 33
Sub-total-III | [16 empty] | 0 | 0 | 0 | 33
Grans Total I + II + III |  |  |  |  | Grants, if any 16: 127.2989 | 82.4401 | 83.923 | 166.3631 | 1439.575
Note : Project Purpose : System Improvement (SI), System Expansion (SE), System Replacements (SR)/ RMI, Generation Evacuation (GE)
The statement to be printed on A3 size sheets please | [18 empty] | Chief Engineer / Transmission