## CapEx 23-24
TRANSMISSION CORPORATION OF TELANGANA LIMITED
Annual Petition for 2024-25 for Transmission Business filed with TGERC
Scheme-wise details of Capital Expenditure incurred in FY: 2023-24 of 4th control period
(figures in Crores)
Sl No. | Project Code / Scheme ID (SAP Code) | Project Title (SAP Project title) | Scope of work (Names of all the Sub-stations and Lines included in the scheme) | Project Purpose (SI/SE/ SR/GE) | Administrative Approval TOO Ref. | SRPC approval (if any) | TGERC Investment Approval Ref. | Total approved Cost (in Cr) | Source of funds |  |  |  | Project Start Date (DD-MM-YY) | Project Completion Date (DD-MM-YY) | DOC | Opening CWIP as on 31.03.2023 | Actual Expenditure from 01.04.2023 to 31.03.2024 | Cumulative expenditure upto 31.03.2024 | % Capatalisation | Remarks / Balance works , if any.
[9 empty] | TGTransco Funds | Loan source | Loan Amount | Grants, if any
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
I. Ongoing Schemes as on 01.04.2023
Sub-total-I
1 | L-17-02 | Palamuru-Rangareddy Lift Irrigation Scheme. | Phase-I: (i) 400/11kV Narlapur LI SS, (ii) 400/11kV Vattem LI SS, (iii) 400/11kV Yedula LI SS (iv) 2Nos. 400kV QMDC Bays at 400/220kV Veltoor SS, (v) 2Nos.400kV QMDC Bays at 400/220kV Dindi SS, (vi) 400kV Yedula – Narlapur QMDC Line (30kM), (vii) 400kV Dindi – Yedula QMDC Line (60kM), (viii) 400kV Yedula - Vattem QMDC Line (34.50kMs), (ix) 400kV Veltoor - Yedula QMDC Line (52kMs) Phase-II: (i) 400/11kV Uddandapur LI Sub-Station (incl.1No.125MVAR Bus Reactor) (ii) 2Nos. 400kV QMDC Bays at 400/11kV Vattem LI SS, (iii) 400kV QMDC Line from 400/220kV Maheswaram SS to proposed 400/11kV Uddandapur LISS( 65kMs) and (iv) 400kV QMDC Line from proposed 400/11kV Vattem LISS to proposed 400/11kV Uddandapur LISS (34.129 kMs). | SE | TOO (CE-400kV) MS No.467 & 468, Dt:25.10.2019. | -- | -- | 2155.17 | --- | --- | --- | Grants. | May'18 | June'25 |  | 1155.16 | 80.61 | 948.65 | 13.32% (287.12)
Sub-total-II
NIL
III. Non-plan schemes taken up during 2023-24
Sub-total-III |  |  | NIL
Grand Total I + II + III
Note : Project Purpose : System Improvement (SI), System Expansion (SE), System Replacements (SR)/ RMI, Generation Evacuation (GE)
The statement to be printed on A3 size sheets please

## Captlztn 23-24
TRANSMISSION CORPORATION OF TELANGANA LIMITED
PRLIS - Annual Petition for 2024-25 for Transmission Business filed with TGERC
PRLIS - Scheme wise details of Actual Capitalisation for FY 2023-24
(Figures in Rs Crore)
Sl No. | Voltage Level | Project Code (SAP Code) / Scheme IDs | Project Title (SAP Project title) | Scope of work (Names of all the Sub-stations and Lines included in the Scheme) | Project Purpose (SI/SE/SR/GE) | Administrative approval no. with date | SRPC approval no with date (if any) | Investment Approval No. with Date | Work Period |  |  |  |  | Approved Cost as per Investment Approval | Source of Funds |  |  |  | Capitalisation Upto Previous Year (n-1) (as per Audited Financial Statements) | Capital Expenditure during the current year (2023-24) |  |  | Additions to Network |  |  |  | Physical Completion Certificate Nos. | Financial Completion Certificate Nos. | Remarks / Reasons for Cost & Time overruns (if any)
[9 empty] | Start Date |  | Completion Date (Charging date) |  | Date of Capitalization |  | Transco Funds | Loan Source | Loan Amount | Grants, if any |  |  | Capitalisation claimed for the Current year (2023-24) | Whether Part Capitalization or Full Capitalisation | Sub-stations (Nos) | Lines (CKM) | PTR (MVA) | Bays (Nos)
[9 empty] | Schedule | Actual | Schedule | Actual
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
I. Ongoing Schemes as on 01.04.2023
Sub-total-I
1 | 400kV | L-17-02 | PRLIS | Phase-I: (i) 400/11kV Narlapur LI SS, (ii) 400/11kV Vattem LI SS, (iii) 400/11kV Yedula LI SS, (iv) 2Nos. 400kV QMDC Bays at 400/220kV Veltoor SS, (v) 2Nos.400kV QMDC Bays at 400/220kV Dindi SS, (vi) 400kV Yedula – Narlapur QMDC Line (30kM), (vii) 400kV Dindi – Yedula QMDC Line (60kM), (viii) 400kV Yedula - Vattem QMDC Line (34.50kMs), (ix) 400kV Veltoor - Yedula QMDC Line (52kMs). Phase-II: (i) 400/11kV Uddandapur LI Sub-Station (incl.1No.125MVAR Bus Reactor) (ii) 2Nos. 400kV QMDC Bays at 400/11kV Vattem LI SS, (iii) 400kV QMDC Line from 400/220kV Maheswaram SS to proposed 400/11kV Uddandapur LISS( 65kMs) and (iv) 400kV QMDC Line from proposed 400/11kV Vattem LISS to proposed 400/11kV Uddandapur LISS (34.129 kMs). | SE | TOO (CE-400kV) MS No.467 & 468, Dt:25.10.2019. | --- | --- | May'18 | December'23 | March'25 | June'25 | 27.09.2023 | 2155.17 | --- | --- | --- | Grants | Nil | 80.61 | 287.12 | Part | --- | 166.11 | --- | 2 | 2023001190 2023001191 2023001192 | 2024000338 2024000340 2024000341 | Time overun due to Handing over of site by Irrigation & CAD department and ROW issues.
II. New schemes taken up during 2023-24
Sub-total-II |  |  |  | NIL
III. Non-plan schemes taken up during 2023-24
Sub-total-III |  |  |  | NIL
Grans Total I + II + III
Note : Project Purpose : System Improvement (SI), System Expansion (SE), System Replacements (SR)/ RMI, Generation Evacuation (GE)
The statement to be printed on A3 size sheets please

## CapEx 25-26
TRANSMISSION CORPORATION OF TELANGANA LIMITED
Annual Petition for 2024-25 for Transmission Business filed with TGERC
Scheme wise details of Capital Expenditure proposed for Financial Year 2025-26
Sl No. | Project Code / Scheme ID (SAP Code) | Project Title (SAP Project title) | Scope of work (Names of all the Sub-stations and Lines included in the scheme maybe given) | Project Purpose. Cost spill over from 4th Control Period and Reasons for Justification | Project Purpose (SI/SE/SR/GE) | Administrative Approval TOO Ref. | SRPC approval (if any) | TGERC Investment Approval Ref. | Total TGERC approved Cost (in Cr) | Source of funds |  |  |  | Proposed Project Start Date DD-MM-YY | Proposed Project Completion Date DD-MM-YY | CWIP O.B. (31.03.2024) | FY:2024-25 |  |  | Projected expenditure for 2025-26 | Spill over Yearly Capital Expenditure projected for works taken up in or before 2025-26 (in Cr) |  |  | Total Cumulative Expenditure (in Cr) | Present Status of work
[10 empty] | TGTransco funds | Loan source | Loan Amount | Grants, if any |  |  |  | 1st Half (Apr-Sept) (Actuals) | 2nd Half (Oct-Mar) (Projected) | Total 24-25 (Projected) |  | 2026-27 | 2027-28 | 2028-29
1 | 2 | 3 | 4 |  | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 |  |  |  | 17 | 18 | 19 | 20 | 21 | 22
I. Ongoing Schemes as on 01.04.2025
Sub-total-I
1 | L-17-02 | Palamuru-Rangareddy Lift Irrigation Scheme. | Phase-I: (i) 400/11kV Narlapur LI SS, (ii) 400/11kV Vattem LI SS, (iii) 400/11kV Yedula LI SS, (iv) 2Nos. 400kV QMDC Bays at 400/220kV Veltoor SS, (v) 2Nos.400kV QMDC Bays at 400/220kV Dindi SS, (vi) 400kV Yedula – Narlapur QMDC Line (30kM), (vii) 400kV Dindi – Yedula QMDC Line (60kM), (viii) 400kV Yedula - Vattem QMDC Line (34.50kMs), (ix) 400kV Veltoor - Yedula QMDC Line (52kMs). Phase-II: (i) 400/11kV Uddandapur LI Sub-Station (incl.1No.125MVAR Bus Reactor) (ii) 2Nos. 400kV QMDC Bays at 400/11kV Vattem LI SS, (iii) 400kV QMDC Line from 400/220kV Maheswaram SS to proposed 400/11kV Uddandapur LISS( 65kMs) and (iv) 400kV QMDC Line from proposed 400/11kV Vattem LISS to proposed 400/11kV Uddandapur LISS (34.129 kMs). | I&CAD has requested for extending power supply to Narlapur (9Pumps),Vattem (10 Pumps), Yedula (10 Pumps), Uddandapur (6 Pumps) and KP Laxmidevipally (4 Pumps) Pumping stations and power required for the above pumping stations is 4197MW for discharging 2TMC of water per day vide their letter dated 20.05.2017. Subsequently,I&CAD vide letter dated 03.09.2019, have requested for extending power supply to Narlapue (4 Pumps), Vattem (5Pumps), Yedula (5 Pumps) Pumping stations for discharing only 1TMC of water per day.Accordingly,TGTRANSCO has taken up the contruction of 400/11kV Substations at Narlapur, Vattem, Yedula alongwith connected lines and bays under Phase-I of PRLIS.Contract was awarded to M/s.L&T Ltd.,Chennai on 23.10.2020 and works are under progress. Further,I&CAD vide letter dated 17.08.2020,have requested for extending power supply to Uddandapur (3Pumps) Pumping station for discharing only 1TMC per day.Accordingly, TGTRANSCO has taken up the contruction of 400/11kV Uddandapur Substation alongwith connected lines and bays under Phase-II of PRLIS.Contract was awarded to M/s.Kalpataru - Siemens (JV) on 04.03.2022 and works are underprogress. The above works were taken up by TGTRANSCO on the request of I&CAD (Govt. of Telangana) under Depository Contribution Works (DCW). i.e.Total scheme cost will be funded by I&CAD. The execution works are getting delayed due to non receipt of funds from I&CAD. | SE (Lift Irrigation Works). | TOO (CE-400kV) MS No.467 & 468, Dt:25.10.2019. | -- | -- | 2155.17 (*) | -- | -- | -- | Grants. | May'18 | June'25 | 948.65 | 13.72 | 80 | 93.72 | 235.71 | 180 | - | - | 1739.76 | Phase-I works : 90% of works completed. Phase-II works: Transmission lines completed but substation works are held up due to ROW issue.
II. New schemes taken up during 2025-26
Sub-total-II
2 |  | System improvement scheme | 1)220kV and 132kV features at 400/11kV Uddandapur SS 2) 220kV DC line from 400/11kV Uddandapur LI SS to 220/132kV Kosigi SS 3)220kV DC line from 400/11kV Uddandapur LI SS to 220/132kV Shadnagar SS 4) 132kV DC line from 400/11kV Uddandapur LI SS to 132kV Balanagar SS 5)220kV Kosigi SS-2Nos. 6) 220kV Shadnagar SS 7)132kV SS Balanagar-2Nos. | The execution of 220/132kV features works were proposed at 400/11kV Uddandapur SS to meet the upcoming loads in the area and alternative 220kV lines to Kosigi SS & Shadnagar SS and alternative source to 132kV Balanagar SS. The proposed works are extension of 400/11kV Uddandapur SS. However, 400/11kV Uddandapur SS wokrs were abruptly delayed due to severe ROW issue and hence 220/132 kV features works will be takenup after completion of Substation works. | SI | T.O.O.(CE-PRLIS).MS.No.1776, dt:11.09.2023 | - | - | 452.48 | to be tie-up |  |  |  | April'2025 | March'2029 | - | - | - | - | 100 | 120 | 132.06 | 100.42 | 452.48 | to be taken up
III. Non-plan schemes taken up during 2025-26
Sub-total-III
Grans Total I + II + III
Note : Project Purpose : System Improvement (SI), System Expansion (SE), System Replacements (SR)/ RMI, Generation Evacuation (GE)
(*) - The Scheme cost includes Project cost,Over head charges and Development charges.
The statement to be printed on A3 size sheets please
0