## CapEx-23-24
TRANSMISSION CORPORATION OF TELANGANA LIMITED
Annual Petition for 2024-25 for Transmission Business filed with TGERC
Scheme-wise details of Capital Expenditure incurred in FY: 2023-24 of 4th control period
400kV Transmission Schemes : | [17 empty] | (figures in Crores)
Sl No. | Project Code / Scheme ID (SAP Code) | Project Title (SAP Project title) | Scope of work (Names of all the Sub-stations and Lines included in the scheme) | Project Purpose (SI/SE/ SR/GE) | Administrative Approval TOO Ref. | SRPC approval (if any) | TGERC Investment Approval Ref. | Total approved Cost (in Cr) | Source of funds |  |  |  | Project Start Date | Project Completion Date | DOC | Opening CWIP | Actual Expenditure from 01.04.2023 to 31.03.2024 | Cumulative expenditure upto 31.03.2024 | % Capatalisation | Remarks/ Balance works , if any. | Capitalizn during 2023-24 | Capitalizn up to 31.03.2023 | Total Capitalization up to 31.03.2024
[9 empty] | TGTransco Funds | Loan source | Loan Amount | Grants, if any | (DD-MM-YY) | (DD-MM-YY) |  | as on 31.03.2023
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
I. Ongoing Schemes as on 01.04.2023
1 | S-14-02 | Suryapet Power Transmission Scheme | 1) 400/220/132 kV Suryapet Substation 2) LILO of 400kV VTS – Malkaram DC Line to Suryapet 400kV SS 3) 400kV Kamavarapukota - Suryapet QMDC Line 4) 400kV Suryapet - Shankarapally QMDC Line | S I | 01/ 17.01.2014 49/ 04.12.2014 11/ 15.03.2016 | 36th & 39th SCPSPSR Meetings dtd. 04.09.2013 & 29.12.2015 respectively | APT/TS/ 400kV Suryapet/ F-INVST-28/2014 dt.21.01.2015 | 1738.03 | 420.76 | REC | 1317.27 | - | Sept., 2013 | Apr.' 2018 | - | 0.007 | 1.58 | 651.632 | 100% |  | 1.5803 | 650.045 | 651.6253 | TOO.(CE-Projects-I) Ms.No.11, dt.15.03.2016 | 0.007
2 | A-15-10, A-15-11 | 400kV Augmentation Scheme | Augmentation of 315 MVA PTRs at Dichpally & Mahaboobnagar and 500MVA ICT at Gajwel 400kV SS | S I | 20/ 29.08.2015 04/ 11.01.2017 49/ 28.03.2017 | 39th & 40th meetings of SCPSPSR dated 28-29.12.2015 & 19.11.2016 respectively | 03/17, 2017-18 dt.04.05.2017 | 95.59 | 15.75 | PFC | 79.84 | - | Feb' 2016 | May, 2018 | - | -0.003 | 0 | 45.288 | 100% |  | 0 | 45.291 | 45.291
3 | P-15-01 | Dindi System Improvement Scheme | 1) 400/220kV Dindi Substation 2) LILO of 400kV Srisailam – Mamidipally DC Line to 400kV Dindi SS | S I | 116/ 02.07.2015 08/ 19.01.2016 | 39th meeting of SCPSPSR dated 28-29.12.2015 | 16 / 15, Dt.02.01.2016 | 334.53 | 60.98 | REC | 273.55 |  | Dec.' 2016 | Dec.' 2017 | - | 0.011 | 0 | 153.838 | 99.99% |  | 0 | 153.827 | 153.827
4 | S-15-13 | 765kV Wardha– Hyderabad Link Transmission Scheme | 1) 400/220kV Maheshwaram; 2) 400kV QMDC Line from Maheshwaram 765/400kV (PGCIL) SS; 3) 400kV Maheswaram - Shankarapally TMDC Line; 4) 400/220/132kV Kethireddypalli SS; 5) LILO of 400kV Shankarpally-Suryapeta QMDC Line to 400kV Kethireddypalli SS; 6) 400kV QMDC line from 400kV Dichpally SS to 400kV Nirmal SS; 7) LILO of 400kV Dindi-Mamidipally TMDC Line to 400kV Maheshwaram SS | S I | 146/ 05.08.2015 30/ 04.10.2016 105/ 15.07.2017 | 36th & 37th SCPSPSR Meetings dtd. 04.09.2013 & 31.07.2014 respectively | 16/17-2017-18, Dt.19.12.2017 | 1178.97 | 177.32 | PFC | 1001.65 | - | Feb.' 2016 | Feb.' 2021 | - | 0 | 10.433 | 938.745 | 100% |  | 10.4333 | 928.312 | 938.7453
5 | P-16-01 | Telangana STPP-I Power Evacuation Scheme | 1) 400/220kV Ramadugu Substation 2) 400kV TSTPP (2x800MW) - Ramadugu QMDC Line; 3) 2) 400kV TSTPP (2x800MW) - Narsapur QMDC Line | G E | 34/ 25.11.2016 104/ 12.07.2017 | 40th & 41st Meetings of SCPSPSR dtd. 19.11.2016 & 22.09.2017 respectively | 10/2017, dt.23.08.2017 | 1151.6 | 20.43 | REC | 1131.17 |  | Oct' 2017 | Aug.' 2021 | - | 0.504 | 0 | 861.68 | 99.94% |  | 0 | 861.176 | 861.176
6 | S-17-08 | Rayadurg System Improvement Scheme | 1) 400/220/132KV GIS at Rayadurg 2) 400KV Kethireddypally - Rayadurg DC Line 3) LILO of 220kV Gachibowli – Shivarampally Line to Rayadurg GIS; 4) LILO of 220kV Gachibowli – Shapurnagar Line to Rayadurg GIS; 5) LILO of 220kV Gachibowli – Miyapur Line to Rayadurg GIS; 6) LILO of 220kV Gachibowli – Erragadda Line to Rayadurg GIS; 7) 132kV Rayadurg - Madhapur DC Line; 8) 132kV Rayadurg - Jubileehills DC Line; 9) LILO of 132kV Jubilee Hills – Shivarampally SC Line to Rayadurg | S I | 44/ 22.03.2017 79/ 13.04.2018 | 41st Meeting of SCPSPSR dated 22.09.2017 | 02 / 2018-19, Dt. 24.05.2018 | 1786.4 | 8.14 | PFC | 1778.26 | - | Sep' 2018 | Apr' 2022 | - | 9.787 | 12.741 | 1741.515 | 99.44% |  | 12.7407 | 1718.987 | 1731.7277
7 | S-19-01 | KTPP System Improvement Scheme | 400/220/132kV Substation at KTPP Switchyard, Bhupalapally | S I | 297/ 09.02.2019 | 1st Meeting of SRSCT dated 07.09.2018 | 03 / 2019-20 Dt. 22.11.2019 | 454.23 | 49.23 | PFC | 405 | - | Jan' 2020 | On-going | - | 121.702 | 49.124 | 170.826 | 0% | Works in progress | 0 | 0 | 0
8 | S-19-02 | Reactor Scheme-III | Installation of 125MVAR Bus Reactors at Suryapet, Rayadurg, Kethireddypalli, Narsapur, Maheshwaram, Janagaon and Dindi 400kV Substations and Installation of 80MVAR Bus Reactor & 63MVAR Switchable Line Reactors at Asupaka 400kV SS | S I | 304/ 23.02.2019 | 41st Meeting of SCPSPSR dated 22.09.2017 & 1st Meeting of SRSCT dated 07.09.2018 | 04 / 2019-20 Dt. 09.12.2019 | 249.79 | 91.07 | PSDF | 0 | 158.72 | Jan' 2020 | On-going | - | 45.192 | 84.498 | 133.319 | 36.37% | Balance works in progress | 44.8596 | 3.629 | 48.4886
9 | S-21-05 | HVWS for 500MVA ICTs at 400kV Substations | HVWS for 500MVA ICTs at 400kV Substations | S I | - | - | - | - | - | - | - | - | Dec' 2021 | May' 2022 | - |  | 0.048 | 0.853 | 100% |  | 0.0483 | 0.805 | 0.8533
10 | P-19-02 | Yadradri Thermal Power Evacuation Scheme | 1) 400/220kV Dameracherla SS; 2) 400kV YTPP Switchyard - Damaracherla QMDC Line; 3) 400kV YTPP Switchyard - Jangoan QMDC Line: and 4) 400/220/132kV Choutuppal SS; 5) LILO of 400kV Mamidipally-Khammam TMDC Line to Choutuppal SS; 6) 400kV YTPP Switchyard - Choutuppal QMDC Line; 7) 400kV YTPP Switchyard - Dindi QMDC Line | G E | 451/ 10.10.2019 | 39th meeting of SCPSPSR dated 28-29.12.2015 & 1st meeting of SRPCTP dt.16.12.19 | 09 / 2019-20, Dt. 27.01.2020 | 2354.35 | 141.44 | PFC & REC | 1102.26 & 1110.65 | - | Jan' 2020 | On-going | - | 869.414 | 180.251 | 1435.189 | 30.9% | Balance works in progress | 57.987 | 385.524 | 443.511
11 | A-21-07 | Augmentation Scheme-IV | Erection of 315/500 MVA ICT’s at 400kV Suryapet, Asupaka, Veltoor, Dichpally & Gajwel Sub-stations | S I | 1311/ 14.02.2022; 1530/ 03.12.2022 | 41st Meeting of SCPSPSR dated 22.09.2017 CEA Lr. Dt. 10.12.2021 | 01 / 2022-23 Dt.05.05.2022 01 / 2024-25 Dt.17.05.2024 | 187.48 | 19.18 | HUDCO | 168.3 | - | Dec.' 2020 | On-going | - | 73.191 | 53.524 | 126.715 | 98.99% | Balance works in progress | 125.4413 | 0 | 125.4413
12 | P-07-01 | Erec Bay Exte @ Malkaram 400kV SS | ERE BAY EXTE@ MALKARAM 400 KV SS | S I | - | - | - | - | - | - | - | - | - | - | - | 0 | 0.061 | 0.061 | - | - | 0.0607 |  | 0.0607
Sub-total-I | [15 empty] | 1119.805 | 392.26 | 6259.661 |  |  | 253.1512 | 4747.596 | 5000.7472
II. New schemes taken up during 2023-24 : - NIL -
Sub-total-II
III. Non-plan schemes taken up during 2023-24
1 | D-15-09 | 2Nos 400kV BE - 400kV Dichpally SS | 2Nos 400kV BE - 400kV Dichpally SS | S I | - | - | - | - | 100% Consumer Contribution |  |  | - | Feb., 2016 | Feb., 2017 | - | 0 | -0.0017 | 16.5783 | 100% | - | -0.0017 | 16.58 | 16.5783
2 | D-20-03 | Diversion of 400kV Julurupadu-KTPS & KTPS-PGCIL Line) | Diversion of 400kV Julurupadu-KTPS & KTPS-PGCIL Line) (D-20-03) | DC Works | - | - | - | - | 100% Consumer Contribution |  |  |  | Aug., 2020 | Aug., 2021 | - | 0 | 0.4339 | 22.3529 | 100% | - | 0.43385 | 21.919 | 22.3529
3 | N-22-01 | Non Plan Capital Works Exe by Const wing | Survey for Shifting Towers of BTPS to Julurupadu 400kV Line (For Sitamma Sagar Multi Purpose Project) | DC Works | - | - | - | - | I&CAD, Govt.of TG |  |  | - | - | - | - | - | 0.0408 | 0.0408 | - | - | 0 |  | 0
Sub-Total-III | [15 empty] | 0 | 0.473 | 38.972
Grans Total I + II + III | [15 empty] | 1119.805 | 392.733 | 6298.633
Chief Engineer/ 400kV
Note : Project Purpose : System Improvement (SI), System Expansion (SE), System Replacements (SR)/ RMI, Generation Evacuation (GE)
The statement to be printed on A3 size sheets please
Note on I13: DELL: Excluding IDC of Rs.100.08 Crore Total incl. IDC Rs.1279.05

## Caplzn 23-24
TRANSMISSION CORPORATION OF TELANGANA LIMITED
Annual Petition for 2024-25 for Transmission Business filed with TGERC
Scheme wise details of Actual Capitalisation for FY 2023-24
400kV Transmission Schemes: | [26 empty] | (Figures in Rs Crore)
[9 empty] | Work Period | [5 empty] | Source of Funds | [7 empty] | Additions to Network
Sl No. | Voltage Level | Project Code (SAP Code) / Scheme IDs | Project Title (SAP Project title) | Scope of work (Names of all the Sub-stations and Lines included in the Scheme) | Project Purpose (SI/SE/SR/GE) | Administrative approval No. with date | SRPC approval no with date (if any) | Investment Approval No. with Date | Start Date |  | Completion Date (Charging date) |  | Date of Capitalization | Approved Cost as per Investment Approval | Transco Funds | Loan Source | Loan Amount | Grants, if any | Capitalisation Upto Previous Year (n-1) (as per Audited Financial Statements) | Capital Expenditure during the current year (2023-24) | Capitalisation claimed for the Current year (2023-24) | Whether Part Capitalization or Full Capitalisation | Sub-stations (Nos) | Lines (CKM) | PTR (MVA) | Bays (Nos) | Physical Completion Certificate Nos. | Financial Completion Certificate Nos. | Remarks / Reasons for Cost & Time overruns (if any)
[9 empty] | Schedule | Actual | Schedule | Actual
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
I. Ongoing Schemes as on 01.04.2023
1 | 400kV | S-14-02 | Suryapet Power Transmission Scheme | 1) 400/220/132 kV Suryapet Substation 2) LILO of 400kV VTS – Malkaram DC Line to Suryapet 400kV SS 3) 400kV Kamavarapukota - Suryapet QMDC Line 4) 400kV Suryapet - Shankarapally QMDC Line | S I | 01 / 17.01.2014 49/ 04.12.2014 11/ 15.03.2016 | 36th & 39th SCPSPSR Meetings dtd. 04.09.2013 & 29.12.2015 respectively | APT/TS/ 400kV Suryapet/ F-INVST-28/2014 dt.21.01.2015 | July 2013 | Sept' 2013 | Mar' 2017 | Apr. 2018 | - | 1738.03 | 420.76 | REC | 1317.27 | - | 650.045 | 1.58 | 1.58 | Part | - | - | - | -
2 | 400kV | S-15-13 | 765kV Wardha– Hyderabad Link Transmission Scheme | 1) 400/220kV Maheshwaram SS; 2) 400kV QMDC Line from Maheshwaram 765/400kV (PGCIL) SS; 3) 400kV Maheswaram - Shankarapally TMDC Line; 4) 400/220/132kV Kethireddypalli SS; 5) LILO of 400kV Shankarpally-Suryapeta QMDC Line to 400kV Kethireddypalli SS; 6) 400kV Dichpally - Nirmal QMDC Line; 7) LILO of 400kV Dindi-Mamidipally TMDC Line to 400kV Maheshwaram SS | S I | 146/ 05.08.2015 30/ 04.10.2016 105/ 15.07.2015 | 36th & 37th SCPSPSR Meetings dtd. 04.09.2013 & 31.07.2014 respectively | 10/15, Dt.11.11.2015 & 16/17-2017-18, Dt.19.12.2017 | Jan. 2016 | Feb. 2016 | Mar' 2019 | Feb' 2021 | - | 1178.97 | 177.32 | PFC | 1001.65 | - | 928.312 | 10.433 | 10.433 | Part | - | - | - | - | 2019000040 2019000043 | 202001469 202000157
3 | 400kV | S-17-08 | Rayadurg System Improvement Scheme | 1) 400/220/132KV GIS at Rayadurg, 2) 400KV Kethireddypally - Rayadurg DC Line 3) LILO of 220kV Gachibowli – Shivarampally Line to Rayadurg GIS; 4) LILO of 220kV Gachibowli – Shapurnagar Line to Rayadurg GIS; 5) LILO of 220kV Gachibowli – Miyapur Line to Rayadurg GIS; 6) LILO of 220kV Gachibowli – Erragadda Line to Rayadurg GIS; 7) 132kV Rayadurg - Madhapur DC Line; 8) 132kV Rayadurg - Jubileehills DC Line; 9) LILO of 132kV Jubilee Hills – Shivarampally SC Line to Rayadurg | S I | 44/ 22.03.2017; 79/ 13.04.2018 | 41st Meeting of SCPSPSR dated 22.09.2017 | 02 / 2018-19, Dt. 24.05.2018 | May 2018 | Sep' 2018 | May 2020 | Apr' 2022 | - | 1786.4 | 8.14 | PFC | 1778.26 | - | 1718.987 | 12.741 | 12.741 | Part | - | - | - | - | 2022000181 2022000129 2022000120 2022000085 | 202200168 2024000692 202200172 2023000609
4 | 400kV | S-19-02 | Reactor Scheme-III | Installation of 125MVAR Bus Reactors at Suryapet, Rayadurg, Kethireddypalli, Narsapur, Maheshwaram, Janagaon and Dindi 400kV Substations and Installation of 80MVAR Bus Reactor & 63MVAR Switchable Line Reactors at Asupaka 400kV SS | S I | 304/ 23.02.2019 | 41st Meeting of SCPSPSR dated 22.09.2017 & 1st Meeting of SRSCT dated 07.09.2018 | 04 / 2019-20 Dt. 09.12.2019 | Jan' 2020 | Jan' 2020 | March, 2023 | On-going | - | 249.79 | 91.07 | PSDF | 0 | 158.72 | 3.629 | 84.498 | 44.86 | Part | 0 | 0 | 0 | 4 | 2023001149 2023001150 2023001176 | 2024000694 2023000712 2024000514
5 | 400kV | P-19-02 | Yadradri Thermal Power Evacuation Scheme | 1) 400/220kV Dameracherla SS; 2) 400kV YTPP Switchyard - Damaracherla QMDC Line; 3) 400kV YTPP Switchyard - Jangoan QMDC Line: and 4) 400/220/132kV Choutuppal SS; 5) LILO of 400kV Mamidipally-Khammam TMDC Line to Choutuppal SS; 6) 400kV YTPP Switchyard - Choutuppal QMDC Line; 7) 400kV YTPP Switchyard - Dindi QMDC Line | G E | 451/ 10.10.2019 | 39th meeting of SCPSPSR dated 28-29.12.2015 & 1st meeting of SRPCTP dt.16.12.19 | 09 / 2019-20, Dt. 27.01.2020 | Jan' 2020 | Dec' 2021 | May, 2022 | On-going | - | 2354.35 | 141.44 | PFC & REC | 1102.26 1110.65 | - | 385.24 | 180.251 | 57.987 | Part | 0 | 0 | 820 | 11 | 2023001136 2023001134 2023001261 2023001148 2023000422 2023001151 | 2023000711 2023000712 2024000749 2023000663 2023000674 2023000671
6 | 400kV | A-21-07 | Augmentation Scheme-IV | Erection of 315/500 MVA ICT’s at 400kV Suryapet, Asupaka, Veltoor, Dichpally & Gajwel Sub-stations | S I | 1311/ 14.02.2022; 1530/ 03.12.2022 | 41st Meeting of SCPSPSR dated 22.09.2017 CEA Lr. Dt. 10.12.2021 | 01 / 2022-23 Dt.05.05.2022 01 / 2024-25 Dt.17.05.2024 | Dec.' 2020 | Aug., 2022 | Sept., 2023 | On-going | - | 187.48 | 19.18 | HUDCO | 168.3 | - | 0 | 53.524 | 125.441 | Part | 0 | 0 | 1185 | 4 | 2023001263 2023001175 2024000129 | 2024000748 2024000742 2024000515
7 | 400kV | S-21-05 | HVWS for 500MVA ICTs at 400kV Substations | HVWS for 500MVA ICTs at 400kV Substations | S I | - | - | - | - | Dec' 2021 | - | May' 2022 | - | - | - | - | - | - | 0.805 | 0.048 | 0.048 | Part | - | - | - | - | 2023000448 2023000445 2023000444 | 2023000713 2023000618 2023000697
8 | 400kV | P-07-01 | Erec Bay Exte @ Malkaram 400kV SS | ERE BAY EXTE@ MALKARAM 400 KV SS | S I | - | - | - | - |  | - |  | - | - | - | - | - | - | 0 | 0.061 | 0.061 | Part | - | - | - | -
Sub-Total-I : | [18 empty] | 3687.018 | 343.136 | 253.151 |  | 0 | 0 | 2005 | 19
II. New schemes taken up during 2023-24 : - Nil -
Sub-total-II
III. Non-plan schemes taken up during 2023-24
1 | 400kV | D-15-09 | 2Nos 400kV BE - 400kV Dichpally SS | 2Nos 400kV BE - 400kV Dichpally SS | S I | - | - | - | - | Feb., 2016 | - | Feb., 2017 | - | 100% Consumer Contribution |  |  |  | - | 16.58 | -0.0017 | -0.002 | Part | - | - | - | -
2 | 400kV | D-20-03 | Diversion of 400kV Julurupadu-KTPS & KTPS-PGCIL Line) | Diversion of 400kV Julurupadu-KTPS & KTPS-PGCIL Line) | DC Works | - | - | - | - | Aug' 2020 | - | Aug' 2021 | 16.10.21 | 100% Consumer Contribution |  |  |  | - | 21.919 | 0.4339 | 0.434 | Part | - | - | - | - | 2022000288 2022000291 | 202200154 202200155
Sub-total-III | [18 empty] | 38.499 | 0.4322 | 0.432
Grans Total I + II + III | [18 empty] | 3725.517 | 343.5682 | 253.583 |  | 0 | 0 | 2005 | 19
Chief Engineer/ 400kV
Note : Project Purpose : System Improvement (SI), System Expansion (SE), System Replacements (SR)/ RMI, Generation Evacuation (GE)
The statement to be printed on A3 size sheets please
Note on O12: DELL: Excluding IDC of Rs.100.08 Crore Total incl. IDC Rs.1279.05
Note on AA15: Dindi - 2 bays CTPL - 220kV -3 Ctpl - 132kV - 6

## CapEx 25-26
TRANSMISSION CORPORATION OF TELANGANA LIMITED
Annual Petition for 2024-25 for Transmission Business filed with TGERC
Scheme wise details of Capital Expenditure proposed for Financial Year 2025-26
400kV Transmission Schemes :
Sl No. | Project Code / Scheme ID (SAP Code) | Project Title (SAP Project title) | Scope of work (Names of all the Sub-stations and Lines included in the scheme maybe given) | Justification | Project Purpose (SI/SE/SR/GE) | Administrative Approval TOO Ref. | SRPC approval (if any) | TGERC Investment Approval Ref. | Total TGERC approved Cost (in Cr) | Source of funds |  |  |  | Proposed Project Start Date DD-MM-YY | Proposed Project Completion Date DD-MM-YY | CWIP O.B. | FY:2024-25 |  |  | Projected expenditure for 2025-26 | Spill over Yearly Capital Expenditure projected for works taken up in or before 2025-26 (in Cr) |  |  | Total Cumulative Expenditure (in Cr) | Present Status of work
[10 empty] | TGTransco funds | Loan source | Loan Amount | Grants, if any |  |  |  | 1st Half (Apr-Sept) (Actuals) | 2nd Half (Oct-Mar) (Projected) | Total 24-25 (Projected) |  | 2026-27 | 2027-28 | 2028-29
1 | 2 | 3 | 4 |  | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 |  |  |  | 17 | 18 | 19 | 20 | 21 | 22
I. Ongoing Schemes as on 01.04.2025 (Investment approval accorded by Hon'ble TGERC)
1 | S-14-02 | Suryapet Power Transmission Scheme | 1) 400/220/132 kV Suryapet Substation 2) LILO of 400kV VTS – Malkaram DC Line to Suryapet 400kV SS 3) 400kV Kamavarapukota - Suryapet QMDC Line 4) 400kV Suryapet - Shankarapally QMDC Line | All the works were Commissioned. | S I | 01/ 17.01.2014 49/ 04.12.2014 11/ 15.03.2016 | 36th & 39th SCPSPSR Meetings dtd. 04.09.2013 & 29.12.2015 respectively | APT/TS/ 400kV Suryapet/ F-INVST-28/2014 dt.21.01.2015 | 1738.03 | 420.76 | REC | 1317.27 | - | Sept., 2013 | Apr.' 2018 | 0.007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 651.632 | 0
2 | A-15-10, A-15-11 | 400kV Augmentation Scheme | Augmentation of 315 MVA PTRs at Dichpally & Mahaboobnagar and 500MVA ICT at Gajwel 400kV SS | All the works were Commissioned. | S I | 20/ 29.08.2015 04/ 11.01.2017 49/ 28.03.2017 | 39th & 40th meetings of SCPSPSR dated 28-29.12.2015 & 19.11.2016 respectively | 03/17, 2017-18 dt.04.05.2017 | 95.59 | 15.75 | PFC | 79.84 | - | Feb' 2016 | May, 2018 | -0.003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45.288 | 0
3 | S-15-13 | 765kV Wardha– Hyderabad Link Transmission Scheme | 1) 400/220kV Maheshwaram; 2) 400kV QMDC Line from Maheshwaram 765/400kV (PGCIL) SS; 3) 400kV Maheswaram - Shankarapally TMDC Line; 4) 400/220/132kV Kethireddypalli SS; 5) LILO of 400kV Shankarpally-Suryapeta QMDC Line to 400kV Kethireddypalli SS; 6) 400kV QMDC line from 400kV Dichpally SS to 400kV Nirmal SS; 7) LILO of 400kV Dindi-Mamidipally TMDC Line to 400kV Maheshwaram SS | All the works were Commissioned. | S I | 146/ 05.08.2015 30/ 04.10.2016 105/ 15.07.2017 | 36th & 37th SCPSPSR Meetings dtd. 04.09.2013 & 31.07.2014 respectively | 10/15, Dt.11.11.2015 & 16/17-2017-18, Dt.19.12.2017 | 1178.97 | 177.32 | PFC | 1001.65 | - | Feb. 2016 | Feb' 2021 | 0.051 | -4.7977 | 10 | 5.2023 | 0 | 0 | 0 | 0 | 943.9473 | 0
4 | P-16-01 | Telangana STPP-I Power Evacuation Scheme | 1) 400/220kV Ramadugu Substation; 2) 400kV TSTPP (2x800MW) - Ramadugu QMDC Line; 3) 2) 400kV TSTPP (2x800MW) - Narsapur QMDC Line | All the works were Commissioned. | G E | 34/ 25.11.2016 104/ 12.07.2017 | 40th & 41st Meetings of SCPSPSR dtd. 19.11.2016 & 22.09.2017 respectively | 10/2017, dt.23.08.2017 | 1151.6 | 20.43 | REC | 1131.17 | - | Oct' 2017 | Aug.' 2021 | 0.502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 861.68 | 0
2 | S-17-08 | Rayadurg System Improvement Scheme | 1) 400/220/132KV GIS at Rayadurg 2) 400KV Kethireddypally - Rayadurg DC Line 3) LILO of 220kV Gachibowli – Shivarampally Line to Rayadurg GIS; 4) LILO of 220kV Gachibowli – Shapurnagar Line to Rayadurg GIS; 5) LILO of 220kV Gachibowli – Miyapur Line to Rayadurg GIS; 6) LILO of 220kV Gachibowli – Erragadda Line to Rayadurg GIS; 7) 132kV Rayadurg - Madhapur DC Line; 8) 132kV Rayadurg - Jubileehills DC Line; 9) LILO of 132kV Jubilee Hills – Shivarampally SC Line to Rayadurg | All the works were Commissioned. | S I | 44/ 22.03.2017 79/ 13.04.2018 | 41st Meeting of SCPSPSR dated 22.09.2017 | 02 / 2018-19, Dt. 24.05.2018 | 1786.4 | 8.14 | PFC | 1778.26 | - | Sep' 2018 | Apr' 2022 | 10.447 | 0.13598 | 16.864 | 17 | 0 | 0 | 0 | 0 | 1758.515 | 0
3 | P-19-02 | Yadradri Thermal Power Evacuation Scheme | 1) 400/220kV Dameracherla SS; 2) 400/220/132kV Choutuppal SS; 3) 400kV YTPPS - Damaracherla QMDC Line; 4) LILO of 400kV Mamidipally-Khammam TMDC Line to Choutuppal SS; 5) 400kV YTPP Switchyard - Dindi QMDC Line; 6) 400kV YTPP Switchyard - Choutuppal QMDC Line; 7) 400kV YTPP Switchyard - Jangoan QMDC Line: | The investment approval received on 27.01.2020, as mentioned in Column (8), TGERC details. 400kV YTPP Switchyard - Dindi QMDC Line, 400kV YTPP Switchyard - Choutuppal QMDC Line and 400kV YTPP Switchyard - Jangoan QMDC Line are proposed in 4th CP. However, the 400kV YTPP Switchyard - Dindi QMDC Line (103.738 Ckm) charged on 12.06.2024.The remaining lines ,Choutuppal (184.754 Ckm) and Jangaon (278 CKM )are expected in March 2025 and Dec 2025 respectively. | G E | 451/ 10.10.2019 | 39th meeting of SCPSPSR dated 28-29.12.2015 & 1st meeting of SRPCTP dt.16.12.19 | 09 / 2019-20, Dt. 27.01.2020 | 2354.35 | 141.44 | PFC & REC | 1102.26 & 1110.65 | - | Jan' 2020 | Dec., 2025 | 991.677 | -0.265 | 100 | 99.735 | 200 | 30 | 0 | 0 | 1764.915 | Works of Items-6 & 7 400kV Lines to Choutuppal & Jangaon are under progress and expected to be charged by March & Dec., 2025 respectively | 1435.18
4 | S-19-02 | Reactor Scheme-III | Installation of 125MVAR Bus Reactors at Suryapet, Rayadurg, Kethireddypalli, Narsapur, Maheshwaram, Janagaon and Dindi 400kV Substations and Installation of 80MVAR Bus Reactor & 63MVAR Switchable Line Reactors at Asupaka 400kV SS | Proposed in 4th CP. However, all the works are Commissioned by December 2024.. | S I | 304/ 23.02.2019 | 41st Meeting of SCPSPSR dated 22.09.2017 & 1st Meeting of SRSCT dated 07.09.2018 | 04 / 2019-20; Dt. 09.12.2019 | 249.79 | 249.79 | PSDF | 0 | 158.72 | Jan' 2020 | Dec'24 | 93.48 | 4.053 | 50 | 54.053 | 11.627 | 0 | 0 | 0 | 198.999 | -
5 | A-21-07 | Augmentation Scheme-IV | Erection of 315/500 MVA ICT’s at 400kV Suryapet, Asupaka, Veltoor, Dichpally & Gajwel Sub-stations | All the works are Commissioned. | S I | 1311/ 14.02.2022; 1530/ 03.12.2022 | 41st Meeting of SCPSPSR dated 22.09.2017 CEA Lr. Dt. 10.12.2021 | 01 / 2022-23 Dt.05.05.2022; 01 / 2024-25 Dt.17.05.2024 | 187.48 | 19.18 | HUDCO | 168.3 | - | Dec.' 2020 | Oct'24 | 1.273 | 0.3 | 25.905 | 26.205 | 0 | 0 | 0 | 0 | 152.92 | -
6 | S-21-05 | HVWS for 500MVA ICTs at 400kV Substations | HVWS for 500MVA ICTs at 400kV Substations | All works commissioned by June 2022. | S I | - | - | - | - | - | - | - | - | Dec' 2021 | May' 2022 | 0.0098 | 0.0098 | 0 | 0.0098 | 0 | 0 | 0 | 0 | 0.8628 | -
7 | S-19-01 | KTPP System Improvement Scheme | 400/220/132kV Substation at KTPP Switchyard, Bhupalapally | The investment approval received on 27.01.2020, as mentioned in Column (8), TGERC details. The Substation is proposed in 4th CP. Ready for charging. | S I | 297/ 09.02.2019 | 1st Meeting of SRSCT dated 07.09.2018 | 03 / 2019-20 Dt. 22.11.2019 | 454.23 | 49.23 | PFC | 405 | - | Jan' 2020 | March, 2025 | 170.826 | 6.093 | 33.081 | 39.174 | 10 | 6 | 0 | 0 | 226 | Works in Progress
Sub-total-I |  |  |  |  | Grants, if any 16: 1268.2658 | 5.5291 | 235.85 | 241.3791 | 221.627 | 36 | 0 | 0
II. New schemes taken up during 2025-26
1 | - | Augmentation Scheme-V | Augmentation of 500MVA, 400/220 kV Auto Transformers, 1 No. each at 400kV Raidurg, Kethireddupally & Maheswaram SSs | New Scheme: Considering the Hyderabad City growth and future laod growth in GHMC, the Augmentation of ICT capacities in the existing Substations is proposed in 5th CP. | S I | To be issued | CEA Lr.dt. 07.10.2024 (Raidurg SS) | - | - | - | - | - | - | April, 2025 | June, 2026 | 0 | 0 | 0 | 0 | 86 | 64 | 0 | 0 | 150 | Scheme is under formulation
2 | - | 400/220 kV Kandi GI Substation and connected Lines | 1) 400/220kV Kandi G I Substation 2) LILO of 400kV Shankarpally-Narsapur TMDC Line to 400/220kV Kandi G I S | New Scheme: To meet the expected/projected state peak demand , the said transmission network is proposed and the scheme is under formulation with tentative scope of works mentioned in column (4), Scope of Work. The details as per clause 7.6 of Regulation 2 od 2023, will be submiited , on approval of the scheme by CEA/SRPC(i.e Voltage -wise MVA and Ckm detalis) | S I | To be issued | - | - | - | - | - | - | - | June, 2025 | Dec., 2027 | 0 | 0 | 0 | 0 | 108 | 216 | 36 | 0 | 360 | Scheme is under formulation
3 | - | 400/220kV Shadnagar GI Substation and connected Lines | 1) 400/220kV Shadnagar G I Substation 2) LILO of one circuit of Maheshwaram-Shankarpally 400kV TMDC Line to 400/220kV Shadnagar G I S |  | S I | To be issued | - | - | - | - | - | - | - | June, 2025 | Dec., 2027 | 0 | 0 | 0 | 0 | 120 | 240 | 40 | 0 | 400 | Scheme is under formulation
Sub-Total-II : |  |  |  |  | Grants, if any 16: 0 | 0 | 0 | 0 | 314 | 520 | 76 | 0 | 910
III. Non-plan schemes taken up during 2025-26 (Will be taken up on payment of amonuts by Third parties)
1 | N-22-01 | Non Plan Capital works for FY 2022-23 | Non Plan Capital works for FY 2022-23 |  | - | - | - | - | - | - | - | - | - | - | - | 0.041 | - | - | 0 | - | - | - | - | -
2 | N-23-01 | Non Plan Capital works Exe by Const wing | Laying- CC road NH 365B to 400Jangaon SS | Completed in November 2024. | [12 empty] | 0.286 | - | 0.286 | - | - | - | - | 0.286 | bar: 5 to TGTransco funds 10; Grants, if any 14 to Grants, if any 16
3 | DC Work | 400kV GIS at CTRLS Data Cetnre and connected Line | 1) 400kV G I Switching-station at CTRLS Data Centre; 2) LILO of one Ckt. of 400kV Maheswaram - Shankarapally TMDC Line | New Proposal received on 10.05. 2024 and submitted the proposal in 5th CP. | S E | To be issued | - | - | - | Depository Contribution Work (Consumer Contribution) |  |  |  | June, 2025 | March, 2027 | 0 | 0 | 0 | 0 | 87.2 | 130.8 | 0 | 0 | 218 | Scheme is under formulation
5 | Z-99-01 | Rolling Stocks Procurement N Consumption | Rolling Stocks Procurement N Consumption | - | - | - | - | - | - | - |  |  |  | - | - | 0.018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | DC Work | Integrated Steel Plant Transmission Scheme* | 1) 400/220kV Integrated Steel Plant SS in Khammam Dist. 2) 400kV Julurupadu - Integrated Steel Plant QMDC Line, and associated 400kV Bays | Already approved vide 29.12.2023 Resource Plan for 5th CP. | S E | To be issued | - | - | - | Depository Contribution Work (Consumer Contribution) |  |  |  | July, 2025 | March, 2028 | 0 | 0 | 0 | 0 | 43.601 | 218.005 | 174.404 | 0 | 436.01 | State Govt. approval for Integrated Steel Plant is yet to be received *.
Sub-total-III |  |  |  |  | Grants, if any 16: 0.059 | 0.286 | 0 | 0.286 | 130.801 | 348.805 | 174.404 | 0 | 654.01
Grans Total I + II + III |  |  |  |  | Grants, if any 16: 1268.3248 | 5.8151 | 235.85 | 241.6651 | 666.428 | 904.805 | 250.404 | 0 | 1564.01
Note :* As per AP Re-Organization Act 2014, Telangana State was assured for establishment of Integrated Steel Plant. In this connection, Mines Department, Telangana requested to furnish the feasibility report for construction of SS& lines for the three sites proposed by M/s. MECON Limited, (Engineering and Consultancy Services). Accordingly TSTRANSCO has submitted detailed report for providing power supply to proposed Integrated Steel Plant vide Letter dated 27.06.2018. No further correspondence received from Govt. of Telangana regarding extension of power supply to proposed steel plant. This Integrated Steel Plant Transmission Scheme will be taken up only after finalization of steel plant site and also based on the System Studies Report, to extend the power supply to proposed steel plant.
CHIEF ENGINEER/400KV
Chief Engineer/ 400kV
Note : Project Purpose : System Improvement (SI), System Expansion (SE), System Replacements (SR)/ RMI, Generation Evacuation (GE)
The statement to be printed on A3 size sheets please
1 | S-17-08 | Rayadurg System Improvement Scheme | 1) 400/220/132KV GIS at Rayadurg 2) 400KV Kethireddypally - Rayadurg DC Line 3) LILO of 220kV Gachibowli – Shivarampally Line to Rayadurg GIS; 4) LILO of 220kV Gachibowli – Shapurnagar Line to Rayadurg GIS; 5) LILO of 220kV Gachibowli – Miyapur Line to Rayadurg GIS; 6) LILO of 220kV Gachibowli – Erragadda Line to Rayadurg GIS; 7) 132kV Rayadurg - Madhapur DC Line; 8) 132kV Rayadurg - Jubileehills DC Line; 9) LILO of 132kV Jubilee Hills – Shivarampally SC Line to Rayadurg |  | S I | 44/ 22.03.2017 79/ 13.04.2018 | 41st Meeting of SCPSPSR dated 22.09.2017 | 02 / 2018-19, Dt. 24.05.2018 | 1786.4 | 8.14 | PFC | 1778.26 | - | Sep' 2018 | Apr' 2022 |  | 0.136
| S-19-02 | Reactor Scheme-III | Installation of 125MVAR Bus Reactors at Suryapet, Rayadurg, Kethireddypalli, Narsapur, Maheshwaram, Janagaon and Dindi 400kV Substations and Installation of 80MVAR Bus Reactor & 63MVAR Switchable Line Reactors at Asupaka 400kV SS |  | S I | 304/ 23.02.2019 | 41st Meeting of SCPSPSR dated 22.09.2017 & 1st Meeting of SRSCT dated 07.09.2018 | 04 / 2019-20 Dt. 09.12.2019 | 249.79 | 91.07 | PSDF | 0 | 158.72 | Jan' 2020 | Mar' 2023 |  | 4.053
| A-21-07 | Augmentation Scheme-IV | Erection of 315/500 MVA ICT’s at 400kV Suryapet, Asupaka, Veltoor, Dichpally & Gajwel Sub-stations |  | S I | 1311/ 14.02.2022 | CEA Lr. Dated 10.12.2021 | 01 / 2022-23 Dt.05.05.2022 01 / 2024-25 Dt.17.05.2024 | 187.48 | 19.18 | HUDCO | 168.3 | - |  |  |  | 0.3
| S-21-05 | HVWS for 500MVA ICTs at 400kV Substations | HVWS for 500MVA ICTs at 400kV Substations |  | S I | - | - | - | - | - | - | - | - | Dec' 2021 | May' 2022 |  | 0.01
| S-15-13 | 765kV Wardha– Hyderabad Link Transmission Scheme | 1) 400/220kV Maheshwaram; 2) 400kV QMDC Line from Maheshwaram 765/400kV (PGCIL) SS; 3) 400kV Maheswaram - Shankarapally TMDC Line; 4) 400/220/132kV Kethireddypalli SS; 5) LILO of 400kV Shankarpally-Suryapeta QMDC Line to 400kV Kethireddy-palli SS; 6) 400kV QMDC line from 400kV Dichpally SS to 400kV Nirmal SS; 7) LILO of 400kV Dindi-Mamidipally TMDC Line to 400kV Maheshwaram SS |  | S I | 146/ 05.08.2015 30/ 04.10.2016 105/ 15.07.2017 | 36th & 37th SCPSPSR Meetings dtd. 04.09.2013 & 31.07.2014 respectively | 16/17-2017-18, Dt.19.12.2017 | 1178.97 | 177.32 | PFC | 1001.65 | - | Nov' 2015 | Mar' 2022 |  | -4.798
Note on J11: DELL: Excluding IDC of Rs.100.08 Crore Total incl. IDC Rs.1279.05
Note on J53: DELL: Excluding IDC of Rs.100.08 Crore Total incl. IDC Rs.1279.05

## CpX-Lis 23-24
TRANSMISSION CORPORATION OF TELANGANA LIMITED
Annual Petition for 2024-25 for Transmission Business filed with TGERC
Scheme-wise details of Capital Expenditure incurred in FY: 2023-24 of 4th control period
400kV Lift Irrigaiton Transmission Schemes : | [17 empty] | (figures in Crores)
Sl No. | Project Code / Scheme ID (SAP Code) | Project Title (SAP Project title) | Scope of work (Names of all the Sub-stations and Lines included in the scheme) | Project Purpose (SI/SE/SR/GE) | Administrative Approval TOO Ref. | SRPC approval (if any) | TGERC Investment Approval Ref. | Total approved Cost (in Cr) | Source of funds |  |  |  | Project Start Date (DD-MM-YY) | Project Completion Date (DD-MM-YY) | DOC | Opening CWIP as on 31.03.2023 | Actual Expenditure from 01.04.2023 to 31.03.2024 | Cumulative expenditure upto 31.03.2024 | % Capatalisation | Remarks / Balance works , if any.
[9 empty] | TGTransco Funds | Loan source | Loan Amount | Grants, if any
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
1 | L-13-01 | Indira Sagar Rudrammakota LI scheme | 1) 400/220kV Asupaka SS 2) 400kV LILO of one ckt of Kalpaka (Vizag) - Khammam 400kV DC line to Asupaka 400/220kV SS | DC Works | 127 / 16.09.2019 | 41st Meeting of SCPSPSR dated 22.09.2017 | - | - | I&CAD, Govt.of TG Funds |  |  |  | Mar' 2014 | Aug' 2017 | 10.08.2017 | 0 | 0.099 | 109.289 | 100% | - | -
2 | L-18-04 | Sita Rama Lift Irrigaiton Scheme | 1) 400/220/11kV Kamalapuram LI SS, 2) 220/11kV B.G.Kothur LI SS, 3) 220/11kV V.K.Ramavaram LI SS, 3) 400kV Julurupadu - Kamalapuram TMDC Line, 4) LILO of one circuit of 220kV KTPS-Manuguru Line to B.G.Kothur, 5) LILO of one circuit of 220kV KTPS V-Lower Sileru -II Line to B.G.Kothur, 6) LILO of 220kV KTS – Lower Sileru-I Line at 400/220 kV Asupaka SS, 7) LILO of 220kV KTS - Asupaka Line to 220kV V.K.Ramavaram LI SS, 8) 220kV TMDC Line from 400/220/11kV Kamalapuram SS to 220/11 kV V.K.Ramavaram | Bulk Load & DC Works | 449 & 450 Dated 10.10.2019 | 41st Meeting of SCPSPSR dated 22.09.2017 | - | - | I&CAD, Govt.of TG Funds |  |  |  | Sep' 2018 | May, 2023 | 28.04.23 | 58.688 | -0.27 | 322.138 | 95.91% | - | -
Total : | [15 empty] | 58.688 | -0.171 | 431.427
Chief Engineer/ 400kV
Note : Project Purpose : System Improvement (SI), System Expansion (SE), System Replacements (SR)/ RMI, Generation Evacuation (GE)
The statement to be printed on A3 size sheets please

## Caplzn-Lis
TRANSMISSION CORPORATION OF TELANGANA LIMITED
Annual Petition for 2024-25 for Transmission Business filed with TGERC
Scheme wise details of Actual Capitalisation for FY 2023-24
400kV Lift Irrigaiton Schemes: | [26 empty] | (Figures in Rs Crore)
[9 empty] | Work Period | [5 empty] | Source of Funds | [7 empty] | Additions to Network
Sl No. | Voltage Level | Project Code (SAP Code) / Scheme IDs | Project Title (SAP Project title) | Scope of work (Names of all the Sub-stations and Lines included in the Scheme) | Project Purpose (SI/SE/SR/GE) | Administrative approval No. with date | SRPC approval no with date (if any) | Investment Approval No. with Date | Start Date |  | Completion Date (Charging date) |  | Date of Capitalization | Approved Cost as per Investment Approval | Transco Funds | Loan Source | Loan Amount | Grants, if any | Capitalisation Upto Previous Year (n-1) (as per Audited Financial Statements) | Capital Expenditure during the current year (2023-24) | Capitalisation claimed for the Current year (2023-24) | Whether Part Capitalization or Full Capitalisation | Sub-stations (Nos) | Lines (CKM) | PTR (MVA) | Bays (Nos) | Physical Completion Certificate Nos. | Financial Completion Certificate Nos. | Remarks / Reasons for Cost & Time overruns (if any)
[9 empty] | Schedule | Actual | Schedule | Actual
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
I. Ongoing Schemes as on 01.04.2023
1 | 400kV | L-13-01 | Indira Sagar Rudrammakota LI scheme | Indira Sagar Rudrammakota LI scheme | Bulk & DC Works | 127 / 16.09.2019 | 41st Meeting of SCPSPSR dated 22.09.2017 | N/A | - | Mar' 2014 | - | Aug' 2017 | 16.09.2017 | 100% Consumer Contribution |  |  |  | - | 109.19 | 0.099 | 0.099 | Part | - | - | - | - | 2019000432 | 202000780
2 | 400kV | L-18-04 | Sita Rama LI Scheme | 1) 400/220/11kV Kamalapuram LI-SS, 2) 400kV Julurupadu - Kamalapuram TMDC Line, 3) 220/11kV V.K.Ramavaram LI-SS, 4) 220/11kV B.G.Kothur LI-SS, 5) LILO of 220kV KTS – Lower Sileru-I Line at 400/220 kV Asupaka SS, | Bulk Load & DC Works | 449 & 450 Dated 10.10.2019 | 41st Meeting of SCPSPSR dated 22.09.2017 | N/A | - | Sep' 2018 | - | May, 2023 | 28.04.2023 | 100% Consumer Contribution |  |  |  | - | 263.72 | -0.27 | 45.254 | Part | - | - | - | - | 2020000587 2021000025 2021000026 2021000177 2022000392 2023000327 2023000328 2023000329 2023000353 2023000354 | 202000375 202100163 202100165 202100166 202200361 2023000423 2023000421 2023000422 2024000320 2023000420
6) LILO of 220kV KTS - Asupaka Line to 220kV V.K.Ramavaram LI SS, 7) 220kV Kamalapuram - V.K. Ramavaram TMDC Line, 8) LILO of one circuit of 220kV KTPS-Manuguru Line to B.G.Kothur, 9) LILO of one circuit of 220kV KTPS V-Lower Sileru -II Line to B.G.Kothur
Total : | [18 empty] | 372.91 | -0.171 | 45.353
Chief Engineer/ 400kV
Note : Project Purpose : System Improvement (SI), System Expansion (SE), System Replacements (SR)/ RMI, Generation Evacuation (GE)
The statement to be printed on A3 size sheets please

## CapEx-Lis 25-26
TRANSMISSION CORPORATION OF TELANGANA LIMITED
Annual Petition for 2024-25 for Transmission Business filed with TGERC
Scheme wise details of Capital Expenditure proposed for Financial Year 2025-26
400kV Lift Irrigaiton Schemes:
Sl No. | Project Code / Scheme ID (SAP Code) | Project Title (SAP Project title) | Scope of work (Names of all the Sub-stations and Lines included in the scheme maybe given) | Justification | Project Purpose (SI/SE/ SR/GE) | Administrative Approval TOO Ref. | SRPC approval (if any) | TGERC Investment Approval Ref. | Total TGERC approved Cost (in Cr) | Source of funds |  |  |  | Proposed Project Start Date DD-MM-YY | Proposed Project Completion Date DD-MM-YY | CWIP O.B. | FY:2024-25 |  |  | Projected expenditure for 2025-26 | Spill over Yearly Capital Expenditure projected for works taken up in or before 2025-26 (in Cr) |  |  | Total Cumulative Expenditure (in Cr) | Present Status of work
[10 empty] | TGTransco funds | Loan source | Loan Amount | Grants, if any |  |  |  | 1st Half (Apr-Sept) (Actuals) | 2nd Half (Oct-Mar) (Projected) | Total 24-25 (Projected) |  | 2026-27 | 2027-28 | 2028-29
1 | 2 | 3 | 4 |  | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 |  |  |  | 17 | 18 | 19 | 20 | 21 | 22
I. Ongoing Schemes as on 01.04.2025 :
| L-18-04 | Sita Rama Lift Irrigaiton Scheme | 1) 400/220/11kV Kamalapuram LI SS, 2) 220/11kV B.G.Kothur LI SS, 3) 220/11kV V.K.Ramavaram LI SS, 3) 400kV Julurupadu - Kamalapuram TMDC Line, 4) LILO of one circuit of 220kV KTPS-Manuguru Line to B.G.Kothur, 5) LILO of one circuit of 220kV KTPS V-Lower Sileru -II Line to B.G.Kothur, 6) LILO of 220kV KTS – Lower Sileru-I Line at 400/220 kV Asupaka SS, 7) LILO of 220kV KTS - Asupaka Line to 220kV V.K.Ramavaram LI SS, 8) 220kV TMDC Line from 400/220/11kV Kamalapuram SS to 220/11 kV V.K.Ramavaram | All works were commissioned. | Bulk Load & DC Works | 449 & 450 Dated 10.10.2019 | 41st Meeting of SCPSPSR dated 22.09.2017 | - | - | I&CAD, Govt.of TG Funds |  |  |  | Sep' 2018 | May, 2023 | 12.77 | 5.82 | 0 | 5.82 | 0 | 0 | 0 | 0 | 327.958
Sub-total-I |  |  |  |  | Grants, if any 16: 12.77 | 5.82 | 0 | 5.82 | 0 | 0 |  |  | 327.958
II. New schemes taken up during 2025-26 (Will be taken up on payment of amonuts by Third parties) :
1 | D-23-01 | Re-alignment of 400kV BTPS to Julurpadu 400kV QMDC Line | Raising/re-aligning Towers of existing 400kV QMDC Line from BTPS (Manuguru) to Julurupadu SS for Sitamma Sagar Multi-Purpose Project | Proposed at the request of Irrigation Department, Kothagudem. | S R (Partial) | - | - | - | - | Rs.166.04 Cr. DC Work |  |  |  | April, 2025 | Sept., 2026 | 0 | 0 | 0 | 0 | 83.02 | 83.02 | 0 | 0 | 166.04 | Tendering will be initiated only after reciving payment from I&CAD department, Govt. of Telangana
2 | - | Extension of 132kV Power Supply to P.S.No.4 of SRLIP at Dibbagudem | 1) 132/11 kV Dibbagudem Substation; 2) LILO from 132kV Ashwaraopeta – Gangaram Line to Dibbagudem; 3) LILO from 132kV Penuballi – Kalluru Line to Gangaram 132/33kV SS; and associated Bays | Already approved vide 29.12.2023 Resource Plan for 5th CP. | S E | 1230 & 1231 Dated 02.11.2021 | - | - | - | Rs.48.65 Cr. Bulk Load & DC Works |  |  |  | April, 2025 | March, 2027 | 0 | 0 | 0 | 0 | 14.595 | 34.055 | 0 | 0 | 48.65
Sub-total-II | [16 empty] | 0 | 0 | 0 | 97.615 | 117.075 | 0 | 0 | 214.69
III. Non-plan schemes taken up during 2025-26 : - Nil -
Sub-total-III
Grans Total I + II + III |  |  |  |  | Grants, if any 16: 12.77 | 5.82 | 0 | 5.82 | 97.615 | 117.075 | 0 | 0 | 214.69
Chief Engineer/ 400kV
Note : Project Purpose : System Improvement (SI), System Expansion (SE), System Replacements (SR)/ RMI, Generation Evacuation (GE)
The statement to be printed on A3 size sheets please
4) 1 No. Transformer Bay at 220/132kV Ashwarao peta; 5) 2 Nos. 132kV Bays at existing 132/33kV SS Gangaram
| S-15-13 | 765kV Wardha– Hyderabad Link Transmission Scheme | 1) 400/220kV Maheshwaram; 2) 400kV QMDC Line from Maheshwaram 765/400kV (PGCIL) SS; 3) 400kV Maheswaram - Shankarapally TMDC Line; 4) 400/220/132kV Kethireddypalli SS; 5) LILO of 400kV Shankarpally-Suryapeta QMDC Line to 400kV Kethireddy-palli SS; 6) 400kV QMDC line from 400kV Dichpally SS to 400kV Nirmal SS; 7) LILO of 400kV Dindi-Mamidipally TMDC Line to 400kV Maheshwaram SS |  | S I | 146/ 05.08.2015 30/ 04.10.2016 105/ 15.07.2017 | 36th & 37th SCPSPSR Meetings dtd. 04.09.2013 & 31.07.2014 respectively | 16/17-2017-18, Dt.19.12.2017 | 1178.97 | 177.32 | PFC | 1001.65 | - | Nov' 2015 | Mar' 2022 |  | -4.798
Note on J33: DELL: Excluding IDC of Rs.100.08 Crore Total incl. IDC Rs.1279.05