## ARR 2025-26
TRANSMISSION CORPORATION OF TELANGANA LIMITED
Annual Petition for 2025-26 for Transmssion Buisiness filed with TGERC
2.Scheme wise details of Capital Expenditure proposed for Financial Year 2024-25
Sl.No. | Project Code/Scheme ID(SAP code) | Project Title(SAP Project Title) | Scope of the Work (names of all the substations and Lines included in the scheme given) | Justification | Project Purpose(SI/SE/SR/GE) | Administrative Approval T.O.O Ref | SRPC Approval (if any) | TGERC Investment Approval Ref. | Total TGERC Approved Cost | Source of Funds |  |  |  | Project Start Date (DD-MM-YY) | Project Completion date (DD-MM-YY) | Opening CWIP as on 31.03.204 | FY 2024-25 |  |  | Projected Expenditure for FY 2025-26 | Spill Over Yearly Caital Expenditure Projected for works taken up in or before 2025-26 (in Cr) |  |  | Total Cumulative Expenditure (in Cr) | Present Status of Work
[10 empty] | TGTransco Funds | Loan Source | Loan Amount | Grants if any |  |  |  | 1 st Half (Apr-Sept) Actuals | 2nd Half (Oct-Mar) Projected | Total 24-25 Projected |  | 2026-27 | 2027-28 | 2028-29 |  |  | Scheme Purpose | Year | Opening CWIP | CWIP Addition during the year
1 | 2 | 3 | 4 |  | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 (17+18) | 20 | 21 | 22 | 23 | 24 | 25
ONGOING SCHEMES AS ON 01.04.2025
1 | D-15-03 L-15-02 L-15-03 L-15-04 L-16-02 L-16-03 L-16-05 | Kaleshwaram Lift Irrigation Project (*) | i)400/11 KV Medaram GIS and 400KV QMDC Line from 400KV RAMADUGU SS to the proposed 400KV MEDARAM SS-42 CKM ii)400/13.8/11 kV Ramadugu SS and 400kV QMDC Line for making LILO of both the circuits of 400kV SCCL-Gajwel QMDC line to Ramadugu SS in Karimnagar District (2x18KM)-72 CKM iii)400/220/11 kV Sundilla SS and 400kV QMDC Line for making LILO of both the circuits of 400kV SCCL – Nirmal QMDC line to proposed Sundilla SS (2x3 KM)-12CKM iv) 400/11 KV Medaram GIS and 400KV QMDC Line from 400KV RAMADUGU SS to the proposed 400KV MEDARAM SS- 21 KM-42CKM v) 400/11 kV Tippapur SS and 400kV QMDC Line from Ramadugu SS to Tippapur 46 KM-92CKM vi)400/11 kV Chandulapur SS , 400kV LILO of both the circuits of 400 KV TMDC Gajwel- Bhoopalapally Line-108.36 CKM and 400 KV QMDC Line from Tippapur 400/11 KV SS to proposed Chandulapur 400/13.8/11 KV SS -38.226 CKM vii)220/11 kV Medigadda SS and 220kV TMDC Line from Sundilla 400/220/11 KV to Medigadda KV SS - 148.76 CKM viii)220/11 kV Annaram SS and 220kV TMDC Line from 400/220/11kV Sundilla Pump House SS (Yellampally SS) to proposed 220/11kV SS at Annaram Pump House -58 CKM viii)132/11 kV Malakpet SS and 132KV DC Line from 220/33 KV Sircilla Substation (Sripada Yellampally SS) to proposed 132/11kV SS at Malakpet -22.7CKM | Works completed. Expenditure was carried over from 4 th control period due to delay in disbursement of funds from I&CAD | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O.(CE-LIS) Ms.No.848, dt:18.09.2020 (BL Works) T.O.O.(CE-LIS) Ms.No.849, dt: 18.09.2020 (DC Works) |  |  |  |  | Govt. of TS Grants I&CAD | 3086.446 | Govt. of TS Grants I&CAD | 2016-08-01 | Apr`23 | 0.68 | 0.15334 | 11.56 | 11.7133 | 2 | 0 | 0 | 0 | 14.3933 | Works completed. Expenditure was carried over from 4 th control period due to delay in disbursement of funds from I&CAD
i)400KV SUPPLY TO MYADARAM/RAMADUGU/TIPPA ii) 400KV SUPPLY TO TIPPAPUR iii) 400KV SUPPLY TO MYADARAM iv) 400KV SUPPLY TO RAMADUGU MANDAL v)ERECTION OF CHANDULAPUR LISS (KLIS) vi)ERECTION OF TUKKAPUR LISS (KLIS)
2 | L-20-01 | KLIS ADDITIONAL 1 TMC-BL | 1.400/11 kV Velgatoor Sub-station and 400kV QMDC Line from 400kV Kachapur Switching station to 400/11kV Velgatoor SS -49.4 CKM 2.400/11 kV Pegadapally (Namapur) Sub-station and (i) 400kV QMDC Line from 400kV Kachapur Switching station to 400/11kV Namapur SS -30.28 CkM (ii) 400kV QMDC Line from 400kVVelgatoor substation to 400/11kV Namapur SS -43.48 CkM 3.400KV Kachapur Switching Station, (i) LILO of 400kV STPP Jaipur - Ramadugu QMDC line to Nampur SS - 19.14 CkM (ii) 400kV QMDC Line 400kV Kachapur Switching station - 400/220/132kV Gajwel SS -14.456 CkM and (iii)LILO of 400kV QMDC Line from NTPC to 400kV Narsapur SS -7.816 CkM 4.400 /11 kV Veljipur Sub-Station and 400 KV QMDC line 400/11 KV Tippapur SS - 400/11 KV Veljipur SS -10.2 CKM 5.400/11 kV Chinagundavelli (Yellaipally) Sub-Station and 400kV QMDC Line from existing 400/13.8/11kV Chandulapur SS to Proposed 400/11kV Yellaipally SS -19.096 CKM 6.400/11 KV New Tukkapur SS and Bays 7.400/220 kV Annaram Sub-Station and 400 KV QMDC line from STPP(Jaipur) to proposed 400 KV SS at Annaram Works -40.344 CKM 8.400 kV QMDC Line from 765/400kV Nizamabad PGCIL SS to 400/13.8/11kV Chandlapur SS -187.996 CKM | Works stopped and were carried over from 4 th control period due to delay in disbursement of funds from I&CAD. | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O.(CE-LIS) Ms.No.848,dt:18.09.2020 (BL Works) T.O.O.(CE-LIS) Ms.No.849,dt:18.09.2020(DC Works) |  |  |  |  | Govt. of TS Grants I&CAD | 2946.53 | Govt. of TS Grants I&CAD | Oct'21 | Mar`26 | 887.2246 | 22.3 | 50 | 72.3 | 400 | 650 | 379.5 | 50 | 2439.0246 | Works were carried over from 4 th control period due to delay in disbursement of funds from I&CAD.
KLIS ADDITIONAL 1TMC - DC Works
D-20-08
3 | L-14-02 | Kaleshwaram PKGS-20,21&22(*) | 1.220/11kV Sarangapur SS and 220 kV DC Line from 400/220 kV Ditchpally SS to proposed 220/11 kV Sarangapur SS-65.88 CKM 2. 220/11kV Manchippa SS and 220kV DC line from 400/220 kV Dichpally SS to 220/11 kV Manchippa SS -48.352 CKM 3.220/11kV Yacharam Thanda SS and 220 KV TMDC line 400/220kV Dichpally SS - 220/11 kV Yacharam Thanda SS -53.804 CKM | Works were carried over from 4 th control period due to delay in disbursement of funds from I&CAD. | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O. (CE-LI) Ms.No.02, dt:22-01-2014(BL Works) T.O.O. (CE-LI) Ms.No. 03, dt:22-01-2014(DC Works) |  |  |  |  | Govt. of TS Grants I&CAD | 264.82 | Govt. of TS Grants I&CAD | Jan'19 | Mar'25 | 111.31 | 1.28 | 1.1 | 2.38 | 10 | 1 | 0 | 0 | 124.69 | Works were carried over from 4 th control period due to delay in disbursement of funds from I&CAD.
|  | 220/11kV Sarangapur, 220/11kV Manichippa, 220/11kV Yacharamthanda |  |  | 6: T.O.O.(ED-LIS) Ms.No.787,dt:23.06.2020(BL Works) T.O.O.(ED-LIS) Ms.No.788,dt:23.06.2020 (DC Works)
4 | L-19-01 | Kaleshwaram Lift Irrigation Schemes(*) | 1. 220/33KV New Manchippa and 33kV DC line from New Manchippa Substation to proposed 33/11kV Ghadkol Substation- 8 CKM 2. 220/11 kV Mentrajpally SS and 220 KV LILO Line to proposed Mentrajpally from one of the circuit of under construction 220 KV DC Line from 400/220 kV SS Dichpally to 220/11 KV Manchippa SS in Nizamabad Dist.-7.517 CKM | Works were carried over from 4 th control period due to delay in disbursement of funds from I&CAD. | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O.(CE-LIS) Ms.No.415,dt:24.07.2019 (BL Works) |  |  |  |  | Govt. of TS Grants I&CAD | 67.77 | Govt. of TS Grants I&CAD | 2020-03-20 | Mar`25 | 4.3 | 0.21 | 2 | 2.21 | 4 | 0 | 0 | 0 | 10.51 | Works were carried over from 4 th control period due to delay in disbursement of funds from I&CAD.
|  | 220/11 kV New Manchippa SS and 220/11 kV New Mentrajpally SS |  |  | 6: T.O.O.(CE-LIS) Ms.No.416,dt:24.07.2019(DC Works)
5 | L-18-01 | JCR Phase-III 220/11kV Devvanapeta SS(**) | 220/11 kV Devannapeta SS and 220kV Twin Moose DC line from 400/220kV Jangaon Sub-Station to 220/11kV Devannapet Sub-Station -108.519 CKM | Works completed. Expenditure was carried over from 4 th control period due to delay in disbursement of funds from I&CAD | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O.(ED-LIS) Ms.No.765,dt:22.05.2020 (BL Works) T.O.O.(ED-LIS) Ms.No.766,dt:22.05.2020 (DC Works) |  |  |  |  | Govt. of TS Grants I&CAD | 138.66 | Govt. of TS Grants I&CAD | Dec-19 | Jun 24 | 0.17 | -0.47 | 5 | 4.53 | 5 | 0 | 0 | 0 | 9.7 | Works completed. Expenditure was carried over from 4 th control period due to delay in disbursement of funds from I&CAD
220/11kV Devvanapeta SS
6 | L-13-02 | Kaleshwaram Lift Irrigation Scheme OLD(*) | 132/11 kV Kannepalli SS and 132 kV DC/SC line from Kataram to Kanepalli and 1 No. 132 kV Bay Extension at Kataram SS-18.007CKM | Works completed. Supply extended to I&CAD Pump House. Expenditure was carried over from 4 th control period due to delay in disbursement of funds from I&CAD. | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O. (CE -LIS) Ms.No.884,dt:19.11.2020 (BL Works) T.O.O. (CE -LIS) Ms.No.885,dt:19.11.2020 (DC Works) |  |  |  |  | Govt. of TS Grants I&CAD | 28.77 | Govt. of TS Grants I&CAD | 2016-12-01 | Jun`20 | 0 | 0.018 | 0.5 | 0.518 | 0 | 0 | 0 | 0 | 0.518 | Works completed. Supply extended to I&CAD Pump House. Expenditure was carried over from 4 th control period due to delay in disbursement of funds from I&CAD.
132/11kV Beersagar(Kannepalli) LIS
7 | L-15-01 | AMRP LLC Lift Irrigation Project at Puliathanda(*) | 1. 2nd Circuit stringing on 220KV Chalakurthy-Puttamgandi line(18.63 KM) and DC line from location no.9 of Chalakurthy-Puttamgandi 220KV line to the proposed 220KV SS at Puliathanda (2 KM) 2. 220kV DC/SC line from 220KV Chalakurthy-Puttamgandi line (18.63 KM) | Works completed. | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | [5 empty] | Govt. of TS Grants I&CAD | 3.37 | Govt. of TS Grants I&CAD | 2016-01-16 | Nov`16 | 0.0012 | 0.02 | 0 | 0.02 | 0 | 0 | 0 | 0 | 0.0212 | Works completed.
8 | L-17-04 | Kaleshwaram Lift Irrigation Scheme- Package -14(*) | 1. 220kV TMDC line from 400/220/132 KV Gajwel SS to 220/11kV Akkaram SS | Works completed. Supply extended to I&CAD Pump House. Expenditure was carried over from 4 th control period due to delay in disbursement of funds from I&CAD. | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O. (CE-LIS) Ms.No. 369,dt.28-05-2019 (BL Works) |  |  |  |  | Govt. of TS Grants I&CAD | 197.66 | Govt. of TS Grants I&CAD | 2018-04-01 | Sep'24 | 2.75 | -0.794 | 4 | 3.206 | 1 | 0 | 0 | 0 | 6.956 | Works completed. Supply extended to I&CAD Pump House. Expenditure was carried over from 4 th control period due to delay in disbursement of funds from I&CAD.
|  | (Akkaram & Markook) | 2. 220kV DC line from 220/11kV Akkaram SS to 220/11kV Markook SS |  | 6: T.O.O. (CE-LIS) Ms.No.370,dt.28-05-2019 (DC Works)
9 | L-18-03 | Thumilla Lift Irrigation (RDS) (*) | 132/11 kV Thumilla SS ,132 kV LILO line to proposed Tummilla 132/11 kV SS to be tapped from IEEJA to Alampur 132 kV DC line at the point of 15 KM from IEEJA 132/33kV SS-17.384 CKM 2)Stringing of Second circuit 132/33KV SS to Alampur 132/33kV SS under 1st circuit -41.849 CKM | Works completed. Supply extended to I&CAD Pump House. Expenditure was carried over from 4 th control period due to delay in disbursement of funds from I&CAD. | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O. (CE -LIS) Ms.No.985,dt:26.02.2021(BL Works) |  |  |  |  | Govt. of TS Grants I&CAD | 34.3 | Govt. of TS Grants I&CAD | Jun'18 | Aug`19 | 1.74 | -0.0042 | 0.6 | 0.5958 | 0 | 0 | 0 | 0 | 2.3358 | Works completed. Supply extended to I&CAD Pump House. Expenditure was carried over from 4 th control period due to delay in disbursement of funds from I&CAD.
|  | 132/11kVThumilla |  |  | 6: T.O.O. (CE -LIS) Ms.No.986,dt:26.02.2021(DC Works)
10 | L-17-05 | PRLIS(*) Diversion of 3Nos. 220kV lines due to submerging in the proposed Anjanagiri Project | Diversion of 3Nos. 220kV lines due to submerging in the proposed Anjanagiri Project | Works completed. Supply extended to I&CAD Pump House. | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O. (CE-Projects-II) Ms.No.15 Dt.09-06-2017 (DC Works) |  |  |  |  | Govt. of TS Grants I&CAD | 18.23 | Govt. of TS Grants I&CAD | May'18 | Dec`20 | 0.0007 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0.0007 | Works completed. Supply extended to I&CAD Pump House.
0.1
11 | L-05-02 | Godavari LIS (*) (a) (132/11kV Gandiramaram, 132/11kV Bommakuru, 132/11kV Rangaraopalli) | 1. 132/11 kV Gandiramaram SS and 132kV DC/SC line from existing 132/33kV Raghunathpalli SS to the proposed 132/11kV SS at Gandiramaram -16.6 CKM 2. 132/11 kV Bommakur SS and 132KV second circuit stringing from Janagoan to Narmetta- 16.6 CKM and LILO to 132/11 KV Bommakur-6 CKM 3. 132/11 kV Rangaraopally SS and 132kV LILO to the proposed 132/11kV SS Rangaraopally tapping from the existing 132kV Mulugu - chelpur line -0.754CKM | Works completed. Expenditure was carried over from 4 th control period due to delay in disbursement of funds from I&CAD. | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O. (CE-Projects-I) Ms. No.19,dt:23-05-2016(BL Works) T.O.O. (CE-Projects-I) Ms. No.20,dt:23-05-2016(DC Works) |  |  |  |  | Govt. of TS Grants I&CAD | 97 | Govt. of TS Grants I&CAD | 2017-04-01 | Oct`19 | 1.31 | 0.1576 | 0 | 0.1576 | 0 | 0 | 0 | 0 | 1.4676 | Works completed. Expenditure was carried over from 4 th control period due to delay in disbursement of funds from I&CAD.
12 | L-17-03 | Lift Irrigation Scheme along Flood Flow Cancal(*) | 1. 220/11 kV Rampur SS, 220 KV Line from Ramadugu to Rampur -70 CKM . 2 No's Bays at Rampur and LILO of 220KV RSS - Bheemgal Feeder to 220/11 KV Rampur SS Under FFC -0.92 CKM 2. 220/11 kV Rajeshwarrao Peta SS and 220kV DC line (36KM) from proposed 220kV Rampur Substation to proposed 220/11kV Rajeshwar Rao Peta Substation-72 CKM 3. 220/11 kV Mupkal SS and 220kV LILO line from 220kV Nirmal – Renjal line to proposed 220/11kV Mupkal Substation-0.676 CKM | Works completed.Expenditure was carried over from 4 th control period due to delay in disbursement of funds from I&CAD | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O.(ED-LIS ) Ms.No.749,dt:15.04.2020(BL Works) T.O.O.(ED-LIS ) Ms.No.750,dt:15.04.2020 (DC Works) |  |  |  |  | Govt. of TS Grants I&CAD | 186.9 | Govt. of TS Grants I&CAD | Feb-18 | JUN`20 | 0.0916 | -0.0856 | 1 | 0.9144 | 0 | 0 | 0 | 0 | 1.006 | Works completed. Expenditure was carried over from 4 th control period due to delay in disbursement of funds from I&CAD.
220/11 kV Rampur SS, 220/11kV Rajeswerraopeta SS, 220/11kV Mupkal SS
13 | L-17-01 | Chanaka Korata LIS(*) | 132/11 kV Hathigat SS , 132kV DC line from existing132/33kVSS at Adilabad to the proposed 132/11kVSS at Hathigat SS in Adilabad District -30 CKM and 132kV LILO Line to 220/132/33kV SS, Nirmal from 132kV Pochamapad – Adilabad feeder -6.172 CkM | Works completed. Expenditure was carried over from 4 th control period due to delay in disbursement of funds from I&CAD. | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O. (CE -LIS) Ms.No.925, dt:15.12.2020 (BL Works) T.O.O. (CE -LIS) Ms.No.926, dt:15.12.2020 (DC Works) |  |  |  |  | Govt. of TS Grants I&CAD | 43.49 | Govt. of TS Grants I&CAD | Apr-17 | Mar`19 | 0.19 | 0.0239 | 1 | 1.0239 | 0 | 0 | 0 | 0 | 1.2139 | Works completed. Expenditure was carried over from 4th control period due to delay in disbursement of funds from I&CAD
132/11kV Hatighat
14 | D-11-05 L-11-01 | Thotapally Reservoir to Gouravelly Reservoir LIS (220/132kV Huzurabad SS and CL)(*) | 1. 132/11 kV Regonda SS and 132kV DC line from 220/132kV Huzurabad Sub-Station to proposed 132/11kV Sub-Station at Regonda (Gouravelly) -63 CKM | Works completed. Expenditure was carried over from 4th control period due to delay in disbursement of funds from I&CAD. | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O.(CE-LI) Ms.No.384,dt:19.01.2012 T.O.O.(CE-LI) Ms.No.149, dt:11.07.2011 |  |  |  |  | Govt. of TS Grants I&CAD | 69.7031 | Govt. of TS Grants I&CAD | Feb-15 | Mar`22 | 0.068 | 0.0053 | 0.5 | 0.5053 | 0 | 0 | 0 | 0 | 0.5733 | Works completed. Expenditure was carried over from 4th control period due to delay in disbursement of funds from I&CAD.
2. 220/132 kV Huzurabad SS and 220kV LILO line to Huzurabad from 220 kV Durshed - Oglapur line-20.54 CKM
15 | L-18-02 | PH-III PACKAGE -II JCRDGLIS-220/11 BHEEMG | Augmentation at 220/11kV Bheemghapur SS | Works completed | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O. (ED -LIS) Ms.No. 10,dt:17.04.2018 (BL&DC Works) |  |  |  |  | Govt. of TS Grants I&CAD | 23.55 | Govt. of TS Grants I&CAD | 2018-06-01 | Aug`19 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | Works completed
16 | L-14-01 | Lift Irrigation Scheme at Jogapur | 132/11 kV Jogapur SS and 132 kV DC/SC Line from 132/33kV Mallaram SS to Proposed 132kV Jogapur SS (13 KM) | Works completed | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O. (CE-Trans&LI) Ms.No.16,dt:01-09-2014 (BL Works) |  |  |  |  | Govt. of TS Grants I&CAD | 45.12 | Govt. of TS Grants I&CAD | 2016-12-16 | May`18` | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Works completed
|  | 132/11kV Jogapur SS |  |  | 6: T.O.O. (CE-Trans.&LI) Ms.No.15,dt:01-09-2014 (DC Works)
17 | L-16-04 | Dr. BRAPCSS LIS (Kanakapur) | 132/11 kV Kanakapur SS and 132kV DC/SC line from existing 132/11kV Kosli Substation to the proposed 132/11kV Kanakapur LIS Substation -20 CKM | Works completed. Supply not extended due to non competion of I&CAD works. Expenditure was carried over from 4th control period due to delay in disbursement of funds from I&CAD. | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O. (CE-Projects-I) Ms.No.04,dt:26 -02-2016 (BL Works) T.O.O. (CE-Projects-I) Ms.No.05,dt.26 -02-2016 (DC Works) |  |  |  |  | Govt. of TS Grants I&CAD | 31.74 | Govt. of TS Grants I&CAD | 2016-12-01 | Nov`18 | 0.042 | 0 | 0.3 | 0.3 | 0 | 0 | 0 | 0 | 0.342 | Works completed. Supply not extended due to non competion of I&CAD works. Expenditure was carried over from 4th control period due to delay in disbursement of funds from I&CAD.
132/11kV Kanakapur
18 | L-13-02 | Kaleshwaram Lift Irrigation Scheme OLD(*) | 132/11 kV Kannepalli SS and 132 kV DC/SC line from Kataram to Kanepalli and 1 No. 132 kV Bay Extension at Kataram SS-18.007CKM | Works completed. Supply extended to I&CAD Pump House. Expenditure was carried over from 4th control period due to delay in disbursement of funds from I&CAD. | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O.CE(LIS)Ms.No. 884, 885 dt.19.11.2020 |  |  |  |  | Govt. of TS Grants I&CAD | 31.39 | Govt. of TS Grants I&CAD | 2016-12-01 | Jun`20 | 0 | 0.018 | 0.5 | 0.518 | 0 | 0 | 0 | 0 | 0.518 | Works completed. Supply extended to I&CAD Pump House. Expenditure was carried over from 4th control period due to delay in disbursement of funds from I&CAD.
132/11kV Beersagar(Kannepalli) LIS
19 | L-19-02 | Phase – III Godavari Lift Irrigation Sch | Suply Erect 132/33-11 kV RS Ghanpur SS and 132kV LILOLine - RS Ghnpr tap Drsgr-Rgnty | Works completed. Supply Not extended to I&CAD Pump House. Expenditure was carried over from 4th control period due to delay in disbursement of funds from I&CAD. | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O.(ED-LIS ) Ms.No.749,dt:15.04.2020(BL Works) ,T.O.O.(ED-LIS ) Ms.No.750,dt:15.04.2020 (DC Works) |  |  |  |  | Govt. of TS Grants I&CAD | 0 | Govt. of TS Grants I&CAD | `Mar`20 | Mar`22 | 0 | 0.0865 | 0 | 0.0865 | 0 | 0 | 0 | 0 | 0.0865 | Works completed. Supply Not extended to I&CAD Pump House. Expenditure was carried over from 4th control period due to delay in disbursement of funds from I&CAD.
Sub-Total(I) |  |  |  |  | 1 st Half (Apr-Sept) Actuals 17: 22.9188; 2nd Half (Oct-Mar) Projected 18: 78.16 | 100.9788 | 422 | 651 | 379.5 | 50 | 2613.407
II.New Schemes taken up during 2025-26 | bar: Grants if any 15
1 | L-23-01 | Kaleshwaram Lift Irrigation Scheme | (i) Erection of 132 kV DC line-5.2 CKM from LILO point at Loc.No.83 of 132 kV Kataram-Beersagar line to the existing 220/11 kV Medigadda SS (ii) Stringing of 2nd Corcuit on existing 132 kV DC/SC Kataram-Bersagar Lift Irrigation Substation-18.007 CKM | These are Deposit contribution works. Works will be taken up as per requirement of I&CAD. Already approved vide resource plan for 5th CP (Amount in Resource plan was communicated without GST and Bays at Beersagar was not included in resource plan) . | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O. (CE -LIS) Ms.No.1557 Dt:21.01.2023 |  |  |  |  | Govt. of TS Grants I&CAD | 55.7786 | Govt. of TS Grants I&CAD | `Sep`25 | `Mar`28 | 0 | 0 | 0 | 0 | 5 | 28.427 | 17.44 | 5 | 55.867 | Tenders will be called after reciept of payments from I&CAD .
Alternate Route to Medigadda -Lines and Bays
2 | L-21-01 | CHITYALA & WADAPALLY LIS | (i)132/11KV Chityala Sub-station and DC/SC line from Haliya 132/33KV - -28CKM (ii) 132/11KV Wadapally Sub-station and DC/SC line from Wadapally(existing) 132/33KV - 12 Ckm and DC/SC line from Chityala to Wadapally -22 CKM | These are Deposit contribution works. Works will be taken up as per requirement of I&CAD. Already approved vide resource plan for 5th CP (Amount in resource plan was communicated without GST). | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O. (CE -LIS) Ms.No. 362 & 363 Dt:13.05.2019 |  |  |  |  | Govt. of TS Grants I&CAD | 67.13 | Govt. of TS Grants I&CAD | `Apr`25 | `Mar28 | 0 | 0 | 0 | 0 | 2 | 33 | 30.13 | 2 | 67.13 | Tenders will be called after reciept of payments from I&CAD .
| D-21-01 | a)132/11kV Chityala SS,Connected Lines and Bays b)132/11kV Wadapally SS,Connected Lines and Bays
3 | L-21-06 | KAMBALAPALLY LIS | 132/11KV SS at Kambalapally and DC line from existing 220KV K.M. Pally SS -96 CKM | These are Deposit contribution works . Works will be taken up as per requirement of I&CAD . Already approved vide resource plan for 5th CP(Amount in resource plan was communicated without development charges). | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O. (CE -LIS) Ms.No.1234 & 1235 Dt:10.11.2021 |  |  |  |  | Govt. of TS Grants I&CAD | 94.42 | Govt. of TS Grants I&CAD | `Apr25 | Mar`28 | 0 | 0 | 0 | 0 | 5 | 42 | 42.42 | 5 | 94.42 | Tenders will be called after reciept of payments from I&CAD .
| D-21-40 | 132/11kV Kambalapally SS ,Connected Lines and Bays
4 | L-21-05 | AMBA BHAVANI LIS | 132/11KV SS at Amba Bhavani and LILO line from proposed Kambalapally SS to K.M.Pally SS -2CKM | These are Deposit contribution works. Works will be taken up as per requirement of I&CAD. Already approved vide resource plan for 5th CP(Amount in resource plan was communicated without development charges). | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | [5 empty] | Govt. of TS Grants I&CAD | 17.28 | Govt. of TS Grants I&CAD | 2024-04-25 | Mar`29 | 0 | 0 | 0 | 0 | 2 | 8.28 | 5 | 2 | 17.28 | Tenders will be called after reciept of payments from I&CAD .
| D-21-39 | 132/11kV Ambabhavani SS,Connected Lines and Bays
5 | L-21-02 | NELLIKAL LIS | 132/11KV SS at Nellikal and LILO line from existing Nagarjuna sagar Receiving station to Nagarjuna sagar Left canal SS - -3CKM | These are Deposit contribution works. Works will be taken up as per requirement of I&CAD . Already approved vide resource plan for 5th CP (Amount in resource plan was communicated without development charges). | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O. (CE -LIS) Ms.No.1161 & 1162 Dt:16.08.2021 |  |  |  |  | Govt. of TS Grants I&CAD | 21.8 | Govt. of TS Grants I&CAD | 2024-04-25 | Mar`29 | 0 | 0 | 0 | 0 | 2 | 10.8 | 7 | 2 | 21.8 | Tenders will be called after reciept of payments from I&CAD .
| D-21-25 | 132/11kV Nellikal SS ,Connected Lines and Bays
6 | L-22-02 | SANGAMESHWARA LIS | (A) 220/11kv LI Sub-Station at Chelmeda Khurd, i) New 220kV DC line from existing 220/132kV Sadasivapet SS to now proposed 220/132/11kV SS at Chelmeda Pump House for a line length of 25 CKM and ii) Replacement of existing 220kV DC line of single Moose conductor from 400/220kV Shankarpally SS to 220/132kV Sadasivapet SS with HTLS Conductor (520mm2 ACCC) for a line length of 38.0KM. (B) 132/11 KV LI SS at Hoti Khurd and 132 kV DC Line from proposed 220/132/11 kV LI SS at Chelmeda Khurd pump house to now proposed 132/11 KV Hoti - Khurd LI SS-56CKM | These are Deposit contribution works. Works will be taken up as per requirement of I&CAD . Already approved vide resource plan for 5th CP. Later, Scheme was revised as per requirement of I&CAD and same was communicated to I&CAD vide letter dtd:03.08.2023. | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O. (CE -LIS) Ms.No.1418 & 1419 Dt:22.06.2022 |  |  |  |  | Govt. of TS Grants I&CAD | 222.51 | Govt. of TS Grants I&CAD | 2024-04-25 | Mar`29 | 0 | 0 | 0 | 0 | 2 | 125 | 92.81 | 2.7 | 222.51 | Tenders will be called after reciept of payments from I&CAD .
| D-22-08 | (i)220/132/11 kV Chelmada SS Connected Lines and Bays (ii)132/11 kV Hotikurd SS,Connected Lines and Bays
7 | L-22-03 | BASAVESHWARA LIS | (A) 220/132/11kV LI Sub-Station at Borancha, i)Erection of new 220kV SMDC line from existing 400/220kV Narsapur SS to now proposed 220/132/11kV SS at Borancha Pump House for a line length of 146 CKM ii) Erection of new 220kV SMDC line from proposed 220/132/11kV Chelmeda SS to now proposed 220/132/11kV SS at Borancha for a line length of 80 CKM (B) 132/11kV LI Sub-Station at Ramthirth and 132kV DC line ( 35 KM) to the proposed 132/11KV Ramthirth LI SS from the proposed 220/132/11kV Borancha LI SS. -70CKM | These are Deposit contribution works . Works will be taken up as per requirement of I&CAD . Already approved vide resource plan for 5th CP(Scheme amount in resourceplan was communicated without deveopment charges). | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O. (CE -LIS) Ms.No.1423 & 1424, Dt:27.06.2022. |  |  |  |  | Govt. of TS Grants I&CAD | 361.72 | Govt. of TS Grants I&CAD | 2024-04-25 | Mar`29 | 0 | 0 | 0 | 0 | 2 | 198 | 158.91 | 2.81 | 361.72 | Tenders will be called after reciept of payments from I&CAD .
| D-22-09 | a)132/11 kV Borancha SS b) 132/11 kV Ramrith SS, Connected Lines and Bays
8 |  | MUKTYALA BRANCH CANAL LIS | 132/11KV Sub-station at Vellatur and 132KV DC Line to the proposed Muktyala Branch Canal LIS from existing 220/132KV SS Sithapuram (15KM) -30CKM | These are Deposit contribution works. Works will be taken up as per requirement of I&CAD . Tentaive Scheme cost was approved vide resource plan for 5th CP. The approved Scheme cost was given in the capitalisation proforma. | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | [5 empty] | Govt. of TS Grants I&CAD | 85.25 | Govt. of TS Grants I&CAD | 2024-04-25 | Mar`29 | 0 | 0 | 0 | 0 | 5 | 40 | 35.25 | 5 | 85.25 | Tenders will be called after reciept of payments from I&CAD .
132/11 kV Vellatur SS Connected Lines and Bays
9 |  | NALA SOMANADRI (GATTU) LIS | 132/11 KV LI SS at Rayapuram , LILO line of the proposed 132 kV DC/SC line from 220/132 kV SS Jurala to 132/33 kV SS Ieeja to the proposed 132/11 KV LI SS at Rayapuram -23 CKM and Stringing of 2nd circuit on the existing DC/SC line from 220/132 kV SS Jurala to 132/33 kV SS Ieeja for a line length of 36.27 Ckm | These are Deposit contribution works . Works will be taken up as per requirement of I&CAD . Already approved vide resource plan for 5th CP (Augmentation of Transformers at IEEJA and Jurala not covered in resource plan). | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | [5 empty] | Govt. of TS Grants I&CAD | 95.25 | Govt. of TS Grants I&CAD | 2024-04-25 | Mar`29 | 0 | 0 | 0 | 0 | 5 | 35 | 50.25 | 5 | 95.25 | Tenders will be called after reciept of payments from I&CAD .
132/11 kV Rayapuram SS Connected Lines and Bays
10 | L-22-04 | CHENNURU LIS | 220/11kV LI Sub-Station at Pokkur and 220KV TMDC line from the existing 400/220kV Sundilla SS to 220kV Medigadda LI SS line to execution of 220kV TMDC line-6CKM | These are Deposit contribution works . Works will be taken up as per requirement of I&CAD . Already approved vide resource plan for 5th CP. | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | T.O.O. (CE -LIS) Ms.No.1446 &1447, Dt.03.08.2022. |  |  |  |  | Govt. of TS Grants I&CAD | 56.18 | Govt. of TS Grants I&CAD | 2024-04-25 | Mar`29 | 0 | 0 | 0 | 0 | 2 | 26 | 26.18 | 2 | 56.18 | Tenders will be called after reciept of payments from I&CAD .
| D-22-11 | 220/11 kV Pokkuru SS Connected Lines and Bays
11 |  | MANJEERA LIS | 132/33/11 kV Substation at Waddepally and 132 kV LILO to proposed Waddepally LIS from the existing 132 kV DC Line from 220/132 kV Banswada to 132 kV SS Waddepally -2CKM (PTR :33/11 KV 2X8 MVA,33 kV line-2 KM,33 kV ptlam SS) | These are Deposit contribution works . Works will be taken up as per requirement of I&CAD . Tentaive Scheme cost was approved vide resource plan for 5th CP. The approved Scheme cost was given in the capitalisation proforma. | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | [5 empty] | Govt. of TS Grants I&CAD | 43.82 | Govt. of TS Grants I&CAD | 2024-04-25 | Mar`29 | 0 | 0 | 0 | 0 | 3 | 30 | 8.82 | 2 | 43.82 | Tenders will be called after reciept of payments from I&CAD .
132/33/11 kV Waddepalli SS Connected Lines and Bays
12 |  | Kodangal LIS | (1) 220/11kv LIS substation at Vutkur and 220kV TMDC line from proposed 220/11 kV Budpur substation to proposed 220/11kV Vutkoor pump house for a line length of 56 CKM (2)220/11kv LIS substation at Bhudpur and 220kV TMDC line from existing 400/220 kV Veltoor Substation to proposed 220/11 kV Budpur pump house for a line length of -78 CKM (3) 220/11kv LIS substation at Jayamma Cheruvu, 220kV TMDC line from proposed 220/11 kV Utkoor Substation to proposed 220/11 kV Jayamma Cheruvu pump house for a line length of 30 CKM and 220kV TMDC line from proposed 220/11 kV Jayamma cheruvu Substation to existing 220/132 KV Kosigi substation for a line length of 58 CKM | These are Deposit contribution works . Works will be taken up as per requirement of I&CAD . Narayanpet-Kondangal New Scheme was proposed based on the requirement of I&CAD (Data not approved in Resource plan). | Extension of power supply to Lift Irrigation project taken up by Govt. of TS | [5 empty] | Govt. of TS Grants I&CAD | 561.54 | Govt. of TS Grants I&CAD | 2024-04-25 | Mar`29 | 0 | 0 | 0 | 0 | 100 | 250 | 206.54 | 5 | 561.54 | Tenders will be called after reciept of payments from I&CAD .
220/11kv LIS substation at Vutkur 220/11kv LIS substation at Bhudpur 220/11kv LIS substation at Jayamma Cheruvu,
Sub Total (II) |  |  |  |  | Grants if any 16: 0; 1 st Half (Apr-Sept) Actuals 17: 0; 2nd Half (Oct-Mar) Projected 18: 0 | 0 | 135 | 826.507 | 680.75 | 40.51 | 1682.767
III. Non-Plan Schemes taken up during 2025-26
Sub-Total(III) | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0
Totals I+II+III |  |  |  |  | 1 st Half (Apr-Sept) Actuals 17: 22.9188; 2nd Half (Oct-Mar) Projected 18: 78.16 | 100.9788 | 557 | 1477.507 | 1060.25 | 90.51 | 4296.174
CHIEF ENGINEER
LIFT IRRIGATION SCHEMES (FAC)